## Feature Matrix
HNSW FILTERED VECTOR INDEX — FINAL MASTER FEATURE MATRIX
Feature is the leftmost column. Frontend, Backend, Database and AI/ML are the implementation ownership columns.
Feature | Frontend | Backend | Database | AI/ML
Search UI shell | ✓
Vector query input | ✓
Metadata filters | ✓
Filter UX | ✓
Result list | ✓
Pagination/Top-K | ✓
Debug mode | ✓
Large-result rendering | ✓
Input hardening | ✓
Keyboard/navigation | ✓
E2E search tests | ✓
Client telemetry | ✓
Search service |  | ✓
Search API |  | ✓
Filter DSL |  | ✓
Query validation |  | ✓
HNSW build |  | ✓
HNSW search |  | ✓
Filtered traversal |  | ✓
Pre/post filtering modes |  | ✓
Adaptive efSearch |  | ✓
Deletion/tombstones |  | ✓
Updates |  | ✓
Compaction/rebuild |  | ✓
Index snapshots |  | ✓
Crash recovery |  | ✓
Read/write concurrency |  | ✓
Locking strategy |  | ✓
Sharding |  | ✓
Replication |  | ✓
Fan-out search |  | ✓
Benchmark harness |  | ✓
Query planner |  | ✓
Tenant isolation |  | ✓
Resource limits |  | ✓
Property tests |  | ✓
Fuzzing |  | ✓
Benchmark datasets |  |  |  | ✓
Filter selectivity corpus |  |  |  | ✓
Recall@k |  |  |  | ✓
Latency modeling |  |  |  | ✓
Adaptive efSearch |  |  |  | ✓
Candidate budgeting |  |  |  | ✓
Query strategy selection |  |  |  | ✓
Recall-risk estimator |  |  |  | ✓
Experiment tracking |  |  |  | ✓
Model/config registry |  |  |  | ✓
Deterministic fallback |  |  |  | ✓
Vector schema |  |  | ✓
Filterable fields |  |  | ✓
Nested metadata |  |  | ✓
Vector storage |  |  | ✓
HNSW metadata |  |  | ✓
Build versions |  |  | ✓
Partitioning |  |  | ✓
Compaction state |  |  | ✓
Snapshots |  |  | ✓
Backup/restore |  |  | ✓
Encryption |  |  | ✓
Retention/deletion |  |  | ✓
Metadata indexes |  |  | ✓
Storage metrics |  |  | ✓
ANN search |  | ✓
Filtered ANN |  | ✓
Exact baseline |  | ✓
Distance metrics |  | ✓
Top-k |  | ✓
Boolean filters |  | ✓
Range filters |  | ✓
Set filters |  | ✓
Filter pushdown |  | ✓
Hybrid execution |  | ✓
Insert |  | ✓
Update |  | ✓
Delete |  | ✓
Rebuild | ✓ | ✓
Online compaction |  | ✓
Warm cache |  | ✓
Batch search |  | ✓
Parallel search |  | ✓
Memory budget |  | ✓
Crash-safe index |  | ✓
Index versioning |  | ✓
Authentication |  | ✓
Authorization |  | ✓
Rate limiting |  | ✓
Audit trail |  | ✓ |  | ✓
Correctness suite | ✓ | ✓
Concurrency suite | ✓ | ✓
Performance suite | ✓ | ✓
Chaos suite | ✓ | ✓
Admin API |  | ✓
Health/readiness |  | ✓
Metrics |  | ✓
Tracing |  | ✓
Containerization |  | ✓ |  | ✓
CI/CD |  | ✓
API docs |  | ✓
Operations runbook |  | ✓
Paper/benchmark report |  | ✓ |  | ✓
Multi-tenancy & Collections |  | ✓ | ✓
Collection lifecycle |  | ✓ | ✓
Schema evolution |  | ✓ | ✓
API pagination/cursors |  | ✓
Idempotent writes |  | ✓ | ✓
Request cancellation |  | ✓
Timeout budgets |  | ✓
Backpressure |  | ✓
Circuit breakers |  | ✓
Load shedding |  | ✓
Rate-limit analytics |  | ✓
API compatibility matrix |  | ✓ | ✓
Feature flags |  | ✓
Canary deployment |  | ✓
Blue/green deployment |  | ✓
SLO/SLI definitions |  | ✓
Alerting policy |  | ✓
Capacity planning |  | ✓ | ✓
Cost monitoring |  | ✓ | ✓
Synthetic monitoring |  | ✓
Data quality validation |  | ✓ | ✓
Embedding provenance |  | ✓ | ✓ | ✓
Embedding drift detection |  |  |  | ✓
Model version compatibility |  | ✓ | ✓ | ✓
Offline evaluation pipeline |  | ✓ |  | ✓
Online A/B evaluation |  | ✓ |  | ✓
Confidence/calibration dashboard |  |  |  | ✓
Adversarial vector testing |  | ✓ | ✓ | ✓
Poisoning/data-integrity checks |  | ✓ | ✓ | ✓
Supply-chain security |  | ✓
SBOM generation |  | ✓
Secrets rotation |  | ✓ | ✓
Key management |  | ✓ | ✓
Immutable audit logs |  | ✓ | ✓
Compliance export |  | ✓ | ✓
Geo/region routing |  | ✓
Disaster recovery region |  | ✓ | ✓
Restore point verification |  |  | ✓
Index corruption detector |  | ✓ | ✓
Online integrity checker |  | ✓ | ✓
Graph visualization/debugger | ✓ | ✓
Query replay |  | ✓
Deterministic seed control |  | ✓ |  | ✓
Golden dataset regression |  | ✓ | ✓ | ✓
Cross-version benchmark |  | ✓ | ✓ | ✓
Memory fragmentation tests |  | ✓ | ✓
Long-duration soak test |  | ✓ | ✓
Upgrade/downgrade test |  | ✓ | ✓
Migration dry-run |  | ✓ | ✓
User-facing error taxonomy |  | ✓
Search explainability panel | ✓ | ✓ |  | ✓
Usage quotas/billing hooks |  | ✓ | ✓

## Detailed Tasks
FINAL DETAILED IMPLEMENTATION MATRIX
Feature | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Frontend | Backend | Database | AI/ML
Search UI shell | Query input, filters, top-k, vector/search mode and result layout | P0 | MVP | Frontend Lead |  | 8 | Medium | All search controls work together | ✓
Vector query input | Text/vector query handling, validation and query-state management | P0 | MVP | Frontend | Search API | 8 | Medium | Valid queries reach API correctly | ✓
Metadata filters | Filter builder for equality/range/set/boolean conditions | P0 | Core | Frontend | Filter schema | 14 | High | Generated filters match backend syntax | ✓
Filter UX | Nested AND/OR groups, clear/reset, saved filters | P1 | Beta | Frontend | Metadata filters | 16 | High | Complex filters remain understandable | ✓
Result list | IDs, scores, metadata, distance/similarity and highlights | P0 | MVP | Frontend | Search API | 10 | Low | Results render consistently | ✓
Pagination/Top-K | Top-k control, cursor/offset semantics and result limits | P0 | MVP | Frontend | Result list | 8 | Medium | Requested k is respected | ✓
Debug mode | Show candidate count, filtering stage and search diagnostics | P1 | Debug | Frontend | Observability API | 10 | Medium | Diagnostics match server metrics | ✓
Large-result rendering | Virtualized lists and incremental rendering | P1 | Hardening | Frontend | Result list | 10 | Medium | UI remains responsive at large k | ✓
Input hardening | Escape/render metadata safely and prevent client-side injection | P0 | Security | Frontend | Result list | 8 | High | Untrusted metadata is safely rendered | ✓
Keyboard/navigation | Keyboard-first search, filters and results | P1 | Beta | Frontend | Search UI | 8 | Low | Core flow usable without pointer | ✓
E2E search tests | Queries, filters, empty results, errors and large k | P0 | Hardening | QA | All frontend flows | 18 | Medium | Critical flows pass CI | ✓
Client telemetry | Query IDs, latency, filter usage and error context | P1 | Beta | Frontend | Telemetry API | 8 | Medium | Events correlate with server request IDs | ✓
Search service | Define query, filter, retrieval and response service boundaries | P0 | Foundation | Backend Lead |  | 12 | High | Responsibilities are independently testable |  | ✓
Search API | Versioned endpoint for vector search + filters + top-k | P0 | MVP | Backend | Search service | 16 | High | Contract and validation tests pass |  | ✓
Filter DSL | Canonical representation and validation for filter expressions | P0 | Core | Backend | Search API | 20 | Critical | All supported operators parse deterministically |  | ✓
Query validation | Dimensions, NaN/Inf, empty vectors, k bounds and filter limits | P0 | Security | Backend | Filter DSL | 12 | High | Invalid input is rejected safely |  | ✓
HNSW build | Graph construction with configurable M/Mmax/efConstruction | P0 | Core | Search/Index | Vector store | 32 | Critical | Index builds reproducibly |  | ✓
HNSW search | Approximate nearest-neighbor traversal with efSearch | P0 | Core | Search/Index | HNSW build | 32 | Critical | Top-k search returns valid candidates |  | ✓
Filtered traversal | Apply metadata predicates during candidate exploration | P0 | Core | Search/Index | Filter DSL + HNSW search | 36 | Critical | Filtered results contain only valid records |  | ✓
Pre/post filtering modes | Support and benchmark filter-before/after candidate selection | P1 | Research | Search/Index | Filtered traversal | 20 | High | Modes are behaviorally correct |  | ✓
Adaptive efSearch | Adjust search breadth based on k, filter selectivity and target recall | P1 | Optimization | Backend | Filtered traversal | 24 | High | Bounded adaptive policy is deterministic |  | ✓
Deletion/tombstones | Logical deletion and graph-safe handling of removed vectors | P0 | Core | Backend | HNSW search | 24 | Critical | Deleted vectors never appear |  | ✓
Updates | Metadata/vector update semantics and re-index strategy | P0 | Core | Backend | Deletion | 26 | High | Updates become query-visible consistently |  | ✓
Compaction/rebuild | Background cleanup and full/partial rebuild | P1 | Scale | Backend | Updates | 30 | Critical | Compaction preserves correctness |  | ✓
Index snapshots | Persist/load graph, vectors, metadata and version information | P0 | MVP | Backend | HNSW build | 24 | Critical | Reloaded index matches source behavior |  | ✓
Crash recovery | Atomic writes, WAL/checkpoint or equivalent recovery | P0 | Production | Backend | Snapshots | 24 | Critical | Crash does not corrupt index |  | ✓
Read/write concurrency | Safe concurrent search, insert, update, delete and rebuild | P0 | Core | Backend | Index lifecycle | 36 | Critical | No races/corruption under stress |  | ✓
Locking strategy | Minimize contention with documented synchronization model | P1 | Optimization | Backend | Concurrency | 18 | High | Hot path contention measured |  | ✓
Sharding | Partition index by tenant, region or hash | P2 | Scale | Backend | Persistence | 32 | High | Queries route to correct shards |  | ✓
Replication | Replica strategy for availability and read scaling | P2 | Production | Backend | Sharding | 28 | Critical | Replica consistency model documented/tested |  | ✓
Fan-out search | Parallel search across shards and global top-k merge | P2 | Scale | Backend | Sharding | 28 | High | Global top-k is correct |  | ✓
Benchmark harness | Recall@k, latency, QPS, memory, build time and filter selectivity | P0 | Research | Performance | Search API | 24 | High | Benchmarks are reproducible |  | ✓
Query planner | Choose search strategy using filter selectivity and index statistics | P1 | Optimization | Backend | Benchmarks | 28 | High | Planner decisions are observable |  | ✓
Tenant isolation | Prevent cross-tenant vector/metadata access | P0 | Security | Backend | API auth | 20 | Critical | Isolation tests pass |  | ✓
Resource limits | Bound vector dimension, k, filter complexity, memory and CPU | P0 | Security | Backend | Query validation | 16 | High | Abusive requests are rejected/throttled |  | ✓
Property tests | Validate graph invariants, filters and ranking behavior | P0 | Hardening | QA | Core index | 24 | Critical | Property suite passes |  | ✓
Fuzzing | Fuzz vectors, filters, serialized indexes and API payloads | P0 | Security | Security/QA | Validation | 28 | Critical | No crashes/corruption found |  | ✓
Benchmark datasets | Curate public/synthetic datasets across dimensions and distributions | P0 | Research | ML/Research |  | 18 | Medium | Datasets are versioned and reproducible |  |  |  | ✓
Filter selectivity corpus | Generate/collect metadata distributions from 0.001% to 100% selectivity | P0 | Research | ML/Research | Datasets | 16 | High | All selectivity bands represented |  |  |  | ✓
Recall@k | Measure filtered and unfiltered recall against exact ground truth | P0 | Research | ML/Research | Datasets + backend | 24 | Critical | Recall curves generated |  |  |  | ✓
Latency modeling | Model p50/p95/p99 latency vs efSearch, k and selectivity | P0 | Research | ML/Research | Benchmarks | 20 | High | Latency model is reproducible |  |  |  | ✓
Adaptive efSearch | Learn/fit policy for efSearch under filter selectivity | P1 | Experimental | ML/Research | Latency modeling | 28 | High | Policy respects recall floor |  |  |  | ✓
Candidate budgeting | Predict required candidate budget from filter density | P1 | Experimental | ML/Research | Selectivity corpus | 24 | High | Budget reduces wasted work without recall loss |  |  |  | ✓
Query strategy selection | Classify query into pre-filter/post-filter/hybrid execution | P1 | Experimental | ML/Research | Query planner | 28 | High | Strategy improves benchmark envelope |  |  |  | ✓
Recall-risk estimator | Estimate whether a query is under-searching | P2 | Research | ML/Research | Evaluation | 22 | Medium | Risk score correlates with recall misses |  |  |  | ✓
Experiment tracking | Version datasets, code, parameters and results | P0 | Research | ML/Research | All experiments | 12 | Medium | Any benchmark is reproducible |  |  |  | ✓
Model/config registry | Promote/revert adaptive policies and benchmark configurations | P1 | Beta | ML/Research | Experiment tracking | 14 | Medium | Rollback works safely |  |  |  | ✓
Deterministic fallback | Disable ML and revert to fixed safe search parameters | P0 | Production | Backend/ML | Adaptive systems | 12 | Critical | System remains correct without ML |  |  |  | ✓
Vector schema | Define vector ID, dimension, metric, payload and version model | P0 | Foundation | DBA/Backend |  | 12 | High | Schema supports required lifecycle |  |  | ✓
Filterable fields | Index/selectivity strategy for categorical, numeric and boolean metadata | P0 | Core | DBA | Filter DSL | 18 | Critical | All supported predicates execute correctly |  |  | ✓
Nested metadata | Define nested/object field semantics and limitations | P1 | Beta | DBA | Filterable fields | 12 | High | Nested behavior is documented/tested |  |  | ✓
Vector storage | Efficient storage/retrieval of vector payloads | P0 | Core | DBA | Vector schema | 20 | High | Vectors round-trip without precision issues |  |  | ✓
HNSW metadata | M, efConstruction, efSearch, metric, graph version and build stats | P0 | Core | DBA | Vector schema | 12 | Medium | Index configuration is recoverable |  |  | ✓
Build versions | Track index generation, source snapshot and migration state | P0 | Production | DBA | HNSW metadata | 10 | High | Every index has provenance |  |  | ✓
Partitioning | Partition vectors/metadata by tenant or collection where needed | P1 | Scale | DBA | Vector storage | 20 | High | Partition queries remain correct |  |  | ✓
Compaction state | Track tombstones, compaction jobs and rebuild progress | P1 | Scale | DBA | Updates | 12 | Medium | Background jobs are observable |  |  | ✓
Snapshots | Atomic index/data snapshots with checksums | P0 | Production | DBA | Index persistence | 18 | Critical | Snapshots restore correctly |  |  | ✓
Backup/restore | Scheduled backups and tested recovery | P0 | Production | DBA | Snapshots | 14 | Critical | Restore drill succeeds |  |  | ✓
Encryption | Encryption in transit/at rest and secret management | P0 | Security | DBA | Infrastructure | 12 | Critical | Sensitive data protected |  |  | ✓
Retention/deletion | Delete vectors and metadata with verifiable purge semantics | P0 | Security | DBA | Lifecycle | 16 | High | Deleted data is not returned |  |  | ✓
Metadata indexes | B-tree/bitmap/hash/etc. indexes for hot filter predicates | P0 | Optimization | DBA | Filterable fields | 18 | High | Hot predicates meet latency targets |  |  | ✓
Storage metrics | Track disk, memory, index size, tombstones and growth | P1 | Production | DBA | All storage | 10 | Low | Capacity trends are visible |  |  | ✓
ANN search | Approximate nearest-neighbor search using HNSW | P0 | Core | Product | HNSW search | 30 | Critical | Correct top-k contract |  | ✓
Filtered ANN | ANN search constrained by metadata predicates | P0 | Core | Product | Filtered traversal | 36 | Critical | No invalid metadata results |  | ✓
Exact baseline | Brute-force/exact search for ground truth and small collections | P0 | Research | Backend | Vector storage | 18 | Medium | Exact results are reproducible |  | ✓
Distance metrics | Cosine, inner product and/or Euclidean as supported | P0 | MVP | Backend | Vector schema | 16 | High | Metric semantics are documented/tested |  | ✓
Top-k | Configurable k with hard limits | P0 | MVP | Backend | Search API | 8 | Medium | Exactly valid k behavior |  | ✓
Boolean filters | AND/OR/NOT expression support | P0 | Core | Backend | Filter DSL | 20 | Critical | Boolean semantics are deterministic |  | ✓
Range filters | Numeric/date range predicates | P0 | Core | Backend | Filter DSL | 14 | High | Inclusive/exclusive semantics documented |  | ✓
Set filters | IN/NOT IN and membership predicates | P0 | Core | Backend | Filter DSL | 12 | Medium | Set semantics correct |  | ✓
Filter pushdown | Use metadata conditions during ANN traversal when safe | P1 | Optimization | Backend | Filtered traversal | 24 | Critical | No recall violations |  | ✓
Hybrid execution | Combine graph traversal and metadata candidate filtering | P1 | Optimization | Backend | Filter pushdown | 28 | High | Strategy is benchmarked |  | ✓
Insert | Add vectors and metadata | P0 | MVP | Backend | Vector storage | 18 | High | Inserted data becomes queryable |  | ✓
Update | Update vector and/or metadata safely | P0 | Core | Backend | Insert + delete | 20 | High | Old record is not returned |  | ✓
Delete | Logical/physical deletion semantics | P0 | Core | Backend | Insert | 18 | Critical | Deleted records never return |  | ✓
Rebuild | Rebuild index from canonical storage | P0 | Production | Backend | Snapshots | 30 | Critical | Rebuilt index matches benchmark | ✓ | ✓
Online compaction | Background tombstone cleanup | P1 | Scale | Backend | Delete + rebuild | 24 | High | Compaction does not block reads |  | ✓
Warm cache | Cache hot query/index metadata where beneficial | P1 | Optimization | Backend | Search | 14 | Medium | Cache improves repeat query latency |  | ✓
Batch search | Efficient multi-query/batch API | P1 | Scale | Backend | Search API | 18 | High | Batch results equal individual semantics |  | ✓
Parallel search | Parallel graph traversal across workers/shards | P2 | Scale | Backend | Sharding | 22 | High | Parallel merge is correct |  | ✓
Memory budget | Bound graph/vector/filter memory consumption | P0 | Hardening | Backend | All index components | 18 | Critical | Configured memory budget is enforced |  | ✓
Crash-safe index | Recover from interrupted build/write | P0 | Production | Backend | Persistence | 22 | Critical | No corrupted index loads |  | ✓
Index versioning | Load old versions or migrate explicitly | P0 | Production | Backend | Snapshots | 18 | High | Compatibility rules are enforced |  | ✓
Authentication | Secure API authentication | P0 | Security | Backend | API | 14 | Critical | Invalid credentials rejected |  | ✓
Authorization | Collection/tenant-level access control | P0 | Security | Backend | Authentication | 16 | Critical | Cross-tenant reads blocked |  | ✓
Rate limiting | Query and write quotas | P0 | Security | Backend | Authentication | 12 | High | Abusive clients are throttled |  | ✓
Audit trail | Record privileged/index lifecycle operations | P1 | Security | Backend | Authorization | 10 | Medium | Audit events are searchable |  | ✓ |  | ✓
Correctness suite | Ranking, filtering, lifecycle and persistence tests | P0 | Hardening | QA | All core features | 30 | Critical | CI blocks regressions | ✓ | ✓
Concurrency suite | Read/write/rebuild concurrency and race testing | P0 | Hardening | QA | Concurrency | 28 | Critical | No data races/corruption | ✓ | ✓
Performance suite | Benchmark recall, p50/p95/p99, QPS, memory and build time | P0 | Research | QA | Benchmark harness | 26 | High | Results are reproducible | ✓ | ✓
Chaos suite | Disk failure, process kill, latency and resource pressure | P1 | Production | QA | Recovery | 24 | Critical | System recovers within targets | ✓ | ✓
Admin API | Index stats, rebuild, compaction, health and job controls | P1 | Beta | Backend | Observability | 20 | High | Operators can safely manage index |  | ✓
Health/readiness | Liveness, readiness and index health endpoints | P0 | Production | Backend | Observability | 10 | Medium | Orchestrator can detect unhealthy instances |  | ✓
Metrics | Recall proxy, latency, QPS, filter selectivity and resource metrics | P0 | Production | Backend | Observability | 16 | Medium | Critical metrics are exposed |  | ✓
Tracing | End-to-end query tracing through planner/index/storage | P1 | Production | Backend | Metrics | 16 | Medium | Slow queries are diagnosable |  | ✓
Containerization | Reproducible service/index runtime | P0 | Production | DevOps | Build | 14 | Medium | Clean deployment succeeds |  | ✓ |  | ✓
CI/CD | Tests, fuzzing, benchmarks and security gates | P0 | Production | DevOps | Testing | 20 | High | Required gates run on changes |  | ✓
API docs | Search/filter/index lifecycle API specification | P0 | Beta | Tech Lead | API | 14 | Low | Examples cover supported behavior |  | ✓
Operations runbook | Rebuild, restore, compaction, incidents and capacity procedures | P0 | Production | DevOps | Operations | 16 | High | Operators can execute drills |  | ✓
Paper/benchmark report | Document algorithm, filtering strategy, baselines and limitations | P2 | Research | Research Lead | Evaluation | 24 | Medium | Results reproducible by another team |  | ✓ |  | ✓
Multi-tenancy & Collections | P0 | Core | Backend Lead | Auth + schema | 18 | Critical | Collections are isolated and addressable | 0 cross-collection leaks |  | ✓ | ✓
Collection lifecycle | P1 | Core | Backend | Collections | 14 | High | Create/update/delete collection safely | Lifecycle tests pass |  | ✓ | ✓
Schema evolution | P1 | Production | Backend/DBA | Database schema | 18 | High | Backward-compatible migrations are tested | Migration success 100% |  | ✓ | ✓
API pagination/cursors | P1 | Core | Backend | Search API | 12 | Medium | Stable cursor semantics across changing data | Cursor tests pass |  | ✓
Idempotent writes | P0 | Reliability | Backend | Insert/update APIs | 12 | High | Retries do not duplicate data | Duplicate-write rate 0 |  | ✓ | ✓
Request cancellation | P1 | Performance | Backend | Search API | 10 | Medium | Cancelled queries stop consuming resources | Cancellation effectiveness |  | ✓
Timeout budgets | P0 | Reliability | Backend | Search API | 10 | High | Per-stage and end-to-end deadlines enforced | Timeout violations tracked |  | ✓
Backpressure | P0 | Scale | Backend | Concurrency | 18 | Critical | Overload is contained without cascading failure | Queue saturation controlled |  | ✓
Circuit breakers | P1 | Production | Backend | Dependencies | 14 | High | Dependency failures do not cascade | Recovery tests |  | ✓
Load shedding | P1 | Scale | Backend | Backpressure | 14 | High | System degrades predictably under overload | Availability target |  | ✓
Rate-limit analytics | P1 | Production | Backend | Rate limiting | 10 | Medium | Operators can inspect abuse patterns | Alerts actionable |  | ✓
API compatibility matrix | P1 | Production | Backend | API versions | 12 | Medium | Supported clients/index versions documented | Compatibility tests |  | ✓ | ✓
Feature flags | P1 | Production | Backend | Deployment | 12 | Medium | Risky features can be enabled/disabled safely | Rollback <5 min |  | ✓
Canary deployment | P1 | Production | DevOps | CI/CD | 16 | High | New version can receive controlled traffic | Canary rollback tested |  | ✓
Blue/green deployment | P2 | Production | DevOps | Deployment | 16 | High | Traffic can switch between versions | Switchback tested |  | ✓
SLO/SLI definitions | P0 | Production | SRE | Observability | 12 | Medium | Latency/availability/error SLOs documented | SLO dashboard |  | ✓
Alerting policy | P0 | Production | SRE | Metrics | 14 | High | Critical failures page with actionable context | Alert test pass |  | ✓
Capacity planning | P1 | Scale | SRE/DBA | Storage metrics | 18 | Medium | Growth thresholds and scaling actions documented | Forecast horizon |  | ✓ | ✓
Cost monitoring | P1 | Production | SRE/DBA | Capacity | 12 | Medium | Compute/storage/network costs attributable | Cost per query tracked |  | ✓ | ✓
Synthetic monitoring | P1 | Production | QA/SRE | Health endpoints | 12 | Low | Scheduled real-user-like queries detect regressions | Synthetic pass rate |  | ✓
Data quality validation | P0 | Core | Data/Backend | Vector storage | 18 | Critical | Dimension/type/range and metadata quality checked | Invalid records blocked |  | ✓ | ✓
Embedding provenance | P0 | Research | ML/Data | Vector schema | 16 | High | Model/version/source are tracked for every vector set | Provenance coverage 100% |  | ✓ | ✓ | ✓
Embedding drift detection | P1 | AI/ML | ML | Provenance | 22 | High | Distribution changes are detected and reported | Drift alerts |  |  |  | ✓
Model version compatibility | P0 | AI/ML | ML/Backend | Embedding provenance | 18 | Critical | Queries and stored vectors use compatible model versions | Compatibility failures blocked |  | ✓ | ✓ | ✓
Offline evaluation pipeline | P0 | AI/ML | ML/Research | Datasets | 22 | High | One command reproduces recall/latency evaluation | Reproduction pass |  | ✓ |  | ✓
Online A/B evaluation | P1 | AI/ML | ML/Product | Feature flags | 24 | High | Search policies can be compared safely | Statistical report |  | ✓ |  | ✓
Confidence/calibration dashboard | P2 | AI/ML | ML | Risk estimator | 16 | Medium | Predicted risk is compared with observed outcomes | Calibration error tracked |  |  |  | ✓
Adversarial vector testing | P0 | Security | Security/ML | Fuzzing | 20 | Critical | Malformed/adversarial vectors cannot crash or poison index | 0 critical findings |  | ✓ | ✓ | ✓
Poisoning/data-integrity checks | P1 | Security | Security/Data | Data validation | 20 | Critical | Suspicious bulk changes are detected | Integrity alerts |  | ✓ | ✓ | ✓
Supply-chain security | P0 | Security | DevSecOps | CI/CD | 16 | Critical | Dependencies/images are scanned and pinned | 0 critical unreviewed CVEs |  | ✓
SBOM generation | P1 | Security | DevSecOps | Build pipeline | 10 | Medium | Release artifacts have SBOMs | 100% releases |  | ✓
Secrets rotation | P0 | Security | DevOps | Secrets manager | 12 | Critical | Secrets can rotate without downtime | Rotation drill |  | ✓ | ✓
Key management | P0 | Security | DevOps | Encryption | 14 | Critical | Encryption keys are managed separately and rotated | Key rotation test |  | ✓ | ✓
Immutable audit logs | P1 | Security | Security/DBA | Audit trail | 14 | High | Privileged events resist alteration | Audit integrity check |  | ✓ | ✓
Compliance export | P2 | Production | Backend/DBA | Audit + retention | 14 | Medium | Required records can be exported | Export correctness |  | ✓ | ✓
Geo/region routing | P2 | Scale | Backend | Sharding | 20 | High | Queries route to intended region | Routing correctness |  | ✓
Disaster recovery region | P2 | Production | SRE/DBA | Backups | 24 | Critical | Service can restore in alternate region | DR drill |  | ✓ | ✓
Restore point verification | P1 | Production | DBA | Snapshots | 12 | High | Backup integrity is automatically verified | Verification pass |  |  | ✓
Index corruption detector | P0 | Reliability | Index/QA | HNSW invariants | 20 | Critical | Corrupt graph/index states are detected before serving | Detection tests |  | ✓ | ✓
Online integrity checker | P1 | Reliability | Index | Corruption detector | 16 | High | Background checks do not block reads | Integrity coverage |  | ✓ | ✓
Graph visualization/debugger | P2 | Developer Tool | Frontend/Index | Index stats | 20 | Medium | Developers can inspect graph/neighbor structure | Debug workflow pass | ✓ | ✓
Query replay | P1 | Developer Tool | Backend/QA | Tracing | 18 | High | Production-safe queries can be replayed offline | Replay parity |  | ✓
Deterministic seed control | P0 | Research | Index/ML | Benchmark harness | 10 | Medium | Benchmarks/builds can be reproduced | Repeatability pass |  | ✓ |  | ✓
Golden dataset regression | P0 | Testing | QA | Exact baseline | 16 | High | Known queries detect ranking/filter regressions | 0 golden regressions |  | ✓ | ✓ | ✓
Cross-version benchmark | P1 | Testing | Performance | Versioning | 18 | Medium | New releases compare against prior baseline | Regression report |  | ✓ | ✓ | ✓
Memory fragmentation tests | P1 | Performance | Performance/DBA | Memory budget | 18 | High | Long-running process remains within memory envelope | Soak memory bound |  | ✓ | ✓
Long-duration soak test | P0 | Reliability | QA/SRE | All core systems | 24 | Critical | System remains stable for extended workload | Soak pass |  | ✓ | ✓
Upgrade/downgrade test | P0 | Production | Release | Versioning | 18 | Critical | Supported upgrades and rollback paths work | Upgrade matrix pass |  | ✓ | ✓
Migration dry-run | P1 | Production | DBA | Schema evolution | 12 | High | Migrations can be validated before production | Dry-run pass |  | ✓ | ✓
User-facing error taxonomy | P1 | Frontend | Frontend | API errors | 10 | Low | Errors are actionable and consistent | Error coverage |  | ✓
Search explainability panel | P2 | Frontend/AI | Frontend/ML | Debug metadata | 16 | Medium | Users can inspect why a result/query strategy was used | Explainability coverage | ✓ | ✓ |  | ✓
Usage quotas/billing hooks | P2 | Product | Backend/DBA | Rate limiting | 16 | Medium | Usage can be measured per tenant | Metering accuracy |  | ✓ | ✓

## Frontend
FRONTEND — ALL ASSIGNED WORK
Feature | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Frontend | Backend | Database | AI/ML
Search UI shell | Query input, filters, top-k, vector/search mode and result layout | P0 | MVP | Frontend Lead |  | 8 | Medium | All search controls work together | ✓
Vector query input | Text/vector query handling, validation and query-state management | P0 | MVP | Frontend | Search API | 8 | Medium | Valid queries reach API correctly | ✓
Metadata filters | Filter builder for equality/range/set/boolean conditions | P0 | Core | Frontend | Filter schema | 14 | High | Generated filters match backend syntax | ✓
Filter UX | Nested AND/OR groups, clear/reset, saved filters | P1 | Beta | Frontend | Metadata filters | 16 | High | Complex filters remain understandable | ✓
Result list | IDs, scores, metadata, distance/similarity and highlights | P0 | MVP | Frontend | Search API | 10 | Low | Results render consistently | ✓
Pagination/Top-K | Top-k control, cursor/offset semantics and result limits | P0 | MVP | Frontend | Result list | 8 | Medium | Requested k is respected | ✓
Debug mode | Show candidate count, filtering stage and search diagnostics | P1 | Debug | Frontend | Observability API | 10 | Medium | Diagnostics match server metrics | ✓
Large-result rendering | Virtualized lists and incremental rendering | P1 | Hardening | Frontend | Result list | 10 | Medium | UI remains responsive at large k | ✓
Input hardening | Escape/render metadata safely and prevent client-side injection | P0 | Security | Frontend | Result list | 8 | High | Untrusted metadata is safely rendered | ✓
Keyboard/navigation | Keyboard-first search, filters and results | P1 | Beta | Frontend | Search UI | 8 | Low | Core flow usable without pointer | ✓
E2E search tests | Queries, filters, empty results, errors and large k | P0 | Hardening | QA | All frontend flows | 18 | Medium | Critical flows pass CI | ✓
Client telemetry | Query IDs, latency, filter usage and error context | P1 | Beta | Frontend | Telemetry API | 8 | Medium | Events correlate with server request IDs | ✓
Rebuild | Rebuild index from canonical storage | P0 | Production | Backend | Snapshots | 30 | Critical | Rebuilt index matches benchmark | ✓ | ✓
Correctness suite | Ranking, filtering, lifecycle and persistence tests | P0 | Hardening | QA | All core features | 30 | Critical | CI blocks regressions | ✓ | ✓
Concurrency suite | Read/write/rebuild concurrency and race testing | P0 | Hardening | QA | Concurrency | 28 | Critical | No data races/corruption | ✓ | ✓
Performance suite | Benchmark recall, p50/p95/p99, QPS, memory and build time | P0 | Research | QA | Benchmark harness | 26 | High | Results are reproducible | ✓ | ✓
Chaos suite | Disk failure, process kill, latency and resource pressure | P1 | Production | QA | Recovery | 24 | Critical | System recovers within targets | ✓ | ✓
Graph visualization/debugger | P2 | Developer Tool | Frontend/Index | Index stats | 20 | Medium | Developers can inspect graph/neighbor structure | Debug workflow pass | ✓ | ✓
Search explainability panel | P2 | Frontend/AI | Frontend/ML | Debug metadata | 16 | Medium | Users can inspect why a result/query strategy was used | Explainability coverage | ✓ | ✓ |  | ✓

## Backend
BACKEND — ALL ASSIGNED WORK
Feature | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Frontend | Backend | Database | AI/ML
Search service | Define query, filter, retrieval and response service boundaries | P0 | Foundation | Backend Lead |  | 12 | High | Responsibilities are independently testable |  | ✓
Search API | Versioned endpoint for vector search + filters + top-k | P0 | MVP | Backend | Search service | 16 | High | Contract and validation tests pass |  | ✓
Filter DSL | Canonical representation and validation for filter expressions | P0 | Core | Backend | Search API | 20 | Critical | All supported operators parse deterministically |  | ✓
Query validation | Dimensions, NaN/Inf, empty vectors, k bounds and filter limits | P0 | Security | Backend | Filter DSL | 12 | High | Invalid input is rejected safely |  | ✓
HNSW build | Graph construction with configurable M/Mmax/efConstruction | P0 | Core | Search/Index | Vector store | 32 | Critical | Index builds reproducibly |  | ✓
HNSW search | Approximate nearest-neighbor traversal with efSearch | P0 | Core | Search/Index | HNSW build | 32 | Critical | Top-k search returns valid candidates |  | ✓
Filtered traversal | Apply metadata predicates during candidate exploration | P0 | Core | Search/Index | Filter DSL + HNSW search | 36 | Critical | Filtered results contain only valid records |  | ✓
Pre/post filtering modes | Support and benchmark filter-before/after candidate selection | P1 | Research | Search/Index | Filtered traversal | 20 | High | Modes are behaviorally correct |  | ✓
Adaptive efSearch | Adjust search breadth based on k, filter selectivity and target recall | P1 | Optimization | Backend | Filtered traversal | 24 | High | Bounded adaptive policy is deterministic |  | ✓
Deletion/tombstones | Logical deletion and graph-safe handling of removed vectors | P0 | Core | Backend | HNSW search | 24 | Critical | Deleted vectors never appear |  | ✓
Updates | Metadata/vector update semantics and re-index strategy | P0 | Core | Backend | Deletion | 26 | High | Updates become query-visible consistently |  | ✓
Compaction/rebuild | Background cleanup and full/partial rebuild | P1 | Scale | Backend | Updates | 30 | Critical | Compaction preserves correctness |  | ✓
Index snapshots | Persist/load graph, vectors, metadata and version information | P0 | MVP | Backend | HNSW build | 24 | Critical | Reloaded index matches source behavior |  | ✓
Crash recovery | Atomic writes, WAL/checkpoint or equivalent recovery | P0 | Production | Backend | Snapshots | 24 | Critical | Crash does not corrupt index |  | ✓
Read/write concurrency | Safe concurrent search, insert, update, delete and rebuild | P0 | Core | Backend | Index lifecycle | 36 | Critical | No races/corruption under stress |  | ✓
Locking strategy | Minimize contention with documented synchronization model | P1 | Optimization | Backend | Concurrency | 18 | High | Hot path contention measured |  | ✓
Sharding | Partition index by tenant, region or hash | P2 | Scale | Backend | Persistence | 32 | High | Queries route to correct shards |  | ✓
Replication | Replica strategy for availability and read scaling | P2 | Production | Backend | Sharding | 28 | Critical | Replica consistency model documented/tested |  | ✓
Fan-out search | Parallel search across shards and global top-k merge | P2 | Scale | Backend | Sharding | 28 | High | Global top-k is correct |  | ✓
Benchmark harness | Recall@k, latency, QPS, memory, build time and filter selectivity | P0 | Research | Performance | Search API | 24 | High | Benchmarks are reproducible |  | ✓
Query planner | Choose search strategy using filter selectivity and index statistics | P1 | Optimization | Backend | Benchmarks | 28 | High | Planner decisions are observable |  | ✓
Tenant isolation | Prevent cross-tenant vector/metadata access | P0 | Security | Backend | API auth | 20 | Critical | Isolation tests pass |  | ✓
Resource limits | Bound vector dimension, k, filter complexity, memory and CPU | P0 | Security | Backend | Query validation | 16 | High | Abusive requests are rejected/throttled |  | ✓
Property tests | Validate graph invariants, filters and ranking behavior | P0 | Hardening | QA | Core index | 24 | Critical | Property suite passes |  | ✓
Fuzzing | Fuzz vectors, filters, serialized indexes and API payloads | P0 | Security | Security/QA | Validation | 28 | Critical | No crashes/corruption found |  | ✓
ANN search | Approximate nearest-neighbor search using HNSW | P0 | Core | Product | HNSW search | 30 | Critical | Correct top-k contract |  | ✓
Filtered ANN | ANN search constrained by metadata predicates | P0 | Core | Product | Filtered traversal | 36 | Critical | No invalid metadata results |  | ✓
Exact baseline | Brute-force/exact search for ground truth and small collections | P0 | Research | Backend | Vector storage | 18 | Medium | Exact results are reproducible |  | ✓
Distance metrics | Cosine, inner product and/or Euclidean as supported | P0 | MVP | Backend | Vector schema | 16 | High | Metric semantics are documented/tested |  | ✓
Top-k | Configurable k with hard limits | P0 | MVP | Backend | Search API | 8 | Medium | Exactly valid k behavior |  | ✓
Boolean filters | AND/OR/NOT expression support | P0 | Core | Backend | Filter DSL | 20 | Critical | Boolean semantics are deterministic |  | ✓
Range filters | Numeric/date range predicates | P0 | Core | Backend | Filter DSL | 14 | High | Inclusive/exclusive semantics documented |  | ✓
Set filters | IN/NOT IN and membership predicates | P0 | Core | Backend | Filter DSL | 12 | Medium | Set semantics correct |  | ✓
Filter pushdown | Use metadata conditions during ANN traversal when safe | P1 | Optimization | Backend | Filtered traversal | 24 | Critical | No recall violations |  | ✓
Hybrid execution | Combine graph traversal and metadata candidate filtering | P1 | Optimization | Backend | Filter pushdown | 28 | High | Strategy is benchmarked |  | ✓
Insert | Add vectors and metadata | P0 | MVP | Backend | Vector storage | 18 | High | Inserted data becomes queryable |  | ✓
Update | Update vector and/or metadata safely | P0 | Core | Backend | Insert + delete | 20 | High | Old record is not returned |  | ✓
Delete | Logical/physical deletion semantics | P0 | Core | Backend | Insert | 18 | Critical | Deleted records never return |  | ✓
Rebuild | Rebuild index from canonical storage | P0 | Production | Backend | Snapshots | 30 | Critical | Rebuilt index matches benchmark | ✓ | ✓
Online compaction | Background tombstone cleanup | P1 | Scale | Backend | Delete + rebuild | 24 | High | Compaction does not block reads |  | ✓
Warm cache | Cache hot query/index metadata where beneficial | P1 | Optimization | Backend | Search | 14 | Medium | Cache improves repeat query latency |  | ✓
Batch search | Efficient multi-query/batch API | P1 | Scale | Backend | Search API | 18 | High | Batch results equal individual semantics |  | ✓
Parallel search | Parallel graph traversal across workers/shards | P2 | Scale | Backend | Sharding | 22 | High | Parallel merge is correct |  | ✓
Memory budget | Bound graph/vector/filter memory consumption | P0 | Hardening | Backend | All index components | 18 | Critical | Configured memory budget is enforced |  | ✓
Crash-safe index | Recover from interrupted build/write | P0 | Production | Backend | Persistence | 22 | Critical | No corrupted index loads |  | ✓
Index versioning | Load old versions or migrate explicitly | P0 | Production | Backend | Snapshots | 18 | High | Compatibility rules are enforced |  | ✓
Authentication | Secure API authentication | P0 | Security | Backend | API | 14 | Critical | Invalid credentials rejected |  | ✓
Authorization | Collection/tenant-level access control | P0 | Security | Backend | Authentication | 16 | Critical | Cross-tenant reads blocked |  | ✓
Rate limiting | Query and write quotas | P0 | Security | Backend | Authentication | 12 | High | Abusive clients are throttled |  | ✓
Audit trail | Record privileged/index lifecycle operations | P1 | Security | Backend | Authorization | 10 | Medium | Audit events are searchable |  | ✓ |  | ✓
Correctness suite | Ranking, filtering, lifecycle and persistence tests | P0 | Hardening | QA | All core features | 30 | Critical | CI blocks regressions | ✓ | ✓
Concurrency suite | Read/write/rebuild concurrency and race testing | P0 | Hardening | QA | Concurrency | 28 | Critical | No data races/corruption | ✓ | ✓
Performance suite | Benchmark recall, p50/p95/p99, QPS, memory and build time | P0 | Research | QA | Benchmark harness | 26 | High | Results are reproducible | ✓ | ✓
Chaos suite | Disk failure, process kill, latency and resource pressure | P1 | Production | QA | Recovery | 24 | Critical | System recovers within targets | ✓ | ✓
Admin API | Index stats, rebuild, compaction, health and job controls | P1 | Beta | Backend | Observability | 20 | High | Operators can safely manage index |  | ✓
Health/readiness | Liveness, readiness and index health endpoints | P0 | Production | Backend | Observability | 10 | Medium | Orchestrator can detect unhealthy instances |  | ✓
Metrics | Recall proxy, latency, QPS, filter selectivity and resource metrics | P0 | Production | Backend | Observability | 16 | Medium | Critical metrics are exposed |  | ✓
Tracing | End-to-end query tracing through planner/index/storage | P1 | Production | Backend | Metrics | 16 | Medium | Slow queries are diagnosable |  | ✓
Containerization | Reproducible service/index runtime | P0 | Production | DevOps | Build | 14 | Medium | Clean deployment succeeds |  | ✓ |  | ✓
CI/CD | Tests, fuzzing, benchmarks and security gates | P0 | Production | DevOps | Testing | 20 | High | Required gates run on changes |  | ✓
API docs | Search/filter/index lifecycle API specification | P0 | Beta | Tech Lead | API | 14 | Low | Examples cover supported behavior |  | ✓
Operations runbook | Rebuild, restore, compaction, incidents and capacity procedures | P0 | Production | DevOps | Operations | 16 | High | Operators can execute drills |  | ✓
Paper/benchmark report | Document algorithm, filtering strategy, baselines and limitations | P2 | Research | Research Lead | Evaluation | 24 | Medium | Results reproducible by another team |  | ✓ |  | ✓
Multi-tenancy & Collections | P0 | Core | Backend Lead | Auth + schema | 18 | Critical | Collections are isolated and addressable | 0 cross-collection leaks |  | ✓ | ✓
Collection lifecycle | P1 | Core | Backend | Collections | 14 | High | Create/update/delete collection safely | Lifecycle tests pass |  | ✓ | ✓
Schema evolution | P1 | Production | Backend/DBA | Database schema | 18 | High | Backward-compatible migrations are tested | Migration success 100% |  | ✓ | ✓
API pagination/cursors | P1 | Core | Backend | Search API | 12 | Medium | Stable cursor semantics across changing data | Cursor tests pass |  | ✓
Idempotent writes | P0 | Reliability | Backend | Insert/update APIs | 12 | High | Retries do not duplicate data | Duplicate-write rate 0 |  | ✓ | ✓
Request cancellation | P1 | Performance | Backend | Search API | 10 | Medium | Cancelled queries stop consuming resources | Cancellation effectiveness |  | ✓
Timeout budgets | P0 | Reliability | Backend | Search API | 10 | High | Per-stage and end-to-end deadlines enforced | Timeout violations tracked |  | ✓
Backpressure | P0 | Scale | Backend | Concurrency | 18 | Critical | Overload is contained without cascading failure | Queue saturation controlled |  | ✓
Circuit breakers | P1 | Production | Backend | Dependencies | 14 | High | Dependency failures do not cascade | Recovery tests |  | ✓
Load shedding | P1 | Scale | Backend | Backpressure | 14 | High | System degrades predictably under overload | Availability target |  | ✓
Rate-limit analytics | P1 | Production | Backend | Rate limiting | 10 | Medium | Operators can inspect abuse patterns | Alerts actionable |  | ✓
API compatibility matrix | P1 | Production | Backend | API versions | 12 | Medium | Supported clients/index versions documented | Compatibility tests |  | ✓ | ✓
Feature flags | P1 | Production | Backend | Deployment | 12 | Medium | Risky features can be enabled/disabled safely | Rollback <5 min |  | ✓
Canary deployment | P1 | Production | DevOps | CI/CD | 16 | High | New version can receive controlled traffic | Canary rollback tested |  | ✓
Blue/green deployment | P2 | Production | DevOps | Deployment | 16 | High | Traffic can switch between versions | Switchback tested |  | ✓
SLO/SLI definitions | P0 | Production | SRE | Observability | 12 | Medium | Latency/availability/error SLOs documented | SLO dashboard |  | ✓
Alerting policy | P0 | Production | SRE | Metrics | 14 | High | Critical failures page with actionable context | Alert test pass |  | ✓
Capacity planning | P1 | Scale | SRE/DBA | Storage metrics | 18 | Medium | Growth thresholds and scaling actions documented | Forecast horizon |  | ✓ | ✓
Cost monitoring | P1 | Production | SRE/DBA | Capacity | 12 | Medium | Compute/storage/network costs attributable | Cost per query tracked |  | ✓ | ✓
Synthetic monitoring | P1 | Production | QA/SRE | Health endpoints | 12 | Low | Scheduled real-user-like queries detect regressions | Synthetic pass rate |  | ✓
Data quality validation | P0 | Core | Data/Backend | Vector storage | 18 | Critical | Dimension/type/range and metadata quality checked | Invalid records blocked |  | ✓ | ✓
Embedding provenance | P0 | Research | ML/Data | Vector schema | 16 | High | Model/version/source are tracked for every vector set | Provenance coverage 100% |  | ✓ | ✓ | ✓
Model version compatibility | P0 | AI/ML | ML/Backend | Embedding provenance | 18 | Critical | Queries and stored vectors use compatible model versions | Compatibility failures blocked |  | ✓ | ✓ | ✓
Offline evaluation pipeline | P0 | AI/ML | ML/Research | Datasets | 22 | High | One command reproduces recall/latency evaluation | Reproduction pass |  | ✓ |  | ✓
Online A/B evaluation | P1 | AI/ML | ML/Product | Feature flags | 24 | High | Search policies can be compared safely | Statistical report |  | ✓ |  | ✓
Adversarial vector testing | P0 | Security | Security/ML | Fuzzing | 20 | Critical | Malformed/adversarial vectors cannot crash or poison index | 0 critical findings |  | ✓ | ✓ | ✓
Poisoning/data-integrity checks | P1 | Security | Security/Data | Data validation | 20 | Critical | Suspicious bulk changes are detected | Integrity alerts |  | ✓ | ✓ | ✓
Supply-chain security | P0 | Security | DevSecOps | CI/CD | 16 | Critical | Dependencies/images are scanned and pinned | 0 critical unreviewed CVEs |  | ✓
SBOM generation | P1 | Security | DevSecOps | Build pipeline | 10 | Medium | Release artifacts have SBOMs | 100% releases |  | ✓
Secrets rotation | P0 | Security | DevOps | Secrets manager | 12 | Critical | Secrets can rotate without downtime | Rotation drill |  | ✓ | ✓
Key management | P0 | Security | DevOps | Encryption | 14 | Critical | Encryption keys are managed separately and rotated | Key rotation test |  | ✓ | ✓
Immutable audit logs | P1 | Security | Security/DBA | Audit trail | 14 | High | Privileged events resist alteration | Audit integrity check |  | ✓ | ✓
Compliance export | P2 | Production | Backend/DBA | Audit + retention | 14 | Medium | Required records can be exported | Export correctness |  | ✓ | ✓
Geo/region routing | P2 | Scale | Backend | Sharding | 20 | High | Queries route to intended region | Routing correctness |  | ✓
Disaster recovery region | P2 | Production | SRE/DBA | Backups | 24 | Critical | Service can restore in alternate region | DR drill |  | ✓ | ✓
Index corruption detector | P0 | Reliability | Index/QA | HNSW invariants | 20 | Critical | Corrupt graph/index states are detected before serving | Detection tests |  | ✓ | ✓
Online integrity checker | P1 | Reliability | Index | Corruption detector | 16 | High | Background checks do not block reads | Integrity coverage |  | ✓ | ✓
Graph visualization/debugger | P2 | Developer Tool | Frontend/Index | Index stats | 20 | Medium | Developers can inspect graph/neighbor structure | Debug workflow pass | ✓ | ✓
Query replay | P1 | Developer Tool | Backend/QA | Tracing | 18 | High | Production-safe queries can be replayed offline | Replay parity |  | ✓
Deterministic seed control | P0 | Research | Index/ML | Benchmark harness | 10 | Medium | Benchmarks/builds can be reproduced | Repeatability pass |  | ✓ |  | ✓
Golden dataset regression | P0 | Testing | QA | Exact baseline | 16 | High | Known queries detect ranking/filter regressions | 0 golden regressions |  | ✓ | ✓ | ✓
Cross-version benchmark | P1 | Testing | Performance | Versioning | 18 | Medium | New releases compare against prior baseline | Regression report |  | ✓ | ✓ | ✓
Memory fragmentation tests | P1 | Performance | Performance/DBA | Memory budget | 18 | High | Long-running process remains within memory envelope | Soak memory bound |  | ✓ | ✓
Long-duration soak test | P0 | Reliability | QA/SRE | All core systems | 24 | Critical | System remains stable for extended workload | Soak pass |  | ✓ | ✓
Upgrade/downgrade test | P0 | Production | Release | Versioning | 18 | Critical | Supported upgrades and rollback paths work | Upgrade matrix pass |  | ✓ | ✓
Migration dry-run | P1 | Production | DBA | Schema evolution | 12 | High | Migrations can be validated before production | Dry-run pass |  | ✓ | ✓
User-facing error taxonomy | P1 | Frontend | Frontend | API errors | 10 | Low | Errors are actionable and consistent | Error coverage |  | ✓
Search explainability panel | P2 | Frontend/AI | Frontend/ML | Debug metadata | 16 | Medium | Users can inspect why a result/query strategy was used | Explainability coverage | ✓ | ✓ |  | ✓
Usage quotas/billing hooks | P2 | Product | Backend/DBA | Rate limiting | 16 | Medium | Usage can be measured per tenant | Metering accuracy |  | ✓ | ✓

## Database
DATABASE — ALL ASSIGNED WORK
Feature | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Frontend | Backend | Database | AI/ML
Vector schema | Define vector ID, dimension, metric, payload and version model | P0 | Foundation | DBA/Backend |  | 12 | High | Schema supports required lifecycle |  |  | ✓
Filterable fields | Index/selectivity strategy for categorical, numeric and boolean metadata | P0 | Core | DBA | Filter DSL | 18 | Critical | All supported predicates execute correctly |  |  | ✓
Nested metadata | Define nested/object field semantics and limitations | P1 | Beta | DBA | Filterable fields | 12 | High | Nested behavior is documented/tested |  |  | ✓
Vector storage | Efficient storage/retrieval of vector payloads | P0 | Core | DBA | Vector schema | 20 | High | Vectors round-trip without precision issues |  |  | ✓
HNSW metadata | M, efConstruction, efSearch, metric, graph version and build stats | P0 | Core | DBA | Vector schema | 12 | Medium | Index configuration is recoverable |  |  | ✓
Build versions | Track index generation, source snapshot and migration state | P0 | Production | DBA | HNSW metadata | 10 | High | Every index has provenance |  |  | ✓
Partitioning | Partition vectors/metadata by tenant or collection where needed | P1 | Scale | DBA | Vector storage | 20 | High | Partition queries remain correct |  |  | ✓
Compaction state | Track tombstones, compaction jobs and rebuild progress | P1 | Scale | DBA | Updates | 12 | Medium | Background jobs are observable |  |  | ✓
Snapshots | Atomic index/data snapshots with checksums | P0 | Production | DBA | Index persistence | 18 | Critical | Snapshots restore correctly |  |  | ✓
Backup/restore | Scheduled backups and tested recovery | P0 | Production | DBA | Snapshots | 14 | Critical | Restore drill succeeds |  |  | ✓
Encryption | Encryption in transit/at rest and secret management | P0 | Security | DBA | Infrastructure | 12 | Critical | Sensitive data protected |  |  | ✓
Retention/deletion | Delete vectors and metadata with verifiable purge semantics | P0 | Security | DBA | Lifecycle | 16 | High | Deleted data is not returned |  |  | ✓
Metadata indexes | B-tree/bitmap/hash/etc. indexes for hot filter predicates | P0 | Optimization | DBA | Filterable fields | 18 | High | Hot predicates meet latency targets |  |  | ✓
Storage metrics | Track disk, memory, index size, tombstones and growth | P1 | Production | DBA | All storage | 10 | Low | Capacity trends are visible |  |  | ✓
Multi-tenancy & Collections | P0 | Core | Backend Lead | Auth + schema | 18 | Critical | Collections are isolated and addressable | 0 cross-collection leaks |  | ✓ | ✓
Collection lifecycle | P1 | Core | Backend | Collections | 14 | High | Create/update/delete collection safely | Lifecycle tests pass |  | ✓ | ✓
Schema evolution | P1 | Production | Backend/DBA | Database schema | 18 | High | Backward-compatible migrations are tested | Migration success 100% |  | ✓ | ✓
Idempotent writes | P0 | Reliability | Backend | Insert/update APIs | 12 | High | Retries do not duplicate data | Duplicate-write rate 0 |  | ✓ | ✓
API compatibility matrix | P1 | Production | Backend | API versions | 12 | Medium | Supported clients/index versions documented | Compatibility tests |  | ✓ | ✓
Capacity planning | P1 | Scale | SRE/DBA | Storage metrics | 18 | Medium | Growth thresholds and scaling actions documented | Forecast horizon |  | ✓ | ✓
Cost monitoring | P1 | Production | SRE/DBA | Capacity | 12 | Medium | Compute/storage/network costs attributable | Cost per query tracked |  | ✓ | ✓
Data quality validation | P0 | Core | Data/Backend | Vector storage | 18 | Critical | Dimension/type/range and metadata quality checked | Invalid records blocked |  | ✓ | ✓
Embedding provenance | P0 | Research | ML/Data | Vector schema | 16 | High | Model/version/source are tracked for every vector set | Provenance coverage 100% |  | ✓ | ✓ | ✓
Model version compatibility | P0 | AI/ML | ML/Backend | Embedding provenance | 18 | Critical | Queries and stored vectors use compatible model versions | Compatibility failures blocked |  | ✓ | ✓ | ✓
Adversarial vector testing | P0 | Security | Security/ML | Fuzzing | 20 | Critical | Malformed/adversarial vectors cannot crash or poison index | 0 critical findings |  | ✓ | ✓ | ✓
Poisoning/data-integrity checks | P1 | Security | Security/Data | Data validation | 20 | Critical | Suspicious bulk changes are detected | Integrity alerts |  | ✓ | ✓ | ✓
Secrets rotation | P0 | Security | DevOps | Secrets manager | 12 | Critical | Secrets can rotate without downtime | Rotation drill |  | ✓ | ✓
Key management | P0 | Security | DevOps | Encryption | 14 | Critical | Encryption keys are managed separately and rotated | Key rotation test |  | ✓ | ✓
Immutable audit logs | P1 | Security | Security/DBA | Audit trail | 14 | High | Privileged events resist alteration | Audit integrity check |  | ✓ | ✓
Compliance export | P2 | Production | Backend/DBA | Audit + retention | 14 | Medium | Required records can be exported | Export correctness |  | ✓ | ✓
Disaster recovery region | P2 | Production | SRE/DBA | Backups | 24 | Critical | Service can restore in alternate region | DR drill |  | ✓ | ✓
Restore point verification | P1 | Production | DBA | Snapshots | 12 | High | Backup integrity is automatically verified | Verification pass |  |  | ✓
Index corruption detector | P0 | Reliability | Index/QA | HNSW invariants | 20 | Critical | Corrupt graph/index states are detected before serving | Detection tests |  | ✓ | ✓
Online integrity checker | P1 | Reliability | Index | Corruption detector | 16 | High | Background checks do not block reads | Integrity coverage |  | ✓ | ✓
Golden dataset regression | P0 | Testing | QA | Exact baseline | 16 | High | Known queries detect ranking/filter regressions | 0 golden regressions |  | ✓ | ✓ | ✓
Cross-version benchmark | P1 | Testing | Performance | Versioning | 18 | Medium | New releases compare against prior baseline | Regression report |  | ✓ | ✓ | ✓
Memory fragmentation tests | P1 | Performance | Performance/DBA | Memory budget | 18 | High | Long-running process remains within memory envelope | Soak memory bound |  | ✓ | ✓
Long-duration soak test | P0 | Reliability | QA/SRE | All core systems | 24 | Critical | System remains stable for extended workload | Soak pass |  | ✓ | ✓
Upgrade/downgrade test | P0 | Production | Release | Versioning | 18 | Critical | Supported upgrades and rollback paths work | Upgrade matrix pass |  | ✓ | ✓
Migration dry-run | P1 | Production | DBA | Schema evolution | 12 | High | Migrations can be validated before production | Dry-run pass |  | ✓ | ✓
Usage quotas/billing hooks | P2 | Product | Backend/DBA | Rate limiting | 16 | Medium | Usage can be measured per tenant | Metering accuracy |  | ✓ | ✓

## AI-ML
AI/ML — ALL ASSIGNED WORK
Feature | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Frontend | Backend | Database | AI/ML
Benchmark datasets | Curate public/synthetic datasets across dimensions and distributions | P0 | Research | ML/Research |  | 18 | Medium | Datasets are versioned and reproducible |  |  |  | ✓
Filter selectivity corpus | Generate/collect metadata distributions from 0.001% to 100% selectivity | P0 | Research | ML/Research | Datasets | 16 | High | All selectivity bands represented |  |  |  | ✓
Recall@k | Measure filtered and unfiltered recall against exact ground truth | P0 | Research | ML/Research | Datasets + backend | 24 | Critical | Recall curves generated |  |  |  | ✓
Latency modeling | Model p50/p95/p99 latency vs efSearch, k and selectivity | P0 | Research | ML/Research | Benchmarks | 20 | High | Latency model is reproducible |  |  |  | ✓
Adaptive efSearch | Learn/fit policy for efSearch under filter selectivity | P1 | Experimental | ML/Research | Latency modeling | 28 | High | Policy respects recall floor |  |  |  | ✓
Candidate budgeting | Predict required candidate budget from filter density | P1 | Experimental | ML/Research | Selectivity corpus | 24 | High | Budget reduces wasted work without recall loss |  |  |  | ✓
Query strategy selection | Classify query into pre-filter/post-filter/hybrid execution | P1 | Experimental | ML/Research | Query planner | 28 | High | Strategy improves benchmark envelope |  |  |  | ✓
Recall-risk estimator | Estimate whether a query is under-searching | P2 | Research | ML/Research | Evaluation | 22 | Medium | Risk score correlates with recall misses |  |  |  | ✓
Experiment tracking | Version datasets, code, parameters and results | P0 | Research | ML/Research | All experiments | 12 | Medium | Any benchmark is reproducible |  |  |  | ✓
Model/config registry | Promote/revert adaptive policies and benchmark configurations | P1 | Beta | ML/Research | Experiment tracking | 14 | Medium | Rollback works safely |  |  |  | ✓
Deterministic fallback | Disable ML and revert to fixed safe search parameters | P0 | Production | Backend/ML | Adaptive systems | 12 | Critical | System remains correct without ML |  |  |  | ✓
Audit trail | Record privileged/index lifecycle operations | P1 | Security | Backend | Authorization | 10 | Medium | Audit events are searchable |  | ✓ |  | ✓
Containerization | Reproducible service/index runtime | P0 | Production | DevOps | Build | 14 | Medium | Clean deployment succeeds |  | ✓ |  | ✓
Paper/benchmark report | Document algorithm, filtering strategy, baselines and limitations | P2 | Research | Research Lead | Evaluation | 24 | Medium | Results reproducible by another team |  | ✓ |  | ✓
Embedding provenance | P0 | Research | ML/Data | Vector schema | 16 | High | Model/version/source are tracked for every vector set | Provenance coverage 100% |  | ✓ | ✓ | ✓
Embedding drift detection | P1 | AI/ML | ML | Provenance | 22 | High | Distribution changes are detected and reported | Drift alerts |  |  |  | ✓
Model version compatibility | P0 | AI/ML | ML/Backend | Embedding provenance | 18 | Critical | Queries and stored vectors use compatible model versions | Compatibility failures blocked |  | ✓ | ✓ | ✓
Offline evaluation pipeline | P0 | AI/ML | ML/Research | Datasets | 22 | High | One command reproduces recall/latency evaluation | Reproduction pass |  | ✓ |  | ✓
Online A/B evaluation | P1 | AI/ML | ML/Product | Feature flags | 24 | High | Search policies can be compared safely | Statistical report |  | ✓ |  | ✓
Confidence/calibration dashboard | P2 | AI/ML | ML | Risk estimator | 16 | Medium | Predicted risk is compared with observed outcomes | Calibration error tracked |  |  |  | ✓
Adversarial vector testing | P0 | Security | Security/ML | Fuzzing | 20 | Critical | Malformed/adversarial vectors cannot crash or poison index | 0 critical findings |  | ✓ | ✓ | ✓
Poisoning/data-integrity checks | P1 | Security | Security/Data | Data validation | 20 | Critical | Suspicious bulk changes are detected | Integrity alerts |  | ✓ | ✓ | ✓
Deterministic seed control | P0 | Research | Index/ML | Benchmark harness | 10 | Medium | Benchmarks/builds can be reproduced | Repeatability pass |  | ✓ |  | ✓
Golden dataset regression | P0 | Testing | QA | Exact baseline | 16 | High | Known queries detect ranking/filter regressions | 0 golden regressions |  | ✓ | ✓ | ✓
Cross-version benchmark | P1 | Testing | Performance | Versioning | 18 | Medium | New releases compare against prior baseline | Regression report |  | ✓ | ✓ | ✓
Search explainability panel | P2 | Frontend/AI | Frontend/ML | Debug metadata | 16 | Medium | Users can inspect why a result/query strategy was used | Explainability coverage | ✓ | ✓ |  | ✓

## Features
FEATURE BACKLOG — ALL FUNCTIONAL & NON-FUNCTIONAL CAPABILITIES
Feature | Priority | Phase | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Frontend | Backend | Database | AI/ML
Search UI shell | Query input, filters, top-k, vector/search mode and result layout | P0 | MVP | Frontend Lead |  | 8 | Medium | All search controls work together | ✓
Vector query input | Text/vector query handling, validation and query-state management | P0 | MVP | Frontend | Search API | 8 | Medium | Valid queries reach API correctly | ✓
Metadata filters | Filter builder for equality/range/set/boolean conditions | P0 | Core | Frontend | Filter schema | 14 | High | Generated filters match backend syntax | ✓
Filter UX | Nested AND/OR groups, clear/reset, saved filters | P1 | Beta | Frontend | Metadata filters | 16 | High | Complex filters remain understandable | ✓
Result list | IDs, scores, metadata, distance/similarity and highlights | P0 | MVP | Frontend | Search API | 10 | Low | Results render consistently | ✓
Pagination/Top-K | Top-k control, cursor/offset semantics and result limits | P0 | MVP | Frontend | Result list | 8 | Medium | Requested k is respected | ✓
Debug mode | Show candidate count, filtering stage and search diagnostics | P1 | Debug | Frontend | Observability API | 10 | Medium | Diagnostics match server metrics | ✓
Large-result rendering | Virtualized lists and incremental rendering | P1 | Hardening | Frontend | Result list | 10 | Medium | UI remains responsive at large k | ✓
Input hardening | Escape/render metadata safely and prevent client-side injection | P0 | Security | Frontend | Result list | 8 | High | Untrusted metadata is safely rendered | ✓
Keyboard/navigation | Keyboard-first search, filters and results | P1 | Beta | Frontend | Search UI | 8 | Low | Core flow usable without pointer | ✓
E2E search tests | Queries, filters, empty results, errors and large k | P0 | Hardening | QA | All frontend flows | 18 | Medium | Critical flows pass CI | ✓
Client telemetry | Query IDs, latency, filter usage and error context | P1 | Beta | Frontend | Telemetry API | 8 | Medium | Events correlate with server request IDs | ✓
Search service | Define query, filter, retrieval and response service boundaries | P0 | Foundation | Backend Lead |  | 12 | High | Responsibilities are independently testable |  | ✓
Search API | Versioned endpoint for vector search + filters + top-k | P0 | MVP | Backend | Search service | 16 | High | Contract and validation tests pass |  | ✓
Filter DSL | Canonical representation and validation for filter expressions | P0 | Core | Backend | Search API | 20 | Critical | All supported operators parse deterministically |  | ✓
Query validation | Dimensions, NaN/Inf, empty vectors, k bounds and filter limits | P0 | Security | Backend | Filter DSL | 12 | High | Invalid input is rejected safely |  | ✓
HNSW build | Graph construction with configurable M/Mmax/efConstruction | P0 | Core | Search/Index | Vector store | 32 | Critical | Index builds reproducibly |  | ✓
HNSW search | Approximate nearest-neighbor traversal with efSearch | P0 | Core | Search/Index | HNSW build | 32 | Critical | Top-k search returns valid candidates |  | ✓
Filtered traversal | Apply metadata predicates during candidate exploration | P0 | Core | Search/Index | Filter DSL + HNSW search | 36 | Critical | Filtered results contain only valid records |  | ✓
Pre/post filtering modes | Support and benchmark filter-before/after candidate selection | P1 | Research | Search/Index | Filtered traversal | 20 | High | Modes are behaviorally correct |  | ✓
Adaptive efSearch | Adjust search breadth based on k, filter selectivity and target recall | P1 | Optimization | Backend | Filtered traversal | 24 | High | Bounded adaptive policy is deterministic |  | ✓
Deletion/tombstones | Logical deletion and graph-safe handling of removed vectors | P0 | Core | Backend | HNSW search | 24 | Critical | Deleted vectors never appear |  | ✓
Updates | Metadata/vector update semantics and re-index strategy | P0 | Core | Backend | Deletion | 26 | High | Updates become query-visible consistently |  | ✓
Compaction/rebuild | Background cleanup and full/partial rebuild | P1 | Scale | Backend | Updates | 30 | Critical | Compaction preserves correctness |  | ✓
Index snapshots | Persist/load graph, vectors, metadata and version information | P0 | MVP | Backend | HNSW build | 24 | Critical | Reloaded index matches source behavior |  | ✓
Crash recovery | Atomic writes, WAL/checkpoint or equivalent recovery | P0 | Production | Backend | Snapshots | 24 | Critical | Crash does not corrupt index |  | ✓
Read/write concurrency | Safe concurrent search, insert, update, delete and rebuild | P0 | Core | Backend | Index lifecycle | 36 | Critical | No races/corruption under stress |  | ✓
Locking strategy | Minimize contention with documented synchronization model | P1 | Optimization | Backend | Concurrency | 18 | High | Hot path contention measured |  | ✓
Sharding | Partition index by tenant, region or hash | P2 | Scale | Backend | Persistence | 32 | High | Queries route to correct shards |  | ✓
Replication | Replica strategy for availability and read scaling | P2 | Production | Backend | Sharding | 28 | Critical | Replica consistency model documented/tested |  | ✓
Fan-out search | Parallel search across shards and global top-k merge | P2 | Scale | Backend | Sharding | 28 | High | Global top-k is correct |  | ✓
Benchmark harness | Recall@k, latency, QPS, memory, build time and filter selectivity | P0 | Research | Performance | Search API | 24 | High | Benchmarks are reproducible |  | ✓
Query planner | Choose search strategy using filter selectivity and index statistics | P1 | Optimization | Backend | Benchmarks | 28 | High | Planner decisions are observable |  | ✓
Tenant isolation | Prevent cross-tenant vector/metadata access | P0 | Security | Backend | API auth | 20 | Critical | Isolation tests pass |  | ✓
Resource limits | Bound vector dimension, k, filter complexity, memory and CPU | P0 | Security | Backend | Query validation | 16 | High | Abusive requests are rejected/throttled |  | ✓
Property tests | Validate graph invariants, filters and ranking behavior | P0 | Hardening | QA | Core index | 24 | Critical | Property suite passes |  | ✓
Fuzzing | Fuzz vectors, filters, serialized indexes and API payloads | P0 | Security | Security/QA | Validation | 28 | Critical | No crashes/corruption found |  | ✓
Benchmark datasets | Curate public/synthetic datasets across dimensions and distributions | P0 | Research | ML/Research |  | 18 | Medium | Datasets are versioned and reproducible |  |  |  | ✓
Filter selectivity corpus | Generate/collect metadata distributions from 0.001% to 100% selectivity | P0 | Research | ML/Research | Datasets | 16 | High | All selectivity bands represented |  |  |  | ✓
Recall@k | Measure filtered and unfiltered recall against exact ground truth | P0 | Research | ML/Research | Datasets + backend | 24 | Critical | Recall curves generated |  |  |  | ✓
Latency modeling | Model p50/p95/p99 latency vs efSearch, k and selectivity | P0 | Research | ML/Research | Benchmarks | 20 | High | Latency model is reproducible |  |  |  | ✓
Adaptive efSearch | Learn/fit policy for efSearch under filter selectivity | P1 | Experimental | ML/Research | Latency modeling | 28 | High | Policy respects recall floor |  |  |  | ✓
Candidate budgeting | Predict required candidate budget from filter density | P1 | Experimental | ML/Research | Selectivity corpus | 24 | High | Budget reduces wasted work without recall loss |  |  |  | ✓
Query strategy selection | Classify query into pre-filter/post-filter/hybrid execution | P1 | Experimental | ML/Research | Query planner | 28 | High | Strategy improves benchmark envelope |  |  |  | ✓
Recall-risk estimator | Estimate whether a query is under-searching | P2 | Research | ML/Research | Evaluation | 22 | Medium | Risk score correlates with recall misses |  |  |  | ✓
Experiment tracking | Version datasets, code, parameters and results | P0 | Research | ML/Research | All experiments | 12 | Medium | Any benchmark is reproducible |  |  |  | ✓
Model/config registry | Promote/revert adaptive policies and benchmark configurations | P1 | Beta | ML/Research | Experiment tracking | 14 | Medium | Rollback works safely |  |  |  | ✓
Deterministic fallback | Disable ML and revert to fixed safe search parameters | P0 | Production | Backend/ML | Adaptive systems | 12 | Critical | System remains correct without ML |  |  |  | ✓
Vector schema | Define vector ID, dimension, metric, payload and version model | P0 | Foundation | DBA/Backend |  | 12 | High | Schema supports required lifecycle |  |  | ✓
Filterable fields | Index/selectivity strategy for categorical, numeric and boolean metadata | P0 | Core | DBA | Filter DSL | 18 | Critical | All supported predicates execute correctly |  |  | ✓
Nested metadata | Define nested/object field semantics and limitations | P1 | Beta | DBA | Filterable fields | 12 | High | Nested behavior is documented/tested |  |  | ✓
Vector storage | Efficient storage/retrieval of vector payloads | P0 | Core | DBA | Vector schema | 20 | High | Vectors round-trip without precision issues |  |  | ✓
HNSW metadata | M, efConstruction, efSearch, metric, graph version and build stats | P0 | Core | DBA | Vector schema | 12 | Medium | Index configuration is recoverable |  |  | ✓
Build versions | Track index generation, source snapshot and migration state | P0 | Production | DBA | HNSW metadata | 10 | High | Every index has provenance |  |  | ✓
Partitioning | Partition vectors/metadata by tenant or collection where needed | P1 | Scale | DBA | Vector storage | 20 | High | Partition queries remain correct |  |  | ✓
Compaction state | Track tombstones, compaction jobs and rebuild progress | P1 | Scale | DBA | Updates | 12 | Medium | Background jobs are observable |  |  | ✓
Snapshots | Atomic index/data snapshots with checksums | P0 | Production | DBA | Index persistence | 18 | Critical | Snapshots restore correctly |  |  | ✓
Backup/restore | Scheduled backups and tested recovery | P0 | Production | DBA | Snapshots | 14 | Critical | Restore drill succeeds |  |  | ✓
Encryption | Encryption in transit/at rest and secret management | P0 | Security | DBA | Infrastructure | 12 | Critical | Sensitive data protected |  |  | ✓
Retention/deletion | Delete vectors and metadata with verifiable purge semantics | P0 | Security | DBA | Lifecycle | 16 | High | Deleted data is not returned |  |  | ✓
Metadata indexes | B-tree/bitmap/hash/etc. indexes for hot filter predicates | P0 | Optimization | DBA | Filterable fields | 18 | High | Hot predicates meet latency targets |  |  | ✓
Storage metrics | Track disk, memory, index size, tombstones and growth | P1 | Production | DBA | All storage | 10 | Low | Capacity trends are visible |  |  | ✓
ANN search | Approximate nearest-neighbor search using HNSW | P0 | Core | Product | HNSW search | 30 | Critical | Correct top-k contract |  | ✓
Filtered ANN | ANN search constrained by metadata predicates | P0 | Core | Product | Filtered traversal | 36 | Critical | No invalid metadata results |  | ✓
Exact baseline | Brute-force/exact search for ground truth and small collections | P0 | Research | Backend | Vector storage | 18 | Medium | Exact results are reproducible |  | ✓
Distance metrics | Cosine, inner product and/or Euclidean as supported | P0 | MVP | Backend | Vector schema | 16 | High | Metric semantics are documented/tested |  | ✓
Top-k | Configurable k with hard limits | P0 | MVP | Backend | Search API | 8 | Medium | Exactly valid k behavior |  | ✓
Boolean filters | AND/OR/NOT expression support | P0 | Core | Backend | Filter DSL | 20 | Critical | Boolean semantics are deterministic |  | ✓
Range filters | Numeric/date range predicates | P0 | Core | Backend | Filter DSL | 14 | High | Inclusive/exclusive semantics documented |  | ✓
Set filters | IN/NOT IN and membership predicates | P0 | Core | Backend | Filter DSL | 12 | Medium | Set semantics correct |  | ✓
Filter pushdown | Use metadata conditions during ANN traversal when safe | P1 | Optimization | Backend | Filtered traversal | 24 | Critical | No recall violations |  | ✓
Hybrid execution | Combine graph traversal and metadata candidate filtering | P1 | Optimization | Backend | Filter pushdown | 28 | High | Strategy is benchmarked |  | ✓
Insert | Add vectors and metadata | P0 | MVP | Backend | Vector storage | 18 | High | Inserted data becomes queryable |  | ✓
Update | Update vector and/or metadata safely | P0 | Core | Backend | Insert + delete | 20 | High | Old record is not returned |  | ✓
Delete | Logical/physical deletion semantics | P0 | Core | Backend | Insert | 18 | Critical | Deleted records never return |  | ✓
Rebuild | Rebuild index from canonical storage | P0 | Production | Backend | Snapshots | 30 | Critical | Rebuilt index matches benchmark | ✓ | ✓
Online compaction | Background tombstone cleanup | P1 | Scale | Backend | Delete + rebuild | 24 | High | Compaction does not block reads |  | ✓
Warm cache | Cache hot query/index metadata where beneficial | P1 | Optimization | Backend | Search | 14 | Medium | Cache improves repeat query latency |  | ✓
Batch search | Efficient multi-query/batch API | P1 | Scale | Backend | Search API | 18 | High | Batch results equal individual semantics |  | ✓
Parallel search | Parallel graph traversal across workers/shards | P2 | Scale | Backend | Sharding | 22 | High | Parallel merge is correct |  | ✓
Memory budget | Bound graph/vector/filter memory consumption | P0 | Hardening | Backend | All index components | 18 | Critical | Configured memory budget is enforced |  | ✓
Crash-safe index | Recover from interrupted build/write | P0 | Production | Backend | Persistence | 22 | Critical | No corrupted index loads |  | ✓
Index versioning | Load old versions or migrate explicitly | P0 | Production | Backend | Snapshots | 18 | High | Compatibility rules are enforced |  | ✓
Authentication | Secure API authentication | P0 | Security | Backend | API | 14 | Critical | Invalid credentials rejected |  | ✓
Authorization | Collection/tenant-level access control | P0 | Security | Backend | Authentication | 16 | Critical | Cross-tenant reads blocked |  | ✓
Rate limiting | Query and write quotas | P0 | Security | Backend | Authentication | 12 | High | Abusive clients are throttled |  | ✓
Audit trail | Record privileged/index lifecycle operations | P1 | Security | Backend | Authorization | 10 | Medium | Audit events are searchable |  | ✓ |  | ✓
Correctness suite | Ranking, filtering, lifecycle and persistence tests | P0 | Hardening | QA | All core features | 30 | Critical | CI blocks regressions | ✓ | ✓
Concurrency suite | Read/write/rebuild concurrency and race testing | P0 | Hardening | QA | Concurrency | 28 | Critical | No data races/corruption | ✓ | ✓
Performance suite | Benchmark recall, p50/p95/p99, QPS, memory and build time | P0 | Research | QA | Benchmark harness | 26 | High | Results are reproducible | ✓ | ✓
Chaos suite | Disk failure, process kill, latency and resource pressure | P1 | Production | QA | Recovery | 24 | Critical | System recovers within targets | ✓ | ✓
Admin API | Index stats, rebuild, compaction, health and job controls | P1 | Beta | Backend | Observability | 20 | High | Operators can safely manage index |  | ✓
Health/readiness | Liveness, readiness and index health endpoints | P0 | Production | Backend | Observability | 10 | Medium | Orchestrator can detect unhealthy instances |  | ✓
Metrics | Recall proxy, latency, QPS, filter selectivity and resource metrics | P0 | Production | Backend | Observability | 16 | Medium | Critical metrics are exposed |  | ✓
Tracing | End-to-end query tracing through planner/index/storage | P1 | Production | Backend | Metrics | 16 | Medium | Slow queries are diagnosable |  | ✓
Containerization | Reproducible service/index runtime | P0 | Production | DevOps | Build | 14 | Medium | Clean deployment succeeds |  | ✓ |  | ✓
CI/CD | Tests, fuzzing, benchmarks and security gates | P0 | Production | DevOps | Testing | 20 | High | Required gates run on changes |  | ✓
API docs | Search/filter/index lifecycle API specification | P0 | Beta | Tech Lead | API | 14 | Low | Examples cover supported behavior |  | ✓
Operations runbook | Rebuild, restore, compaction, incidents and capacity procedures | P0 | Production | DevOps | Operations | 16 | High | Operators can execute drills |  | ✓
Paper/benchmark report | Document algorithm, filtering strategy, baselines and limitations | P2 | Research | Research Lead | Evaluation | 24 | Medium | Results reproducible by another team |  | ✓ |  | ✓
Multi-tenancy & Collections | P0 | Core | Backend Lead | Auth + schema | 18 | Critical | Collections are isolated and addressable | 0 cross-collection leaks |  | ✓ | ✓
Collection lifecycle | P1 | Core | Backend | Collections | 14 | High | Create/update/delete collection safely | Lifecycle tests pass |  | ✓ | ✓
Schema evolution | P1 | Production | Backend/DBA | Database schema | 18 | High | Backward-compatible migrations are tested | Migration success 100% |  | ✓ | ✓
API pagination/cursors | P1 | Core | Backend | Search API | 12 | Medium | Stable cursor semantics across changing data | Cursor tests pass |  | ✓
Idempotent writes | P0 | Reliability | Backend | Insert/update APIs | 12 | High | Retries do not duplicate data | Duplicate-write rate 0 |  | ✓ | ✓
Request cancellation | P1 | Performance | Backend | Search API | 10 | Medium | Cancelled queries stop consuming resources | Cancellation effectiveness |  | ✓
Timeout budgets | P0 | Reliability | Backend | Search API | 10 | High | Per-stage and end-to-end deadlines enforced | Timeout violations tracked |  | ✓
Backpressure | P0 | Scale | Backend | Concurrency | 18 | Critical | Overload is contained without cascading failure | Queue saturation controlled |  | ✓
Circuit breakers | P1 | Production | Backend | Dependencies | 14 | High | Dependency failures do not cascade | Recovery tests |  | ✓
Load shedding | P1 | Scale | Backend | Backpressure | 14 | High | System degrades predictably under overload | Availability target |  | ✓
Rate-limit analytics | P1 | Production | Backend | Rate limiting | 10 | Medium | Operators can inspect abuse patterns | Alerts actionable |  | ✓
API compatibility matrix | P1 | Production | Backend | API versions | 12 | Medium | Supported clients/index versions documented | Compatibility tests |  | ✓ | ✓
Feature flags | P1 | Production | Backend | Deployment | 12 | Medium | Risky features can be enabled/disabled safely | Rollback <5 min |  | ✓
Canary deployment | P1 | Production | DevOps | CI/CD | 16 | High | New version can receive controlled traffic | Canary rollback tested |  | ✓
Blue/green deployment | P2 | Production | DevOps | Deployment | 16 | High | Traffic can switch between versions | Switchback tested |  | ✓
SLO/SLI definitions | P0 | Production | SRE | Observability | 12 | Medium | Latency/availability/error SLOs documented | SLO dashboard |  | ✓
Alerting policy | P0 | Production | SRE | Metrics | 14 | High | Critical failures page with actionable context | Alert test pass |  | ✓
Capacity planning | P1 | Scale | SRE/DBA | Storage metrics | 18 | Medium | Growth thresholds and scaling actions documented | Forecast horizon |  | ✓ | ✓
Cost monitoring | P1 | Production | SRE/DBA | Capacity | 12 | Medium | Compute/storage/network costs attributable | Cost per query tracked |  | ✓ | ✓
Synthetic monitoring | P1 | Production | QA/SRE | Health endpoints | 12 | Low | Scheduled real-user-like queries detect regressions | Synthetic pass rate |  | ✓
Data quality validation | P0 | Core | Data/Backend | Vector storage | 18 | Critical | Dimension/type/range and metadata quality checked | Invalid records blocked |  | ✓ | ✓
Embedding provenance | P0 | Research | ML/Data | Vector schema | 16 | High | Model/version/source are tracked for every vector set | Provenance coverage 100% |  | ✓ | ✓ | ✓
Embedding drift detection | P1 | AI/ML | ML | Provenance | 22 | High | Distribution changes are detected and reported | Drift alerts |  |  |  | ✓
Model version compatibility | P0 | AI/ML | ML/Backend | Embedding provenance | 18 | Critical | Queries and stored vectors use compatible model versions | Compatibility failures blocked |  | ✓ | ✓ | ✓
Offline evaluation pipeline | P0 | AI/ML | ML/Research | Datasets | 22 | High | One command reproduces recall/latency evaluation | Reproduction pass |  | ✓ |  | ✓
Online A/B evaluation | P1 | AI/ML | ML/Product | Feature flags | 24 | High | Search policies can be compared safely | Statistical report |  | ✓ |  | ✓
Confidence/calibration dashboard | P2 | AI/ML | ML | Risk estimator | 16 | Medium | Predicted risk is compared with observed outcomes | Calibration error tracked |  |  |  | ✓
Adversarial vector testing | P0 | Security | Security/ML | Fuzzing | 20 | Critical | Malformed/adversarial vectors cannot crash or poison index | 0 critical findings |  | ✓ | ✓ | ✓
Poisoning/data-integrity checks | P1 | Security | Security/Data | Data validation | 20 | Critical | Suspicious bulk changes are detected | Integrity alerts |  | ✓ | ✓ | ✓
Supply-chain security | P0 | Security | DevSecOps | CI/CD | 16 | Critical | Dependencies/images are scanned and pinned | 0 critical unreviewed CVEs |  | ✓
SBOM generation | P1 | Security | DevSecOps | Build pipeline | 10 | Medium | Release artifacts have SBOMs | 100% releases |  | ✓
Secrets rotation | P0 | Security | DevOps | Secrets manager | 12 | Critical | Secrets can rotate without downtime | Rotation drill |  | ✓ | ✓
Key management | P0 | Security | DevOps | Encryption | 14 | Critical | Encryption keys are managed separately and rotated | Key rotation test |  | ✓ | ✓
Immutable audit logs | P1 | Security | Security/DBA | Audit trail | 14 | High | Privileged events resist alteration | Audit integrity check |  | ✓ | ✓
Compliance export | P2 | Production | Backend/DBA | Audit + retention | 14 | Medium | Required records can be exported | Export correctness |  | ✓ | ✓
Geo/region routing | P2 | Scale | Backend | Sharding | 20 | High | Queries route to intended region | Routing correctness |  | ✓
Disaster recovery region | P2 | Production | SRE/DBA | Backups | 24 | Critical | Service can restore in alternate region | DR drill |  | ✓ | ✓
Restore point verification | P1 | Production | DBA | Snapshots | 12 | High | Backup integrity is automatically verified | Verification pass |  |  | ✓
Index corruption detector | P0 | Reliability | Index/QA | HNSW invariants | 20 | Critical | Corrupt graph/index states are detected before serving | Detection tests |  | ✓ | ✓
Online integrity checker | P1 | Reliability | Index | Corruption detector | 16 | High | Background checks do not block reads | Integrity coverage |  | ✓ | ✓
Graph visualization/debugger | P2 | Developer Tool | Frontend/Index | Index stats | 20 | Medium | Developers can inspect graph/neighbor structure | Debug workflow pass | ✓ | ✓
Query replay | P1 | Developer Tool | Backend/QA | Tracing | 18 | High | Production-safe queries can be replayed offline | Replay parity |  | ✓
Deterministic seed control | P0 | Research | Index/ML | Benchmark harness | 10 | Medium | Benchmarks/builds can be reproduced | Repeatability pass |  | ✓ |  | ✓
Golden dataset regression | P0 | Testing | QA | Exact baseline | 16 | High | Known queries detect ranking/filter regressions | 0 golden regressions |  | ✓ | ✓ | ✓
Cross-version benchmark | P1 | Testing | Performance | Versioning | 18 | Medium | New releases compare against prior baseline | Regression report |  | ✓ | ✓ | ✓
Memory fragmentation tests | P1 | Performance | Performance/DBA | Memory budget | 18 | High | Long-running process remains within memory envelope | Soak memory bound |  | ✓ | ✓
Long-duration soak test | P0 | Reliability | QA/SRE | All core systems | 24 | Critical | System remains stable for extended workload | Soak pass |  | ✓ | ✓
Upgrade/downgrade test | P0 | Production | Release | Versioning | 18 | Critical | Supported upgrades and rollback paths work | Upgrade matrix pass |  | ✓ | ✓
Migration dry-run | P1 | Production | DBA | Schema evolution | 12 | High | Migrations can be validated before production | Dry-run pass |  | ✓ | ✓
User-facing error taxonomy | P1 | Frontend | Frontend | API errors | 10 | Low | Errors are actionable and consistent | Error coverage |  | ✓
Search explainability panel | P2 | Frontend/AI | Frontend/ML | Debug metadata | 16 | Medium | Users can inspect why a result/query strategy was used | Explainability coverage | ✓ | ✓ |  | ✓
Usage quotas/billing hooks | P2 | Product | Backend/DBA | Rate limiting | 16 | Medium | Usage can be measured per tenant | Metering accuracy |  | ✓ | ✓

## Dashboard
FINAL PROJECT DASHBOARD
Scope, effort, priorities and workstream coverage.
Metric | Value
Total capabilities/features
Frontend assignments
Backend assignments
Database assignments
AI/ML assignments
P0 items
P1 items
Estimated engineering hours
Critical-risk items

## Release Gates
RELEASE GATES
Gate | Required condition | Owner | Status | Evidence / target
G0 Scope | All required capabilities mapped to an owner/workstream | Tech Lead | Not Started | Feature Matrix reviewed
G1 Foundation | API, filter DSL, schema, build and test harness | Tech Lead | Not Started | Foundation tests pass
G2 HNSW Core | Build/search/exact baseline/snapshot/restore | Index Lead | Not Started | Recall + latency benchmark
G3 Filtering | Boolean/range/set filters and filtered traversal | Backend Lead | Not Started | 0 invalid filtered results
G4 Lifecycle | Insert/update/delete/rebuild/compaction | Backend Lead | Not Started | Lifecycle suite pass
G5 Performance | p50/p95/p99, QPS, recall and memory envelope | Performance Lead | Not Started | Benchmark report
G6 Security | Auth, isolation, limits, fuzzing, supply-chain controls | Security | Not Started | 0 critical findings
G7 Reliability | Backups, restore, crash recovery, soak and chaos | SRE/QA | Not Started | RPO/RTO met
G8 AI/ML | Offline evaluation, guardrails, fallback, versioning | ML Lead | Not Started | Reproducible evaluation
G9 Production | SLOs, alerting, tracing, CI/CD, canary/rollback | DevOps | Not Started | Production checklist
G10 Documentation | API, architecture, research report and runbooks | Tech/Research | Not Started | Docs review passed