## Dashboard
PROJECT DASHBOARD — 02 HNSW-FILTERED-VECTOR-INDEX
System Metric | Count / Value | Formula Reference
Total Features |  | COUNTA
Verified Features |  | COUNTIF Verified
Implemented Features |  | COUNTIF Implemented
Specified Features |  | COUNTIF Specified
P0 Features |  | COUNTIF P0
P1 Features |  | COUNTIF P1
P2 Features |  | COUNTIF P2
Total Estimated Effort (Hours) |  | SUM Hours

## Feature Matrix
ID | Feature | Priority | Area | Frontend | Backend | Database | AI/ML | API | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-02-001 | Search UI shell | P0 | Core | ✓ |  |  |  |  | 8 | Medium | Specified | All search controls work together | 100% test pass
FEAT-02-002 | Vector query input | P0 | Core |  | ✓ |  |  |  | 8 | Medium | Specified | Valid queries reach API correctly | 100% test pass
FEAT-02-003 | Metadata filters | P0 | Core |  | ✓ |  |  |  | 14 | High | Specified | Generated filters match backend syntax | 100% test pass
FEAT-02-004 | Filter UX | P1 | Core |  | ✓ |  |  |  | 16 | High | Specified | Complex filters remain understandable | 100% test pass
FEAT-02-005 | Result list | P0 | Core |  | ✓ |  |  |  | 10 | Low | Specified | Results render consistently | 100% test pass
FEAT-02-006 | Pagination/Top-K | P0 | Core |  | ✓ |  |  |  | 8 | Medium | Specified | Requested k is respected | 100% test pass
FEAT-02-007 | Debug mode | P1 | Core |  | ✓ |  |  |  | 10 | Medium | Specified | Diagnostics match server metrics | 100% test pass
FEAT-02-008 | Large-result rendering | P1 | Core |  | ✓ |  |  |  | 10 | Medium | Specified | UI remains responsive at large k | 100% test pass
FEAT-02-009 | Input hardening | P0 | Core |  | ✓ |  |  |  | 8 | High | Specified | Untrusted metadata is safely rendered | 100% test pass
FEAT-02-010 | Keyboard/navigation | P1 | Core |  | ✓ |  |  |  | 8 | Low | Specified | Core flow usable without pointer | 100% test pass
FEAT-02-011 | E2E search tests | P0 | Core |  | ✓ |  |  |  | 18 | Medium | Specified | Critical flows pass CI | 100% test pass
FEAT-02-012 | Client telemetry | P1 | Core |  | ✓ |  |  |  | 8 | Medium | Specified | Events correlate with server request IDs | 100% test pass
FEAT-02-013 | Search service | P0 | Core |  | ✓ |  |  |  | 12 | High | Specified | Responsibilities are independently testable | 100% test pass
FEAT-02-014 | Search API | P0 | Core |  | ✓ |  |  |  | 16 | High | Specified | Contract and validation tests pass | 100% test pass
FEAT-02-015 | Filter DSL | P0 | Core |  | ✓ |  |  |  | 20 | Critical | Specified | All supported operators parse deterministically | 100% test pass
FEAT-02-016 | Query validation | P0 | Core |  | ✓ |  |  |  | 12 | High | Specified | Invalid input is rejected safely | 100% test pass
FEAT-02-017 | HNSW build | P0 | Core | ✓ |  |  |  |  | 32 | Critical | Specified | Index builds reproducibly | 100% test pass
FEAT-02-018 | HNSW search | P0 | Core |  | ✓ |  |  |  | 32 | Critical | Specified | Top-k search returns valid candidates | 100% test pass
FEAT-02-019 | Filtered traversal | P0 | Core |  | ✓ |  |  |  | 36 | Critical | Specified | Filtered results contain only valid records | 100% test pass
FEAT-02-020 | Pre/post filtering modes | P1 | Core |  | ✓ |  |  |  | 20 | High | Specified | Modes are behaviorally correct | 100% test pass
FEAT-02-021 | Adaptive efSearch | P1 | Core |  | ✓ |  |  |  | 24 | High | Specified | Bounded adaptive policy is deterministic | 100% test pass
FEAT-02-022 | Deletion/tombstones | P0 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | Deleted vectors never appear | 100% test pass
FEAT-02-023 | Updates | P0 | Core |  | ✓ |  |  |  | 26 | High | Specified | Updates become query-visible consistently | 100% test pass
FEAT-02-024 | Compaction/rebuild | P1 | Core | ✓ |  |  |  |  | 30 | Critical | Specified | Compaction preserves correctness | 100% test pass
FEAT-02-025 | Index snapshots | P0 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | Reloaded index matches source behavior | 100% test pass
FEAT-02-026 | Crash recovery | P0 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | Crash does not corrupt index | 100% test pass
FEAT-02-027 | Read/write concurrency | P0 | Core |  | ✓ |  |  |  | 36 | Critical | Specified | No races/corruption under stress | 100% test pass
FEAT-02-028 | Locking strategy | P1 | Core |  | ✓ |  |  |  | 18 | High | Specified | Hot path contention measured | 100% test pass
FEAT-02-029 | Sharding | P2 | Core |  | ✓ |  |  |  | 32 | High | Specified | Queries route to correct shards | 100% test pass
FEAT-02-030 | Replication | P2 | Core |  | ✓ |  |  |  | 28 | Critical | Specified | Replica consistency model documented/tested | 100% test pass
FEAT-02-031 | Fan-out search | P2 | Core |  | ✓ |  |  |  | 28 | High | Specified | Global top-k is correct | 100% test pass
FEAT-02-032 | Benchmark harness | P0 | Core |  | ✓ |  |  |  | 24 | High | Specified | Benchmarks are reproducible | 100% test pass
FEAT-02-033 | Query planner | P1 | Core |  | ✓ |  |  |  | 28 | High | Specified | Planner decisions are observable | 100% test pass
FEAT-02-034 | Tenant isolation | P0 | Core |  | ✓ |  |  |  | 20 | Critical | Specified | Isolation tests pass | 100% test pass
FEAT-02-035 | Resource limits | P0 | Core |  | ✓ |  |  |  | 16 | High | Specified | Abusive requests are rejected/throttled | 100% test pass
FEAT-02-036 | Property tests | P0 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | Property suite passes | 100% test pass
FEAT-02-037 | Fuzzing | P0 | Core |  | ✓ |  |  |  | 28 | Critical | Specified | No crashes/corruption found | 100% test pass
FEAT-02-038 | Benchmark datasets | P0 | Core |  | ✓ |  |  |  | 18 | Medium | Specified | Datasets are versioned and reproducible | 100% test pass
FEAT-02-039 | Filter selectivity corpus | P0 | Core |  | ✓ |  |  |  | 16 | High | Specified | All selectivity bands represented | 100% test pass
FEAT-02-040 | Recall@k | P0 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | Recall curves generated | 100% test pass
FEAT-02-041 | Latency modeling | P0 | Core |  |  |  | ✓ |  | 20 | High | Specified | Latency model is reproducible | 100% test pass
FEAT-02-042 | Adaptive efSearch | P1 | Core |  | ✓ |  |  |  | 28 | High | Specified | Policy respects recall floor | 100% test pass
FEAT-02-043 | Candidate budgeting | P1 | Core |  | ✓ |  |  |  | 24 | High | Specified | Budget reduces wasted work without recall loss | 100% test pass
FEAT-02-044 | Query strategy selection | P1 | Core |  | ✓ |  |  |  | 28 | High | Specified | Strategy improves benchmark envelope | 100% test pass
FEAT-02-045 | Recall-risk estimator | P2 | Core |  | ✓ |  |  |  | 22 | Medium | Specified | Risk score correlates with recall misses | 100% test pass
FEAT-02-046 | Experiment tracking | P0 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Any benchmark is reproducible | 100% test pass
FEAT-02-047 | Model/config registry | P1 | Core |  |  |  | ✓ |  | 14 | Medium | Specified | Rollback works safely | 100% test pass
FEAT-02-048 | Deterministic fallback | P0 | Core |  | ✓ |  |  |  | 12 | Critical | Specified | System remains correct without ML | 100% test pass
FEAT-02-049 | Vector schema | P0 | Core |  |  | ✓ |  |  | 12 | High | Specified | Schema supports required lifecycle | 100% test pass
FEAT-02-050 | Filterable fields | P0 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | All supported predicates execute correctly | 100% test pass
FEAT-02-051 | Nested metadata | P1 | Core |  | ✓ |  |  |  | 12 | High | Specified | Nested behavior is documented/tested | 100% test pass
FEAT-02-052 | Vector storage | P0 | Core |  | ✓ |  |  |  | 20 | High | Specified | Vectors round-trip without precision issues | 100% test pass
FEAT-02-053 | HNSW metadata | P0 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Index configuration is recoverable | 100% test pass
FEAT-02-054 | Build versions | P0 | Core | ✓ |  |  |  |  | 10 | High | Specified | Every index has provenance | 100% test pass
FEAT-02-055 | Partitioning | P1 | Core |  | ✓ |  |  |  | 20 | High | Specified | Partition queries remain correct | 100% test pass
FEAT-02-056 | Compaction state | P1 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Background jobs are observable | 100% test pass
FEAT-02-057 | Snapshots | P0 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | Snapshots restore correctly | 100% test pass
FEAT-02-058 | Backup/restore | P0 | Core |  | ✓ |  |  |  | 14 | Critical | Specified | Restore drill succeeds | 100% test pass
FEAT-02-059 | Encryption | P0 | Core |  | ✓ |  |  |  | 12 | Critical | Specified | Sensitive data protected | 100% test pass
FEAT-02-060 | Retention/deletion | P0 | Core |  | ✓ |  |  |  | 16 | High | Specified | Deleted data is not returned | 100% test pass
FEAT-02-061 | Metadata indexes | P0 | Core |  | ✓ |  |  |  | 18 | High | Specified | Hot predicates meet latency targets | 100% test pass
FEAT-02-062 | Storage metrics | P1 | Core |  | ✓ |  |  |  | 10 | Low | Specified | Capacity trends are visible | 100% test pass
FEAT-02-063 | ANN search | P0 | Core |  | ✓ |  |  |  | 30 | Critical | Specified | Correct top-k contract | 100% test pass
FEAT-02-064 | Filtered ANN | P0 | Core |  | ✓ |  |  |  | 36 | Critical | Specified | No invalid metadata results | 100% test pass
FEAT-02-065 | Exact baseline | P0 | Core |  | ✓ |  |  |  | 18 | Medium | Specified | Exact results are reproducible | 100% test pass
FEAT-02-066 | Distance metrics | P0 | Core |  | ✓ |  |  |  | 16 | High | Specified | Metric semantics are documented/tested | 100% test pass
FEAT-02-067 | Top-k | P0 | Core |  | ✓ |  |  |  | 8 | Medium | Specified | Exactly valid k behavior | 100% test pass
FEAT-02-068 | Boolean filters | P0 | Core |  | ✓ |  |  |  | 20 | Critical | Specified | Boolean semantics are deterministic | 100% test pass
FEAT-02-069 | Range filters | P0 | Core |  | ✓ |  |  |  | 14 | High | Specified | Inclusive/exclusive semantics documented | 100% test pass
FEAT-02-070 | Set filters | P0 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Set semantics correct | 100% test pass
FEAT-02-071 | Filter pushdown | P1 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | No recall violations | 100% test pass
FEAT-02-072 | Hybrid execution | P1 | Core |  | ✓ |  |  |  | 28 | High | Specified | Strategy is benchmarked | 100% test pass
FEAT-02-073 | Insert | P0 | Core |  | ✓ |  |  |  | 18 | High | Specified | Inserted data becomes queryable | 100% test pass
FEAT-02-074 | Update | P0 | Core |  | ✓ |  |  |  | 20 | High | Specified | Old record is not returned | 100% test pass
FEAT-02-075 | Delete | P0 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | Deleted records never return | 100% test pass
FEAT-02-076 | Rebuild | P0 | Core | ✓ |  |  |  |  | 30 | Critical | Specified | Rebuilt index matches benchmark | 100% test pass
FEAT-02-077 | Online compaction | P1 | Core |  | ✓ |  |  |  | 24 | High | Specified | Compaction does not block reads | 100% test pass
FEAT-02-078 | Warm cache | P1 | Core |  | ✓ |  |  |  | 14 | Medium | Specified | Cache improves repeat query latency | 100% test pass
FEAT-02-079 | Batch search | P1 | Core |  | ✓ |  |  |  | 18 | High | Specified | Batch results equal individual semantics | 100% test pass
FEAT-02-080 | Parallel search | P2 | Core |  | ✓ |  |  |  | 22 | High | Specified | Parallel merge is correct | 100% test pass
FEAT-02-081 | Memory budget | P0 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | Configured memory budget is enforced | 100% test pass
FEAT-02-082 | Crash-safe index | P0 | Core |  | ✓ |  |  |  | 22 | Critical | Specified | No corrupted index loads | 100% test pass
FEAT-02-083 | Index versioning | P0 | Core |  | ✓ |  |  |  | 18 | High | Specified | Compatibility rules are enforced | 100% test pass
FEAT-02-084 | Authentication | P0 | Core |  | ✓ |  |  |  | 14 | Critical | Specified | Invalid credentials rejected | 100% test pass
FEAT-02-085 | Authorization | P0 | Core |  | ✓ |  |  |  | 16 | Critical | Specified | Cross-tenant reads blocked | 100% test pass
FEAT-02-086 | Rate limiting | P0 | Core |  | ✓ |  |  |  | 12 | High | Specified | Abusive clients are throttled | 100% test pass
FEAT-02-087 | Audit trail | P1 | Core |  |  |  | ✓ |  | 10 | Medium | Specified | Audit events are searchable | 100% test pass
FEAT-02-088 | Correctness suite | P0 | Core | ✓ |  |  |  |  | 30 | Critical | Specified | CI blocks regressions | 100% test pass
FEAT-02-089 | Concurrency suite | P0 | Core | ✓ |  |  |  |  | 28 | Critical | Specified | No data races/corruption | 100% test pass
FEAT-02-090 | Performance suite | P0 | Core | ✓ |  |  |  |  | 26 | High | Specified | Results are reproducible | 100% test pass
FEAT-02-091 | Chaos suite | P1 | Core | ✓ |  |  |  |  | 24 | Critical | Specified | System recovers within targets | 100% test pass
FEAT-02-092 | Admin API | P1 | Core |  | ✓ |  |  |  | 20 | High | Specified | Operators can safely manage index | 100% test pass
FEAT-02-093 | Health/readiness | P0 | Core |  | ✓ |  |  |  | 10 | Medium | Specified | Orchestrator can detect unhealthy instances | 100% test pass
FEAT-02-094 | Metrics | P0 | Core |  | ✓ |  |  |  | 16 | Medium | Specified | Critical metrics are exposed | 100% test pass
FEAT-02-095 | Tracing | P1 | Core |  | ✓ |  |  |  | 16 | Medium | Specified | Slow queries are diagnosable | 100% test pass
FEAT-02-096 | Containerization | P0 | Core |  |  |  | ✓ |  | 14 | Medium | Specified | Clean deployment succeeds | 100% test pass
FEAT-02-097 | CI/CD | P0 | Core |  | ✓ |  |  |  | 20 | High | Specified | Required gates run on changes | 100% test pass
FEAT-02-098 | API docs | P0 | Core |  | ✓ |  |  |  | 14 | Low | Specified | Examples cover supported behavior | 100% test pass
FEAT-02-099 | Operations runbook | P0 | Core |  | ✓ |  |  |  | 16 | High | Specified | Operators can execute drills | 100% test pass
FEAT-02-100 | Paper/benchmark report | P2 | Core |  | ✓ |  |  |  | 24 | Medium | Specified | Results reproducible by another team | 100% test pass
FEAT-02-101 | Multi-tenancy & Collections | P1 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | Collections are isolated and addressable | 100% test pass
FEAT-02-102 | Collection lifecycle | P1 | Core |  | ✓ |  |  |  | 14 | High | Specified | Create/update/delete collection safely | 100% test pass
FEAT-02-103 | Schema evolution | P1 | Core |  |  | ✓ |  |  | 18 | High | Specified | Backward-compatible migrations are tested | 100% test pass
FEAT-02-104 | API pagination/cursors | P1 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Stable cursor semantics across changing data | 100% test pass
FEAT-02-105 | Idempotent writes | P1 | Core |  | ✓ |  |  |  | 12 | High | Specified | Retries do not duplicate data | 100% test pass
FEAT-02-106 | Request cancellation | P1 | Core |  | ✓ |  |  |  | 10 | Medium | Specified | Cancelled queries stop consuming resources | 100% test pass
FEAT-02-107 | Timeout budgets | P1 | Core |  | ✓ |  |  |  | 10 | High | Specified | Per-stage and end-to-end deadlines enforced | 100% test pass
FEAT-02-108 | Backpressure | P1 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | Overload is contained without cascading failure | 100% test pass
FEAT-02-109 | Circuit breakers | P1 | Core | ✓ |  |  |  |  | 14 | High | Specified | Dependency failures do not cascade | 100% test pass
FEAT-02-110 | Load shedding | P1 | Core |  | ✓ |  |  |  | 14 | High | Specified | System degrades predictably under overload | 100% test pass
FEAT-02-111 | Rate-limit analytics | P1 | Core |  | ✓ |  |  |  | 10 | Medium | Specified | Operators can inspect abuse patterns | 100% test pass
FEAT-02-112 | API compatibility matrix | P1 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Supported clients/index versions documented | 100% test pass
FEAT-02-113 | Feature flags | P1 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Risky features can be enabled/disabled safely | 100% test pass
FEAT-02-114 | Canary deployment | P1 | Core |  | ✓ |  |  |  | 16 | High | Specified | New version can receive controlled traffic | 100% test pass
FEAT-02-115 | Blue/green deployment | P1 | Core |  | ✓ |  |  |  | 16 | High | Specified | Traffic can switch between versions | 100% test pass
FEAT-02-116 | SLO/SLI definitions | P1 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Latency/availability/error SLOs documented | 100% test pass
FEAT-02-117 | Alerting policy | P1 | Core |  | ✓ |  |  |  | 14 | High | Specified | Critical failures page with actionable context | 100% test pass
FEAT-02-118 | Capacity planning | P1 | Core |  | ✓ |  |  |  | 18 | Medium | Specified | Growth thresholds and scaling actions documented | 100% test pass
FEAT-02-119 | Cost monitoring | P1 | Core |  | ✓ |  |  |  | 12 | Medium | Specified | Compute/storage/network costs attributable | 100% test pass
FEAT-02-120 | Synthetic monitoring | P1 | Core |  | ✓ |  |  |  | 12 | Low | Specified | Scheduled real-user-like queries detect regressions | 100% test pass
FEAT-02-121 | Data quality validation | P1 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | Dimension/type/range and metadata quality checked | 100% test pass
FEAT-02-122 | Embedding provenance | P1 | Core |  | ✓ |  |  |  | 16 | High | Specified | Model/version/source are tracked for every vector set | 100% test pass
FEAT-02-123 | Embedding drift detection | P1 | Core |  | ✓ |  |  |  | 22 | High | Specified | Distribution changes are detected and reported | 100% test pass
FEAT-02-124 | Model version compatibility | P1 | Core |  |  |  | ✓ |  | 18 | Critical | Specified | Queries and stored vectors use compatible model versions | 100% test pass
FEAT-02-125 | Offline evaluation pipeline | P1 | Core |  | ✓ |  |  |  | 22 | High | Specified | One command reproduces recall/latency evaluation | 100% test pass
FEAT-02-126 | Online A/B evaluation | P1 | Core |  | ✓ |  |  |  | 24 | High | Specified | Search policies can be compared safely | 100% test pass
FEAT-02-127 | Confidence/calibration dashboard | P1 | Core |  | ✓ |  |  |  | 16 | Medium | Specified | Predicted risk is compared with observed outcomes | 100% test pass
FEAT-02-128 | Adversarial vector testing | P1 | Core |  | ✓ |  |  |  | 20 | Critical | Specified | Malformed/adversarial vectors cannot crash or poison index | 100% test pass
FEAT-02-129 | Poisoning/data-integrity checks | P1 | Core |  | ✓ |  |  |  | 20 | Critical | Specified | Suspicious bulk changes are detected | 100% test pass
FEAT-02-130 | Supply-chain security | P1 | Core |  |  |  | ✓ |  | 16 | Critical | Specified | Dependencies/images are scanned and pinned | 100% test pass
FEAT-02-131 | SBOM generation | P1 | Core |  | ✓ |  |  |  | 10 | Medium | Specified | Release artifacts have SBOMs | 100% test pass
FEAT-02-132 | Secrets rotation | P1 | Core |  | ✓ |  |  |  | 12 | Critical | Specified | Secrets can rotate without downtime | 100% test pass
FEAT-02-133 | Key management | P1 | Core |  | ✓ |  |  |  | 14 | Critical | Specified | Encryption keys are managed separately and rotated | 100% test pass
FEAT-02-134 | Immutable audit logs | P1 | Core |  | ✓ |  |  |  | 14 | High | Specified | Privileged events resist alteration | 100% test pass
FEAT-02-135 | Compliance export | P1 | Core |  | ✓ |  |  |  | 14 | Medium | Specified | Required records can be exported | 100% test pass
FEAT-02-136 | Geo/region routing | P1 | Core |  | ✓ |  |  |  | 20 | High | Specified | Queries route to intended region | 100% test pass
FEAT-02-137 | Disaster recovery region | P1 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | Service can restore in alternate region | 100% test pass
FEAT-02-138 | Restore point verification | P1 | Core |  | ✓ |  |  |  | 12 | High | Specified | Backup integrity is automatically verified | 100% test pass
FEAT-02-139 | Index corruption detector | P1 | Core |  | ✓ |  |  |  | 20 | Critical | Specified | Corrupt graph/index states are detected before serving | 100% test pass
FEAT-02-140 | Online integrity checker | P1 | Core |  | ✓ |  |  |  | 16 | High | Specified | Background checks do not block reads | 100% test pass
FEAT-02-141 | Graph visualization/debugger | P1 | Core |  | ✓ |  |  |  | 20 | Medium | Specified | Developers can inspect graph/neighbor structure | 100% test pass
FEAT-02-142 | Query replay | P1 | Core |  | ✓ |  |  |  | 18 | High | Specified | Production-safe queries can be replayed offline | 100% test pass
FEAT-02-143 | Deterministic seed control | P1 | Core |  | ✓ |  |  |  | 10 | Medium | Specified | Benchmarks/builds can be reproduced | 100% test pass
FEAT-02-144 | Golden dataset regression | P1 | Core |  | ✓ |  |  |  | 16 | High | Specified | Known queries detect ranking/filter regressions | 100% test pass
FEAT-02-145 | Cross-version benchmark | P1 | Core |  | ✓ |  |  |  | 18 | Medium | Specified | New releases compare against prior baseline | 100% test pass
FEAT-02-146 | Memory fragmentation tests | P1 | Core |  | ✓ |  |  |  | 18 | High | Specified | Long-running process remains within memory envelope | 100% test pass
FEAT-02-147 | Long-duration soak test | P1 | Core |  | ✓ |  |  |  | 24 | Critical | Specified | System remains stable for extended workload | 100% test pass
FEAT-02-148 | Upgrade/downgrade test | P1 | Core |  | ✓ |  |  |  | 18 | Critical | Specified | Supported upgrades and rollback paths work | 100% test pass
FEAT-02-149 | Migration dry-run | P1 | Core |  | ✓ |  |  |  | 12 | High | Specified | Migrations can be validated before production | 100% test pass
FEAT-02-150 | User-facing error taxonomy | P1 | Core |  | ✓ |  |  |  | 10 | Low | Specified | Errors are actionable and consistent | 100% test pass
FEAT-02-151 | Search explainability panel | P1 | Core |  |  |  | ✓ |  | 16 | Medium | Specified | Users can inspect why a result/query strategy was used | 100% test pass
FEAT-02-152 | Usage quotas/billing hooks | P1 | Core |  | ✓ |  |  |  | 16 | Medium | Specified | Usage can be measured per tenant | 100% test pass

## Frontend
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-02-001 | Search UI shell | P0 | Core | 8 | Medium | Specified | All search controls work together | 100% test pass
FEAT-02-017 | HNSW build | P0 | Core | 32 | Critical | Specified | Index builds reproducibly | 100% test pass
FEAT-02-024 | Compaction/rebuild | P1 | Core | 30 | Critical | Specified | Compaction preserves correctness | 100% test pass
FEAT-02-054 | Build versions | P0 | Core | 10 | High | Specified | Every index has provenance | 100% test pass
FEAT-02-076 | Rebuild | P0 | Core | 30 | Critical | Specified | Rebuilt index matches benchmark | 100% test pass
FEAT-02-088 | Correctness suite | P0 | Core | 30 | Critical | Specified | CI blocks regressions | 100% test pass
FEAT-02-089 | Concurrency suite | P0 | Core | 28 | Critical | Specified | No data races/corruption | 100% test pass
FEAT-02-090 | Performance suite | P0 | Core | 26 | High | Specified | Results are reproducible | 100% test pass
FEAT-02-091 | Chaos suite | P1 | Core | 24 | Critical | Specified | System recovers within targets | 100% test pass
FEAT-02-109 | Circuit breakers | P1 | Core | 14 | High | Specified | Dependency failures do not cascade | 100% test pass

## Backend
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-02-002 | Vector query input | P0 | Core | 8 | Medium | Specified | Valid queries reach API correctly | 100% test pass
FEAT-02-003 | Metadata filters | P0 | Core | 14 | High | Specified | Generated filters match backend syntax | 100% test pass
FEAT-02-004 | Filter UX | P1 | Core | 16 | High | Specified | Complex filters remain understandable | 100% test pass
FEAT-02-005 | Result list | P0 | Core | 10 | Low | Specified | Results render consistently | 100% test pass
FEAT-02-006 | Pagination/Top-K | P0 | Core | 8 | Medium | Specified | Requested k is respected | 100% test pass
FEAT-02-007 | Debug mode | P1 | Core | 10 | Medium | Specified | Diagnostics match server metrics | 100% test pass
FEAT-02-008 | Large-result rendering | P1 | Core | 10 | Medium | Specified | UI remains responsive at large k | 100% test pass
FEAT-02-009 | Input hardening | P0 | Core | 8 | High | Specified | Untrusted metadata is safely rendered | 100% test pass
FEAT-02-010 | Keyboard/navigation | P1 | Core | 8 | Low | Specified | Core flow usable without pointer | 100% test pass
FEAT-02-011 | E2E search tests | P0 | Core | 18 | Medium | Specified | Critical flows pass CI | 100% test pass
FEAT-02-012 | Client telemetry | P1 | Core | 8 | Medium | Specified | Events correlate with server request IDs | 100% test pass
FEAT-02-013 | Search service | P0 | Core | 12 | High | Specified | Responsibilities are independently testable | 100% test pass
FEAT-02-014 | Search API | P0 | Core | 16 | High | Specified | Contract and validation tests pass | 100% test pass
FEAT-02-015 | Filter DSL | P0 | Core | 20 | Critical | Specified | All supported operators parse deterministically | 100% test pass
FEAT-02-016 | Query validation | P0 | Core | 12 | High | Specified | Invalid input is rejected safely | 100% test pass
FEAT-02-018 | HNSW search | P0 | Core | 32 | Critical | Specified | Top-k search returns valid candidates | 100% test pass
FEAT-02-019 | Filtered traversal | P0 | Core | 36 | Critical | Specified | Filtered results contain only valid records | 100% test pass
FEAT-02-020 | Pre/post filtering modes | P1 | Core | 20 | High | Specified | Modes are behaviorally correct | 100% test pass
FEAT-02-021 | Adaptive efSearch | P1 | Core | 24 | High | Specified | Bounded adaptive policy is deterministic | 100% test pass
FEAT-02-022 | Deletion/tombstones | P0 | Core | 24 | Critical | Specified | Deleted vectors never appear | 100% test pass
FEAT-02-023 | Updates | P0 | Core | 26 | High | Specified | Updates become query-visible consistently | 100% test pass
FEAT-02-025 | Index snapshots | P0 | Core | 24 | Critical | Specified | Reloaded index matches source behavior | 100% test pass
FEAT-02-026 | Crash recovery | P0 | Core | 24 | Critical | Specified | Crash does not corrupt index | 100% test pass
FEAT-02-027 | Read/write concurrency | P0 | Core | 36 | Critical | Specified | No races/corruption under stress | 100% test pass
FEAT-02-028 | Locking strategy | P1 | Core | 18 | High | Specified | Hot path contention measured | 100% test pass
FEAT-02-029 | Sharding | P2 | Core | 32 | High | Specified | Queries route to correct shards | 100% test pass
FEAT-02-030 | Replication | P2 | Core | 28 | Critical | Specified | Replica consistency model documented/tested | 100% test pass
FEAT-02-031 | Fan-out search | P2 | Core | 28 | High | Specified | Global top-k is correct | 100% test pass
FEAT-02-032 | Benchmark harness | P0 | Core | 24 | High | Specified | Benchmarks are reproducible | 100% test pass
FEAT-02-033 | Query planner | P1 | Core | 28 | High | Specified | Planner decisions are observable | 100% test pass
FEAT-02-034 | Tenant isolation | P0 | Core | 20 | Critical | Specified | Isolation tests pass | 100% test pass
FEAT-02-035 | Resource limits | P0 | Core | 16 | High | Specified | Abusive requests are rejected/throttled | 100% test pass
FEAT-02-036 | Property tests | P0 | Core | 24 | Critical | Specified | Property suite passes | 100% test pass
FEAT-02-037 | Fuzzing | P0 | Core | 28 | Critical | Specified | No crashes/corruption found | 100% test pass
FEAT-02-038 | Benchmark datasets | P0 | Core | 18 | Medium | Specified | Datasets are versioned and reproducible | 100% test pass
FEAT-02-039 | Filter selectivity corpus | P0 | Core | 16 | High | Specified | All selectivity bands represented | 100% test pass
FEAT-02-040 | Recall@k | P0 | Core | 24 | Critical | Specified | Recall curves generated | 100% test pass
FEAT-02-042 | Adaptive efSearch | P1 | Core | 28 | High | Specified | Policy respects recall floor | 100% test pass
FEAT-02-043 | Candidate budgeting | P1 | Core | 24 | High | Specified | Budget reduces wasted work without recall loss | 100% test pass
FEAT-02-044 | Query strategy selection | P1 | Core | 28 | High | Specified | Strategy improves benchmark envelope | 100% test pass
FEAT-02-045 | Recall-risk estimator | P2 | Core | 22 | Medium | Specified | Risk score correlates with recall misses | 100% test pass
FEAT-02-046 | Experiment tracking | P0 | Core | 12 | Medium | Specified | Any benchmark is reproducible | 100% test pass
FEAT-02-048 | Deterministic fallback | P0 | Core | 12 | Critical | Specified | System remains correct without ML | 100% test pass
FEAT-02-050 | Filterable fields | P0 | Core | 18 | Critical | Specified | All supported predicates execute correctly | 100% test pass
FEAT-02-051 | Nested metadata | P1 | Core | 12 | High | Specified | Nested behavior is documented/tested | 100% test pass
FEAT-02-052 | Vector storage | P0 | Core | 20 | High | Specified | Vectors round-trip without precision issues | 100% test pass
FEAT-02-053 | HNSW metadata | P0 | Core | 12 | Medium | Specified | Index configuration is recoverable | 100% test pass
FEAT-02-055 | Partitioning | P1 | Core | 20 | High | Specified | Partition queries remain correct | 100% test pass
FEAT-02-056 | Compaction state | P1 | Core | 12 | Medium | Specified | Background jobs are observable | 100% test pass
FEAT-02-057 | Snapshots | P0 | Core | 18 | Critical | Specified | Snapshots restore correctly | 100% test pass
FEAT-02-058 | Backup/restore | P0 | Core | 14 | Critical | Specified | Restore drill succeeds | 100% test pass
FEAT-02-059 | Encryption | P0 | Core | 12 | Critical | Specified | Sensitive data protected | 100% test pass
FEAT-02-060 | Retention/deletion | P0 | Core | 16 | High | Specified | Deleted data is not returned | 100% test pass
FEAT-02-061 | Metadata indexes | P0 | Core | 18 | High | Specified | Hot predicates meet latency targets | 100% test pass
FEAT-02-062 | Storage metrics | P1 | Core | 10 | Low | Specified | Capacity trends are visible | 100% test pass
FEAT-02-063 | ANN search | P0 | Core | 30 | Critical | Specified | Correct top-k contract | 100% test pass
FEAT-02-064 | Filtered ANN | P0 | Core | 36 | Critical | Specified | No invalid metadata results | 100% test pass
FEAT-02-065 | Exact baseline | P0 | Core | 18 | Medium | Specified | Exact results are reproducible | 100% test pass
FEAT-02-066 | Distance metrics | P0 | Core | 16 | High | Specified | Metric semantics are documented/tested | 100% test pass
FEAT-02-067 | Top-k | P0 | Core | 8 | Medium | Specified | Exactly valid k behavior | 100% test pass
FEAT-02-068 | Boolean filters | P0 | Core | 20 | Critical | Specified | Boolean semantics are deterministic | 100% test pass
FEAT-02-069 | Range filters | P0 | Core | 14 | High | Specified | Inclusive/exclusive semantics documented | 100% test pass
FEAT-02-070 | Set filters | P0 | Core | 12 | Medium | Specified | Set semantics correct | 100% test pass
FEAT-02-071 | Filter pushdown | P1 | Core | 24 | Critical | Specified | No recall violations | 100% test pass
FEAT-02-072 | Hybrid execution | P1 | Core | 28 | High | Specified | Strategy is benchmarked | 100% test pass
FEAT-02-073 | Insert | P0 | Core | 18 | High | Specified | Inserted data becomes queryable | 100% test pass
FEAT-02-074 | Update | P0 | Core | 20 | High | Specified | Old record is not returned | 100% test pass
FEAT-02-075 | Delete | P0 | Core | 18 | Critical | Specified | Deleted records never return | 100% test pass
FEAT-02-077 | Online compaction | P1 | Core | 24 | High | Specified | Compaction does not block reads | 100% test pass
FEAT-02-078 | Warm cache | P1 | Core | 14 | Medium | Specified | Cache improves repeat query latency | 100% test pass
FEAT-02-079 | Batch search | P1 | Core | 18 | High | Specified | Batch results equal individual semantics | 100% test pass
FEAT-02-080 | Parallel search | P2 | Core | 22 | High | Specified | Parallel merge is correct | 100% test pass
FEAT-02-081 | Memory budget | P0 | Core | 18 | Critical | Specified | Configured memory budget is enforced | 100% test pass
FEAT-02-082 | Crash-safe index | P0 | Core | 22 | Critical | Specified | No corrupted index loads | 100% test pass
FEAT-02-083 | Index versioning | P0 | Core | 18 | High | Specified | Compatibility rules are enforced | 100% test pass
FEAT-02-084 | Authentication | P0 | Core | 14 | Critical | Specified | Invalid credentials rejected | 100% test pass
FEAT-02-085 | Authorization | P0 | Core | 16 | Critical | Specified | Cross-tenant reads blocked | 100% test pass
FEAT-02-086 | Rate limiting | P0 | Core | 12 | High | Specified | Abusive clients are throttled | 100% test pass
FEAT-02-092 | Admin API | P1 | Core | 20 | High | Specified | Operators can safely manage index | 100% test pass
FEAT-02-093 | Health/readiness | P0 | Core | 10 | Medium | Specified | Orchestrator can detect unhealthy instances | 100% test pass
FEAT-02-094 | Metrics | P0 | Core | 16 | Medium | Specified | Critical metrics are exposed | 100% test pass
FEAT-02-095 | Tracing | P1 | Core | 16 | Medium | Specified | Slow queries are diagnosable | 100% test pass
FEAT-02-097 | CI/CD | P0 | Core | 20 | High | Specified | Required gates run on changes | 100% test pass
FEAT-02-098 | API docs | P0 | Core | 14 | Low | Specified | Examples cover supported behavior | 100% test pass
FEAT-02-099 | Operations runbook | P0 | Core | 16 | High | Specified | Operators can execute drills | 100% test pass
FEAT-02-100 | Paper/benchmark report | P2 | Core | 24 | Medium | Specified | Results reproducible by another team | 100% test pass
FEAT-02-101 | Multi-tenancy & Collections | P1 | Core | 18 | Critical | Specified | Collections are isolated and addressable | 100% test pass
FEAT-02-102 | Collection lifecycle | P1 | Core | 14 | High | Specified | Create/update/delete collection safely | 100% test pass
FEAT-02-104 | API pagination/cursors | P1 | Core | 12 | Medium | Specified | Stable cursor semantics across changing data | 100% test pass
FEAT-02-105 | Idempotent writes | P1 | Core | 12 | High | Specified | Retries do not duplicate data | 100% test pass
FEAT-02-106 | Request cancellation | P1 | Core | 10 | Medium | Specified | Cancelled queries stop consuming resources | 100% test pass
FEAT-02-107 | Timeout budgets | P1 | Core | 10 | High | Specified | Per-stage and end-to-end deadlines enforced | 100% test pass
FEAT-02-108 | Backpressure | P1 | Core | 18 | Critical | Specified | Overload is contained without cascading failure | 100% test pass
FEAT-02-110 | Load shedding | P1 | Core | 14 | High | Specified | System degrades predictably under overload | 100% test pass
FEAT-02-111 | Rate-limit analytics | P1 | Core | 10 | Medium | Specified | Operators can inspect abuse patterns | 100% test pass
FEAT-02-112 | API compatibility matrix | P1 | Core | 12 | Medium | Specified | Supported clients/index versions documented | 100% test pass
FEAT-02-113 | Feature flags | P1 | Core | 12 | Medium | Specified | Risky features can be enabled/disabled safely | 100% test pass
FEAT-02-114 | Canary deployment | P1 | Core | 16 | High | Specified | New version can receive controlled traffic | 100% test pass
FEAT-02-115 | Blue/green deployment | P1 | Core | 16 | High | Specified | Traffic can switch between versions | 100% test pass
FEAT-02-116 | SLO/SLI definitions | P1 | Core | 12 | Medium | Specified | Latency/availability/error SLOs documented | 100% test pass
FEAT-02-117 | Alerting policy | P1 | Core | 14 | High | Specified | Critical failures page with actionable context | 100% test pass
FEAT-02-118 | Capacity planning | P1 | Core | 18 | Medium | Specified | Growth thresholds and scaling actions documented | 100% test pass
FEAT-02-119 | Cost monitoring | P1 | Core | 12 | Medium | Specified | Compute/storage/network costs attributable | 100% test pass
FEAT-02-120 | Synthetic monitoring | P1 | Core | 12 | Low | Specified | Scheduled real-user-like queries detect regressions | 100% test pass
FEAT-02-121 | Data quality validation | P1 | Core | 18 | Critical | Specified | Dimension/type/range and metadata quality checked | 100% test pass
FEAT-02-122 | Embedding provenance | P1 | Core | 16 | High | Specified | Model/version/source are tracked for every vector set | 100% test pass
FEAT-02-123 | Embedding drift detection | P1 | Core | 22 | High | Specified | Distribution changes are detected and reported | 100% test pass
FEAT-02-125 | Offline evaluation pipeline | P1 | Core | 22 | High | Specified | One command reproduces recall/latency evaluation | 100% test pass
FEAT-02-126 | Online A/B evaluation | P1 | Core | 24 | High | Specified | Search policies can be compared safely | 100% test pass
FEAT-02-127 | Confidence/calibration dashboard | P1 | Core | 16 | Medium | Specified | Predicted risk is compared with observed outcomes | 100% test pass
FEAT-02-128 | Adversarial vector testing | P1 | Core | 20 | Critical | Specified | Malformed/adversarial vectors cannot crash or poison index | 100% test pass
FEAT-02-129 | Poisoning/data-integrity checks | P1 | Core | 20 | Critical | Specified | Suspicious bulk changes are detected | 100% test pass
FEAT-02-131 | SBOM generation | P1 | Core | 10 | Medium | Specified | Release artifacts have SBOMs | 100% test pass
FEAT-02-132 | Secrets rotation | P1 | Core | 12 | Critical | Specified | Secrets can rotate without downtime | 100% test pass
FEAT-02-133 | Key management | P1 | Core | 14 | Critical | Specified | Encryption keys are managed separately and rotated | 100% test pass
FEAT-02-134 | Immutable audit logs | P1 | Core | 14 | High | Specified | Privileged events resist alteration | 100% test pass
FEAT-02-135 | Compliance export | P1 | Core | 14 | Medium | Specified | Required records can be exported | 100% test pass
FEAT-02-136 | Geo/region routing | P1 | Core | 20 | High | Specified | Queries route to intended region | 100% test pass
FEAT-02-137 | Disaster recovery region | P1 | Core | 24 | Critical | Specified | Service can restore in alternate region | 100% test pass
FEAT-02-138 | Restore point verification | P1 | Core | 12 | High | Specified | Backup integrity is automatically verified | 100% test pass
FEAT-02-139 | Index corruption detector | P1 | Core | 20 | Critical | Specified | Corrupt graph/index states are detected before serving | 100% test pass
FEAT-02-140 | Online integrity checker | P1 | Core | 16 | High | Specified | Background checks do not block reads | 100% test pass
FEAT-02-141 | Graph visualization/debugger | P1 | Core | 20 | Medium | Specified | Developers can inspect graph/neighbor structure | 100% test pass
FEAT-02-142 | Query replay | P1 | Core | 18 | High | Specified | Production-safe queries can be replayed offline | 100% test pass
FEAT-02-143 | Deterministic seed control | P1 | Core | 10 | Medium | Specified | Benchmarks/builds can be reproduced | 100% test pass
FEAT-02-144 | Golden dataset regression | P1 | Core | 16 | High | Specified | Known queries detect ranking/filter regressions | 100% test pass
FEAT-02-145 | Cross-version benchmark | P1 | Core | 18 | Medium | Specified | New releases compare against prior baseline | 100% test pass
FEAT-02-146 | Memory fragmentation tests | P1 | Core | 18 | High | Specified | Long-running process remains within memory envelope | 100% test pass
FEAT-02-147 | Long-duration soak test | P1 | Core | 24 | Critical | Specified | System remains stable for extended workload | 100% test pass
FEAT-02-148 | Upgrade/downgrade test | P1 | Core | 18 | Critical | Specified | Supported upgrades and rollback paths work | 100% test pass
FEAT-02-149 | Migration dry-run | P1 | Core | 12 | High | Specified | Migrations can be validated before production | 100% test pass
FEAT-02-150 | User-facing error taxonomy | P1 | Core | 10 | Low | Specified | Errors are actionable and consistent | 100% test pass
FEAT-02-152 | Usage quotas/billing hooks | P1 | Core | 16 | Medium | Specified | Usage can be measured per tenant | 100% test pass

## Database
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-02-049 | Vector schema | P0 | Core | 12 | High | Specified | Schema supports required lifecycle | 100% test pass
FEAT-02-103 | Schema evolution | P1 | Core | 18 | High | Specified | Backward-compatible migrations are tested | 100% test pass

## AIML
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-02-041 | Latency modeling | P0 | Core | 20 | High | Specified | Latency model is reproducible | 100% test pass
FEAT-02-047 | Model/config registry | P1 | Core | 14 | Medium | Specified | Rollback works safely | 100% test pass
FEAT-02-087 | Audit trail | P1 | Core | 10 | Medium | Specified | Audit events are searchable | 100% test pass
FEAT-02-096 | Containerization | P0 | Core | 14 | Medium | Specified | Clean deployment succeeds | 100% test pass
FEAT-02-124 | Model version compatibility | P1 | Core | 18 | Critical | Specified | Queries and stored vectors use compatible model versions | 100% test pass
FEAT-02-130 | Supply-chain security | P1 | Core | 16 | Critical | Specified | Dependencies/images are scanned and pinned | 100% test pass
FEAT-02-151 | Search explainability panel | P1 | Core | 16 | Medium | Specified | Users can inspect why a result/query strategy was used | 100% test pass

## API
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target