## Feature Matrix
LSM-TREE KV ENGINE — ULTIMATE 145 FEATURE MASTER
Feature on the left; Frontend, Backend, Database and AI/ML across the top.
Feature | Frontend | Backend | Database | AI/ML | Feature ID | Implemented | Verified | Status | Evidence | Evidence Commit
KV Put API |  | ✓ |  |  | 06-001 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 2
KV Get API |  | ✓ |  |  | 06-002 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 2
KV Delete API |  | ✓ |  |  | 06-003 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 2
Batch write API |  | ✓ |  |  | 06-004 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Batch read API |  | ✓ |  |  | 06-005 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Prefix scan API |  | ✓ |  |  | 06-006 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Range scan API |  | ✓ |  |  | 06-007 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Iterator API |  | ✓ |  |  | 06-008 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 1
Snapshot API |  | ✓ |  |  | 06-009 | ✗ | ✗ | Specified
Transaction API |  | ✓ |  |  | 06-010 | ✗ | ✗ | Specified
TTL/expiration API |  | ✓ |  |  | 06-011 | ✗ | ✗ | Specified
Admin/health API |  | ✓ |  |  | 06-012 | ✗ | ✗ | Specified
Client metrics API |  | ✓ |  |  | 06-013 | ✗ | ✗ | Specified
WAL record format |  | ✓ | ✓ |  | 06-014 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 1
WAL append path |  | ✓ | ✓ |  | 06-015 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 2
WAL segment rotation |  | ✓ | ✓ |  | 06-016 | ✗ | ✗ | Specified
WAL checksums |  | ✓ | ✓ |  | 06-017 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 2
fsync policy modes |  | ✓ | ✓ |  | 06-018 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 3
group commit |  | ✓ | ✓ |  | 06-019 | ✗ | ✗ | Specified
WAL recovery/replay |  | ✓ | ✓ |  | 06-020 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 3
WAL corruption detection |  | ✓ | ✓ |  | 06-021 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 1
WAL truncation policy |  | ✓ | ✓ |  | 06-022 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 3
WAL archival |  | ✓ | ✓ |  | 06-023 | ✗ | ✗ | Specified
WAL encryption option |  | ✓ | ✓ |  | 06-024 | ✗ | ✗ | Specified
WAL metrics |  | ✓ | ✓ |  | 06-025 | ✗ | ✗ | Specified
Durability fault-injection tests |  | ✓ | ✓ |  | 06-026 | ✗ | ✗ | Specified
Skiplist memtable |  | ✓ |  |  | 06-027 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 4
Memtable lookup |  | ✓ |  |  | 06-028 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 3
Memtable ordered iterator |  | ✓ |  |  | 06-029 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 4
Memtable size thresholds |  | ✓ |  |  | 06-030 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 2
Immutable memtable transition |  | ✓ |  |  | 06-031 | ✗ | ✗ | Specified
Memtable flush scheduling |  | ✓ |  |  | 06-032 | ✗ | ✗ | Specified
Concurrent writers |  | ✓ |  |  | 06-033 | ✗ | ✗ | Specified
Write batching |  | ✓ |  |  | 06-034 | ✗ | ✗ | Specified
Write backpressure |  | ✓ |  |  | 06-035 | ✗ | ✗ | Specified
Write buffer memory accounting |  | ✓ |  |  | 06-036 | ✗ | ✗ | Specified
Memtable recovery |  | ✓ |  |  | 06-037 | ✗ | ✗ | Specified
Alternative memtable abstraction |  | ✓ |  |  | 06-038 | ✗ | ✗ | Specified
Write-path benchmarks |  | ✓ |  |  | 06-039 | ✗ | ✗ | Specified
SSTable file format |  | ✓ | ✓ |  | 06-040 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 1
Data block encoding |  | ✓ | ✓ |  | 06-041 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 2
Block checksums |  | ✓ | ✓ |  | 06-042 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 1
Sparse index |  | ✓ | ✓ |  | 06-043 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 3
Bloom filter |  | ✓ | ✓ |  | 06-044 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 1
Prefix compression |  | ✓ | ✓ |  | 06-045 | ✗ | ✗ | Specified
Block trailer format |  | ✓ | ✓ |  | 06-046 | ✗ | ✗ | Specified
File metadata |  | ✓ | ✓ |  | 06-047 | ✗ | ✗ | Specified
SSTable versioning |  | ✓ | ✓ |  | 06-048 | ✗ | ✗ | Specified
SSTable validation |  | ✓ | ✓ |  | 06-049 | ✗ | ✗ | Specified
SSTable reader |  | ✓ | ✓ |  | 06-050 | ✗ | ✗ | Specified
SSTable writer |  | ✓ | ✓ |  | 06-051 | ✗ | ✗ | Specified
SSTable corruption tests |  | ✓ | ✓ |  | 06-052 | ✗ | ✗ | Specified
Leveled compaction |  | ✓ |  |  | 06-053 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 5
Size-tiered compaction |  | ✓ |  |  | 06-054 | ✗ | ✗ | Specified
Compaction picker |  | ✓ |  |  | 06-055 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 5
Compaction scheduling |  | ✓ |  |  | 06-056 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 1
Compaction concurrency |  | ✓ |  |  | 06-057 | ✗ | ✗ | Specified
Compaction input selection |  | ✓ |  |  | 06-058 | ✗ | ✗ | Specified
Compaction output generation |  | ✓ |  |  | 06-059 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 4
Write amplification accounting |  | ✓ |  |  | 06-060 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 2
Read amplification accounting |  | ✓ |  |  | 06-061 | ✗ | ✗ | Specified
Compaction debt tracking |  | ✓ |  |  | 06-062 | ✗ | ✗ | Specified
Compaction throttling |  | ✓ |  |  | 06-063 | ✗ | ✗ | Specified
Compaction cancellation/recovery |  | ✓ |  |  | 06-064 | ✗ | ✗ | Specified
Compaction benchmark suite |  | ✓ |  |  | 06-065 | ✗ | ✗ | Specified
Point lookup path |  | ✓ |  |  | 06-066 | ✗ | ✗ | Specified
Multi-level read path |  | ✓ |  |  | 06-067 | ✗ | ✗ | Specified
Bloom filter short-circuit |  | ✓ |  |  | 06-068 | ✗ | ✗ | Specified
Index-assisted lookup |  | ✓ |  |  | 06-069 | ✗ | ✗ | Specified
Block cache lookup |  | ✓ |  |  | 06-070 | ✗ | ✗ | Specified
Iterator merge |  | ✓ |  |  | 06-071 | ✗ | ✗ | Specified
Forward iterator |  | ✓ |  |  | 06-072 | ✗ | ✗ | Specified
Reverse iterator |  | ✓ |  |  | 06-073 | ✗ | ✗ | Specified
Prefix iterator |  | ✓ |  |  | 06-074 | ✗ | ✗ | Specified
Range iterator |  | ✓ |  |  | 06-075 | ✗ | ✗ | Specified
Read batching |  | ✓ |  |  | 06-076 | ✗ | ✗ | Specified
Read amplification telemetry |  | ✓ |  |  | 06-077 | ✗ | ✗ | Specified
Read-path profiling |  | ✓ |  |  | 06-078 | ✗ | ✗ | Specified
Sequence number allocation |  | ✓ |  |  | 06-079 | ✗ | ✗ | Specified
Versioned records |  | ✓ |  |  | 06-080 | ✗ | ✗ | Specified
Snapshot creation |  | ✓ |  |  | 06-081 | ✗ | ✗ | Specified
Snapshot visibility |  | ✓ |  |  | 06-082 | ✗ | ✗ | Specified
Snapshot expiration |  | ✓ |  |  | 06-083 | ✗ | ✗ | Specified
MVCC read resolution |  | ✓ |  |  | 06-084 | ✗ | ✗ | Specified
Tombstone semantics |  | ✓ |  |  | 06-085 | ✗ | ✗ | Specified
Delete markers |  | ✓ |  |  | 06-086 | ✗ | ✗ | Specified
Atomic batch semantics |  | ✓ |  |  | 06-087 | ✗ | ✗ | Specified
Optimistic transaction API |  | ✓ |  |  | 06-088 | ✗ | ✗ | Specified
Conflict detection |  | ✓ |  |  | 06-089 | ✗ | ✗ | Specified
Transaction recovery |  | ✓ |  |  | 06-090 | ✗ | ✗ | Specified
MVCC correctness tests |  | ✓ |  |  | 06-091 | ✗ | ✗ | Specified
Block cache |  | ✓ |  |  | 06-092 | ✗ | ✗ | Specified
Cache admission policy |  | ✓ |  |  | 06-093 | ✗ | ✗ | Specified
Cache eviction policy |  | ✓ |  |  | 06-094 | ✗ | ✗ | Specified
Cache hit/miss metrics |  | ✓ |  |  | 06-095 | ✗ | ✗ | Specified
Cache memory limits |  | ✓ |  |  | 06-096 | ✗ | ✗ | Specified
Arena allocation |  | ✓ |  |  | 06-097 | ✗ | ✗ | Specified
Memory accounting |  | ✓ |  |  | 06-098 | ✗ | ✗ | Specified
Out-of-memory handling |  | ✓ |  |  | 06-099 | ✗ | ✗ | Specified
File descriptor limits |  | ✓ |  |  | 06-100 | ✗ | ✗ | Specified
Open-file cache |  | ✓ |  |  | 06-101 | ✗ | ✗ | Specified
Read-ahead policy |  | ✓ |  |  | 06-102 | ✗ | ✗ | Specified
Resource quotas |  | ✓ |  |  | 06-103 | ✗ | ✗ | Specified
Memory pressure telemetry |  | ✓ |  |  | 06-104 | ✗ | ✗ | Specified
Manifest format |  | ✓ | ✓ |  | 06-105 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 3
Version edit records |  | ✓ | ✓ |  | 06-106 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 4
Current manifest pointer |  | ✓ | ✓ |  | 06-107 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 3
Atomic metadata updates |  | ✓ | ✓ |  | 06-108 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 2
Startup recovery |  | ✓ | ✓ |  | 06-109 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 4
SSTable inventory |  | ✓ | ✓ |  | 06-110 | ✗ | ✗ | Specified
Orphan file detection |  | ✓ | ✓ |  | 06-111 | ✗ | ✗ | Specified
Manifest corruption handling |  | ✓ | ✓ |  | 06-112 | ✗ | ✗ | Specified
Metadata checksums |  | ✓ | ✓ |  | 06-113 | ✗ | ✗ | Specified
Version retention |  | ✓ | ✓ |  | 06-114 | ✗ | ✗ | Specified
Crash-safe install |  | ✓ | ✓ |  | 06-115 | ✗ | ✗ | Specified
Recovery diagnostics |  | ✓ | ✓ |  | 06-116 | ✗ | ✗ | Specified
Recovery benchmark suite |  | ✓ | ✓ |  | 06-117 | ✗ | ✗ | Specified
Input validation |  | ✓ |  |  | 06-118 | ✗ | ✗ | Specified
Key/value size limits |  | ✓ |  |  | 06-119 | ✗ | ✗ | Specified
Malformed file rejection |  | ✓ |  |  | 06-120 | ✗ | ✗ | Specified
Checksum verification |  | ✓ |  |  | 06-121 | ✗ | ✗ | Specified
Crash consistency tests |  | ✓ |  |  | 06-122 | ✗ | ✗ | Specified
Power-loss simulation |  | ✓ |  |  | 06-123 | ✗ | ✗ | Specified
Fault injection |  | ✓ |  |  | 06-124 | ✗ | ✗ | Specified
Fuzz testing |  | ✓ |  |  | 06-125 | ✗ | ✗ | Specified
Secrets/config handling |  | ✓ |  |  | 06-126 | ✗ | ✗ | Specified
At-rest encryption option |  | ✓ |  |  | 06-127 | ✗ | ✗ | Specified
Access-control hooks |  | ✓ |  |  | 06-128 | ✗ | ✗ | Specified
Audit logging |  | ✓ |  |  | 06-129 | ✗ | ✗ | Specified
Security regression suite |  | ✓ |  |  | 06-130 | ✗ | ✗ | Specified
PostgreSQL telemetry schema |  | ✓ | ✓ |  | 06-131 | ✗ | ✗ | Specified
Redis state/cache integration |  | ✓ | ✓ |  | 06-132 | ✗ | ✗ | Specified
Operation metrics |  | ✓ | ✓ |  | 06-133 | ✗ | ✗ | Specified
WAL metrics storage |  | ✓ | ✓ |  | 06-134 | ✗ | ✗ | Specified
SSTable metrics storage |  | ✓ | ✓ |  | 06-135 | ✗ | ✗ | Specified
Compaction metrics storage |  | ✓ | ✓ |  | 06-136 | ✗ | ✗ | Specified
Latency histograms |  | ✓ | ✓ |  | 06-137 | ✗ | ✗ | Specified
p50/p95/p99 dashboards | ✓ | ✓ | ✓ |  | 06-138 | ✗ | ✗ | Specified
Write amplification dashboard | ✓ | ✓ | ✓ |  | 06-139 | ✗ | ✗ | Specified
Read amplification dashboard | ✓ | ✓ | ✓ |  | 06-140 | ✗ | ✗ | Specified
Health/status endpoint | ✓ | ✓ | ✓ |  | 06-141 | ✗ | ✗ | Specified
Retention and aggregation jobs |  | ✓ | ✓ |  | 06-142 | ✗ | ✗ | Specified
Exportable benchmark results |  | ✓ | ✓ |  | 06-143 | ✗ | ✗ | Specified
Next.js application shell | ✓ | ✓ |  |  | 06-144 | ✗ | ✗ | Specified
OAuth authentication | ✓ | ✓ |  |  | 06-145 | ✗ | ✗ | Specified

## Detailed Analysis
Feature | Frontend | Backend | Database | AI/ML | Priority | Area | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Implementation Notes | Feature ID | Implemented | Verified | Status | Evidence | Evidence Commit
KV Put API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | KV Put API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-001 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 2
KV Get API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | KV Get API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-002 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 2
KV Delete API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | KV Delete API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-003 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 2
Batch write API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Batch write API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-004 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Batch read API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Batch read API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-005 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Prefix scan API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Prefix scan API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-006 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Range scan API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Range scan API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-007 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 3
Iterator API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Iterator API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-008 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs | 1
Snapshot API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Snapshot API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-009 | ✗ | ✗ | Specified
Transaction API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Transaction API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-010 | ✗ | ✗ | Specified
TTL/expiration API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | TTL/expiration API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-011 | ✗ | ✗ | Specified
Admin/health API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Admin/health API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-012 | ✗ | ✗ | Specified
Client metrics API |  | ✓ |  |  | P0 | API & Client Surface | Team owner | Core engine state | 24 | High | Client metrics API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-013 | ✗ | ✗ | Specified
WAL record format |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL record format has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-014 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 1
WAL append path |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL append path has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-015 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 2
WAL segment rotation |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL segment rotation has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-016 | ✗ | ✗ | Specified
WAL checksums |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL checksums has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-017 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 2
fsync policy modes |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | fsync policy modes has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-018 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 3
group commit |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | group commit has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-019 | ✗ | ✗ | Specified
WAL recovery/replay |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL recovery/replay has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-020 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 3
WAL corruption detection |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL corruption detection has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-021 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 1
WAL truncation policy |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL truncation policy has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-022 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs | 3
WAL archival |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL archival has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-023 | ✗ | ✗ | Specified
WAL encryption option |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 34 | Critical | WAL encryption option has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-024 | ✗ | ✗ | Specified
WAL metrics |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | WAL metrics has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-025 | ✗ | ✗ | Specified
Durability fault-injection tests |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Storage path | 24 | Critical | Durability fault-injection tests has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-026 | ✗ | ✗ | Specified
Skiplist memtable |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Skiplist memtable has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-027 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 4
Memtable lookup |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Memtable lookup has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-028 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 3
Memtable ordered iterator |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Memtable ordered iterator has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-029 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 4
Memtable size thresholds |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Memtable size thresholds has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-030 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs | 2
Immutable memtable transition |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Immutable memtable transition has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-031 | ✗ | ✗ | Specified
Memtable flush scheduling |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Memtable flush scheduling has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-032 | ✗ | ✗ | Specified
Concurrent writers |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Concurrent writers has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-033 | ✗ | ✗ | Specified
Write batching |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Write batching has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-034 | ✗ | ✗ | Specified
Write backpressure |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Write backpressure has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-035 | ✗ | ✗ | Specified
Write buffer memory accounting |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Write buffer memory accounting has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-036 | ✗ | ✗ | Specified
Memtable recovery |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Memtable recovery has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-037 | ✗ | ✗ | Specified
Alternative memtable abstraction |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Alternative memtable abstraction has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-038 | ✗ | ✗ | Specified
Write-path benchmarks |  | ✓ |  |  | P0 | Memtable & Write Path | Team owner | Write API + sequence numbers | 24 | Critical | Write-path benchmarks has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-039 | ✗ | ✗ | Specified
SSTable file format |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | SSTable file format has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-040 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 1
Data block encoding |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | Data block encoding has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-041 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 2
Block checksums |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | Block checksums has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-042 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 1
Sparse index |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | Sparse index has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-043 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 3
Bloom filter |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | Bloom filter has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-044 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs | 1
Prefix compression |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | Prefix compression has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-045 | ✗ | ✗ | Specified
Block trailer format |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | Block trailer format has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-046 | ✗ | ✗ | Specified
File metadata |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | File metadata has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-047 | ✗ | ✗ | Specified
SSTable versioning |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | SSTable versioning has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-048 | ✗ | ✗ | Specified
SSTable validation |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | SSTable validation has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-049 | ✗ | ✗ | Specified
SSTable reader |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | SSTable reader has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-050 | ✗ | ✗ | Specified
SSTable writer |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | SSTable writer has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-051 | ✗ | ✗ | Specified
SSTable corruption tests |  | ✓ | ✓ |  | P0 | SSTable & File Format | Team owner | Memtable flush | 24 | Critical | SSTable corruption tests has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-052 | ✗ | ✗ | Specified
Leveled compaction |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Leveled compaction has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-053 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 5
Size-tiered compaction |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Size-tiered compaction has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-054 | ✗ | ✗ | Specified
Compaction picker |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction picker has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-055 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 5
Compaction scheduling |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction scheduling has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-056 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 1
Compaction concurrency |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction concurrency has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-057 | ✗ | ✗ | Specified
Compaction input selection |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction input selection has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-058 | ✗ | ✗ | Specified
Compaction output generation |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction output generation has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-059 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 4
Write amplification accounting |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Write amplification accounting has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-060 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs | 2
Read amplification accounting |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Read amplification accounting has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-061 | ✗ | ✗ | Specified
Compaction debt tracking |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction debt tracking has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-062 | ✗ | ✗ | Specified
Compaction throttling |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction throttling has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-063 | ✗ | ✗ | Specified
Compaction cancellation/recovery |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction cancellation/recovery has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-064 | ✗ | ✗ | Specified
Compaction benchmark suite |  | ✓ |  |  | P0 | Compaction | Team owner | SSTable inventory + metadata | 24 | Critical | Compaction benchmark suite has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-065 | ✗ | ✗ | Specified
Point lookup path |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Point lookup path has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-066 | ✗ | ✗ | Specified
Multi-level read path |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Multi-level read path has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-067 | ✗ | ✗ | Specified
Bloom filter short-circuit |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Bloom filter short-circuit has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-068 | ✗ | ✗ | Specified
Index-assisted lookup |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Index-assisted lookup has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-069 | ✗ | ✗ | Specified
Block cache lookup |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Block cache lookup has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-070 | ✗ | ✗ | Specified
Iterator merge |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Iterator merge has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-071 | ✗ | ✗ | Specified
Forward iterator |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Forward iterator has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-072 | ✗ | ✗ | Specified
Reverse iterator |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Reverse iterator has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-073 | ✗ | ✗ | Specified
Prefix iterator |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Prefix iterator has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-074 | ✗ | ✗ | Specified
Range iterator |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Range iterator has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-075 | ✗ | ✗ | Specified
Read batching |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Read batching has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-076 | ✗ | ✗ | Specified
Read amplification telemetry |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Read amplification telemetry has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-077 | ✗ | ✗ | Specified
Read-path profiling |  | ✓ |  |  | P0 | Reads & Query Engine | Team owner | SSTables + cache | 24 | High | Read-path profiling has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-078 | ✗ | ✗ | Specified
Sequence number allocation |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Sequence number allocation has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-079 | ✗ | ✗ | Specified
Versioned records |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Versioned records has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-080 | ✗ | ✗ | Specified
Snapshot creation |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Snapshot creation has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-081 | ✗ | ✗ | Specified
Snapshot visibility |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Snapshot visibility has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-082 | ✗ | ✗ | Specified
Snapshot expiration |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Snapshot expiration has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-083 | ✗ | ✗ | Specified
MVCC read resolution |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | MVCC read resolution has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-084 | ✗ | ✗ | Specified
Tombstone semantics |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Tombstone semantics has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-085 | ✗ | ✗ | Specified
Delete markers |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Delete markers has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-086 | ✗ | ✗ | Specified
Atomic batch semantics |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Atomic batch semantics has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-087 | ✗ | ✗ | Specified
Optimistic transaction API |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Optimistic transaction API has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-088 | ✗ | ✗ | Specified
Conflict detection |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Conflict detection has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-089 | ✗ | ✗ | Specified
Transaction recovery |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | Transaction recovery has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-090 | ✗ | ✗ | Specified
MVCC correctness tests |  | ✓ |  |  | P0 | MVCC & Transactions | Team owner | Sequence numbers + memtable/SSTable | 24 | Critical | MVCC correctness tests has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-091 | ✗ | ✗ | Specified
Block cache |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Block cache has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-092 | ✗ | ✗ | Specified
Cache admission policy |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Cache admission policy has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-093 | ✗ | ✗ | Specified
Cache eviction policy |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Cache eviction policy has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-094 | ✗ | ✗ | Specified
Cache hit/miss metrics |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Cache hit/miss metrics has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-095 | ✗ | ✗ | Specified
Cache memory limits |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Cache memory limits has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-096 | ✗ | ✗ | Specified
Arena allocation |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Arena allocation has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-097 | ✗ | ✗ | Specified
Memory accounting |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Memory accounting has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-098 | ✗ | ✗ | Specified
Out-of-memory handling |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Out-of-memory handling has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-099 | ✗ | ✗ | Specified
File descriptor limits |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | File descriptor limits has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-100 | ✗ | ✗ | Specified
Open-file cache |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Open-file cache has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-101 | ✗ | ✗ | Specified
Read-ahead policy |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Read-ahead policy has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-102 | ✗ | ✗ | Specified
Resource quotas |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Resource quotas has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-103 | ✗ | ✗ | Specified
Memory pressure telemetry |  | ✓ |  |  | P1 | Cache, Memory & Resource Control | Team owner | Read path + allocator | 30 | High | Memory pressure telemetry has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-104 | ✗ | ✗ | Specified
Manifest format |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Manifest format has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-105 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 3
Version edit records |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Version edit records has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-106 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 4
Current manifest pointer |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Current manifest pointer has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-107 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 3
Atomic metadata updates |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Atomic metadata updates has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-108 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 2
Startup recovery |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Startup recovery has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-109 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs | 4
SSTable inventory |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | SSTable inventory has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-110 | ✗ | ✗ | Specified
Orphan file detection |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Orphan file detection has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-111 | ✗ | ✗ | Specified
Manifest corruption handling |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Manifest corruption handling has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-112 | ✗ | ✗ | Specified
Metadata checksums |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Metadata checksums has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-113 | ✗ | ✗ | Specified
Version retention |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Version retention has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-114 | ✗ | ✗ | Specified
Crash-safe install |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Crash-safe install has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-115 | ✗ | ✗ | Specified
Recovery diagnostics |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Recovery diagnostics has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-116 | ✗ | ✗ | Specified
Recovery benchmark suite |  | ✓ | ✓ |  | P0 | Manifest, Metadata & Recovery | Team owner | SSTable lifecycle | 24 | Critical | Recovery benchmark suite has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-117 | ✗ | ✗ | Specified
Input validation |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Input validation has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-118 | ✗ | ✗ | Specified
Key/value size limits |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Key/value size limits has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-119 | ✗ | ✗ | Specified
Malformed file rejection |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Malformed file rejection has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-120 | ✗ | ✗ | Specified
Checksum verification |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Checksum verification has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-121 | ✗ | ✗ | Specified
Crash consistency tests |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Crash consistency tests has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-122 | ✗ | ✗ | Specified
Power-loss simulation |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Power-loss simulation has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-123 | ✗ | ✗ | Specified
Fault injection |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Fault injection has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-124 | ✗ | ✗ | Specified
Fuzz testing |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Fuzz testing has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-125 | ✗ | ✗ | Specified
Secrets/config handling |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Secrets/config handling has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-126 | ✗ | ✗ | Specified
At-rest encryption option |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 34 | Critical | At-rest encryption option has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-127 | ✗ | ✗ | Specified
Access-control hooks |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Access-control hooks has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-128 | ✗ | ✗ | Specified
Audit logging |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Audit logging has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-129 | ✗ | ✗ | Specified
Security regression suite |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All persistence boundaries | 24 | Critical | Security regression suite has deterministic tests or measurable validation and documented failure behavior. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified. | 06-130 | ✗ | ✗ | Specified
PostgreSQL telemetry schema |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | PostgreSQL telemetry schema has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-131 | ✗ | ✗ | Specified
Redis state/cache integration |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 40 | High | Redis state/cache integration has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-132 | ✗ | ✗ | Specified
Operation metrics |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Operation metrics has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-133 | ✗ | ✗ | Specified
WAL metrics storage |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | WAL metrics storage has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-134 | ✗ | ✗ | Specified
SSTable metrics storage |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | SSTable metrics storage has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-135 | ✗ | ✗ | Specified
Compaction metrics storage |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Compaction metrics storage has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-136 | ✗ | ✗ | Specified
Latency histograms |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Latency histograms has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-137 | ✗ | ✗ | Specified
p50/p95/p99 dashboards | ✓ | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | p50/p95/p99 dashboards has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-138 | ✗ | ✗ | Specified
Write amplification dashboard | ✓ | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Write amplification dashboard has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-139 | ✗ | ✗ | Specified
Read amplification dashboard | ✓ | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Read amplification dashboard has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-140 | ✗ | ✗ | Specified
Health/status endpoint | ✓ | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Health/status endpoint has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-141 | ✗ | ✗ | Specified
Retention and aggregation jobs |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Retention and aggregation jobs has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-142 | ✗ | ✗ | Specified
Exportable benchmark results |  | ✓ | ✓ |  | P1 | Storage & Observability | Team owner | Engine telemetry | 30 | High | Exportable benchmark results has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-143 | ✗ | ✗ | Specified
Next.js application shell | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 30 | Medium | Next.js application shell has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-144 | ✗ | ✗ | Specified
OAuth authentication | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 30 | Medium | OAuth authentication has deterministic tests or measurable validation and documented failure behavior. | Measured operational target | Status: Specified → Scaffolded → Implemented → Verified. | 06-145 | ✗ | ✗ | Specified

## Dashboard
METRIC | VALUE
Total features | 145
Estimated engineering hours | 3678
Frontend responsibilities | 6
Backend responsibilities | 145
Database responsibilities | 52
AI/ML responsibilities | 0
P0 features | 117
P1 features | 28
P2 features | 0
API & Client Surface | 13
WAL & Durability | 13
Memtable & Write Path | 13
SSTable & File Format | 13
Compaction | 13
Reads & Query Engine | 13
MVCC & Transactions | 13
Cache, Memory & Resource Control | 13
Manifest, Metadata & Recovery | 13
Security & Reliability | 13
Storage & Observability | 13
Frontend & Visualization | 2
AI/ML Tier A | 0
AI/ML Tier B & Intelligence | 0

## Project Inventory
Repository Area | Files
backend/ | 2
frontend/ | 4
aiml/ | 2
docs/ | 13
spreadsheets/ | 1
README.md | present
backend/Cargo.toml | present
frontend/package.json | present
aiml/MODEL_CARD.md | present

## Implementation Status
IMPLEMENTATION & VERIFICATION STATUS — PROJECT 06 (06-lsm-kv-engine)
Generated At: | 2026-10-01 22:59:51
Git Commit: | e04913e
Source File: | 06_LSM_KV_ENGINE_ULTIMATE_145_Master.xlsx
METRIC | TOTAL | IMPLEMENTED (✓) | VERIFIED (✓) | % VERIFIED
All Features
P0 BURNDOWN LIST
Feature ID | Feature Name | Priority | Implemented | Verified | Status | Evidence Test / Artifact
06-001 | KV Put API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-002 | KV Get API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-003 | KV Delete API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-004 | Batch write API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-005 | Batch read API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-006 | Prefix scan API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-007 | Range scan API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-008 | Iterator API | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/engine_api_tests.rs
06-009 | Snapshot API | P0 | ✗ | ✗ | Specified
06-010 | Transaction API | P0 | ✗ | ✗ | Specified
06-011 | TTL/expiration API | P0 | ✗ | ✗ | Specified
06-012 | Admin/health API | P0 | ✗ | ✗ | Specified
06-013 | Client metrics API | P0 | ✗ | ✗ | Specified
06-014 | WAL record format | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs
06-015 | WAL append path | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs
06-016 | WAL segment rotation | P0 | ✗ | ✗ | Specified
06-017 | WAL checksums | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs
06-018 | fsync policy modes | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs
06-019 | group commit | P0 | ✗ | ✗ | Specified
06-020 | WAL recovery/replay | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs
06-021 | WAL corruption detection | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs
06-022 | WAL truncation policy | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/wal_tests.rs
06-023 | WAL archival | P0 | ✗ | ✗ | Specified
06-024 | WAL encryption option | P0 | ✗ | ✗ | Specified
06-025 | WAL metrics | P0 | ✗ | ✗ | Specified
06-026 | Durability fault-injection tests | P0 | ✗ | ✗ | Specified
06-027 | Skiplist memtable | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs
06-028 | Memtable lookup | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs
06-029 | Memtable ordered iterator | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs
06-030 | Memtable size thresholds | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/memtable_tests.rs
06-031 | Immutable memtable transition | P0 | ✗ | ✗ | Specified
06-032 | Memtable flush scheduling | P0 | ✗ | ✗ | Specified
06-033 | Concurrent writers | P0 | ✗ | ✗ | Specified
06-034 | Write batching | P0 | ✗ | ✗ | Specified
06-035 | Write backpressure | P0 | ✗ | ✗ | Specified
06-036 | Write buffer memory accounting | P0 | ✗ | ✗ | Specified
06-037 | Memtable recovery | P0 | ✗ | ✗ | Specified
06-038 | Alternative memtable abstraction | P0 | ✗ | ✗ | Specified
06-039 | Write-path benchmarks | P0 | ✗ | ✗ | Specified
06-040 | SSTable file format | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs
06-041 | Data block encoding | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs
06-042 | Block checksums | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs
06-043 | Sparse index | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs
06-044 | Bloom filter | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/sstable_tests.rs
06-045 | Prefix compression | P0 | ✗ | ✗ | Specified
06-046 | Block trailer format | P0 | ✗ | ✗ | Specified
06-047 | File metadata | P0 | ✗ | ✗ | Specified
06-048 | SSTable versioning | P0 | ✗ | ✗ | Specified
06-049 | SSTable validation | P0 | ✗ | ✗ | Specified
06-050 | SSTable reader | P0 | ✗ | ✗ | Specified
06-051 | SSTable writer | P0 | ✗ | ✗ | Specified
06-052 | SSTable corruption tests | P0 | ✗ | ✗ | Specified
06-053 | Leveled compaction | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs
06-054 | Size-tiered compaction | P0 | ✗ | ✗ | Specified
06-055 | Compaction picker | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs
06-056 | Compaction scheduling | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs
06-057 | Compaction concurrency | P0 | ✗ | ✗ | Specified
06-058 | Compaction input selection | P0 | ✗ | ✗ | Specified
06-059 | Compaction output generation | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs
06-060 | Write amplification accounting | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/compaction_tests.rs
06-061 | Read amplification accounting | P0 | ✗ | ✗ | Specified
06-062 | Compaction debt tracking | P0 | ✗ | ✗ | Specified
06-063 | Compaction throttling | P0 | ✗ | ✗ | Specified
06-064 | Compaction cancellation/recovery | P0 | ✗ | ✗ | Specified
06-065 | Compaction benchmark suite | P0 | ✗ | ✗ | Specified
06-066 | Point lookup path | P0 | ✗ | ✗ | Specified
06-067 | Multi-level read path | P0 | ✗ | ✗ | Specified
06-068 | Bloom filter short-circuit | P0 | ✗ | ✗ | Specified
06-069 | Index-assisted lookup | P0 | ✗ | ✗ | Specified
06-070 | Block cache lookup | P0 | ✗ | ✗ | Specified
06-071 | Iterator merge | P0 | ✗ | ✗ | Specified
06-072 | Forward iterator | P0 | ✗ | ✗ | Specified
06-073 | Reverse iterator | P0 | ✗ | ✗ | Specified
06-074 | Prefix iterator | P0 | ✗ | ✗ | Specified
06-075 | Range iterator | P0 | ✗ | ✗ | Specified
06-076 | Read batching | P0 | ✗ | ✗ | Specified
06-077 | Read amplification telemetry | P0 | ✗ | ✗ | Specified
06-078 | Read-path profiling | P0 | ✗ | ✗ | Specified
06-079 | Sequence number allocation | P0 | ✗ | ✗ | Specified
06-080 | Versioned records | P0 | ✗ | ✗ | Specified
06-081 | Snapshot creation | P0 | ✗ | ✗ | Specified
06-082 | Snapshot visibility | P0 | ✗ | ✗ | Specified
06-083 | Snapshot expiration | P0 | ✗ | ✗ | Specified
06-084 | MVCC read resolution | P0 | ✗ | ✗ | Specified
06-085 | Tombstone semantics | P0 | ✗ | ✗ | Specified
06-086 | Delete markers | P0 | ✗ | ✗ | Specified
06-087 | Atomic batch semantics | P0 | ✗ | ✗ | Specified
06-088 | Optimistic transaction API | P0 | ✗ | ✗ | Specified
06-089 | Conflict detection | P0 | ✗ | ✗ | Specified
06-090 | Transaction recovery | P0 | ✗ | ✗ | Specified
06-091 | MVCC correctness tests | P0 | ✗ | ✗ | Specified
06-105 | Manifest format | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs
06-106 | Version edit records | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs
06-107 | Current manifest pointer | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs
06-108 | Atomic metadata updates | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs
06-109 | Startup recovery | P0 | ✓ | ✓ | Verified | projects/06-lsm-kv-engine/backend/tests/manifest_tests.rs
06-110 | SSTable inventory | P0 | ✗ | ✗ | Specified
06-111 | Orphan file detection | P0 | ✗ | ✗ | Specified
06-112 | Manifest corruption handling | P0 | ✗ | ✗ | Specified
06-113 | Metadata checksums | P0 | ✗ | ✗ | Specified
06-114 | Version retention | P0 | ✗ | ✗ | Specified
06-115 | Crash-safe install | P0 | ✗ | ✗ | Specified
06-116 | Recovery diagnostics | P0 | ✗ | ✗ | Specified
06-117 | Recovery benchmark suite | P0 | ✗ | ✗ | Specified
06-118 | Input validation | P0 | ✗ | ✗ | Specified
06-119 | Key/value size limits | P0 | ✗ | ✗ | Specified
06-120 | Malformed file rejection | P0 | ✗ | ✗ | Specified
06-121 | Checksum verification | P0 | ✗ | ✗ | Specified
06-122 | Crash consistency tests | P0 | ✗ | ✗ | Specified
06-123 | Power-loss simulation | P0 | ✗ | ✗ | Specified
06-124 | Fault injection | P0 | ✗ | ✗ | Specified
06-125 | Fuzz testing | P0 | ✗ | ✗ | Specified
06-126 | Secrets/config handling | P0 | ✗ | ✗ | Specified
06-127 | At-rest encryption option | P0 | ✗ | ✗ | Specified
06-128 | Access-control hooks | P0 | ✗ | ✗ | Specified
06-129 | Audit logging | P0 | ✗ | ✗ | Specified
06-130 | Security regression suite | P0 | ✗ | ✗ | Specified