## Feature Matrix
MINI-QUIC — ULTIMATE 145 FEATURE MASTER
Feature is on the left; Frontend, Backend, Database and AI/ML are the responsibility columns.
Feature | Frontend | Backend | Database | AI/ML | Feature ID | Implemented | Verified | Status | Evidence | Evidence Commit
QUIC packet header encoding/decoding |  | ✓ |  |  | 05-001 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 2
Long-header packet support |  | ✓ |  |  | 05-002 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 1
Short-header packet support |  | ✓ |  |  | 05-003 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 2
Connection ID management |  | ✓ |  |  | 05-004 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 3
Packet number encoding/decoding |  | ✓ |  |  | 05-005 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 1
Frame type registry |  | ✓ |  |  | 05-006 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 1
STREAM frame encoding/decoding |  | ✓ |  |  | 05-007 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 4
ACK frame encoding/decoding |  | ✓ |  |  | 05-008 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 4
CRYPTO frame handling |  | ✓ |  |  | 05-009 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
PING/PADDING/CONNECTION_CLOSE frames |  | ✓ |  |  | 05-010 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
MAX_DATA/MAX_STREAM_DATA frames |  | ✓ |  |  | 05-011 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
MAX_STREAMS frames |  | ✓ |  |  | 05-012 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
Connection state machine |  | ✓ |  |  | 05-013 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Client/server handshake flow |  | ✓ |  |  | 05-014 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 4
X25519 key agreement |  | ✓ |  |  | 05-015 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs | 1
ChaCha20-Poly1305 packet protection |  | ✓ |  |  | 05-016 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs | 5
Key derivation and key phase |  | ✓ |  |  | 05-017 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs | 6
Initial/Handshake/Application packet spaces |  | ✓ |  |  | 05-018 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Handshake timeout handling |  | ✓ |  |  | 05-019 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Connection close/draining states |  | ✓ |  |  | 05-020 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 1
Transport parameter negotiation |  | ✓ |  |  | 05-021 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Version negotiation |  | ✓ |  |  | 05-022 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Connection establishment metrics |  | ✓ |  |  | 05-023 | ✗ | ✗ | Specified
Handshake error taxonomy |  | ✓ |  |  | 05-024 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
ACK range tracking |  | ✓ |  |  | 05-025 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Duplicate ACK handling |  | ✓ |  |  | 05-026 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Packet loss detection |  | ✓ |  |  | 05-027 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Packet-threshold loss detection |  | ✓ |  |  | 05-028 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Time-threshold loss detection |  | ✓ |  |  | 05-029 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Probe Timeout (PTO) calculation |  | ✓ |  |  | 05-030 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
PTO probe transmission |  | ✓ |  |  | 05-031 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Retransmission bookkeeping |  | ✓ |  |  | 05-032 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
RTT sampling |  | ✓ |  |  | 05-033 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Smoothed RTT estimation |  | ✓ |  |  | 05-034 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
RTT variance estimation |  | ✓ |  |  | 05-035 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
NewReno congestion control |  | ✓ |  |  | 05-036 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
CUBIC congestion control |  | ✓ |  |  | 05-037 | ✗ | ✗ | Specified
Congestion window tracking |  | ✓ |  |  | 05-038 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 3
Slow start |  | ✓ |  |  | 05-039 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Congestion avoidance |  | ✓ |  |  | 05-040 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Fast recovery |  | ✓ |  |  | 05-041 | ✗ | ✗ | Specified
ECN-ready congestion signals |  | ✓ |  |  | 05-042 | ✗ | ✗ | Specified
Packet pacing |  | ✓ |  |  | 05-043 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Pacing timer scheduling |  | ✓ |  |  | 05-044 | ✗ | ✗ | Specified
Bandwidth-delay product estimation |  | ✓ |  |  | 05-045 | ✗ | ✗ | Specified
Congestion controller interface |  | ✓ |  |  | 05-046 | ✗ | ✗ | Specified
Bidirectional stream management |  | ✓ |  |  | 05-047 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Unidirectional stream management |  | ✓ |  |  | 05-048 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Stream ID allocation |  | ✓ |  |  | 05-049 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 8
Stream receive reassembly |  | ✓ |  |  | 05-050 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 4
Stream send buffering |  | ✓ |  |  | 05-051 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Stream-level flow control |  | ✓ |  |  | 05-052 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 2
Connection-level flow control |  | ✓ |  |  | 05-053 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
MAX_DATA enforcement |  | ✓ |  |  | 05-054 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
MAX_STREAM_DATA enforcement |  | ✓ |  |  | 05-055 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
MAX_STREAMS enforcement |  | ✓ |  |  | 05-056 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 4
Stream reset handling |  | ✓ |  |  | 05-057 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Path state management |  | ✓ |  |  | 05-058 | ✗ | ✗ | Specified
Path validation |  | ✓ |  |  | 05-059 | ✗ | ✗ | Specified
Migration trigger logic |  | ✓ |  |  | 05-060 | ✗ | ✗ | Specified
Active path selection |  | ✓ |  |  | 05-061 | ✗ | ✗ | Specified
Path failure detection |  | ✓ |  |  | 05-062 | ✗ | ✗ | Specified
NAT rebinding support |  | ✓ |  |  | 05-063 | ✗ | ✗ | Specified
Deterministic network simulator |  | ✓ |  |  | 05-064 | ✗ | ✗ | Specified
Configurable latency injection |  | ✓ |  |  | 05-065 | ✗ | ✗ | Specified
Packet loss injection |  | ✓ |  |  | 05-066 | ✗ | ✗ | Specified
Packet duplication injection |  | ✓ |  |  | 05-067 | ✗ | ✗ | Specified
Packet reordering injection |  | ✓ |  |  | 05-068 | ✗ | ✗ | Specified
Tokio UDP socket runtime |  | ✓ |  |  | 05-069 | ✗ | ✗ | Specified
Zero-copy receive path |  | ✓ |  |  | 05-070 | ✗ | ✗ | Specified
Buffer pooling |  | ✓ |  |  | 05-071 | ✗ | ✗ | Specified
Packet parsing allocation budget |  | ✓ |  |  | 05-072 | ✗ | ✗ | Specified
Lock/contention profiling |  | ✓ |  |  | 05-073 | ✗ | ✗ | Specified
Async task lifecycle |  | ✓ |  |  | 05-074 | ✗ | ✗ | Specified
Timer-wheel or timer optimization |  | ✓ |  |  | 05-075 | ✗ | ✗ | Specified
Backpressure management |  | ✓ |  |  | 05-076 | ✗ | ✗ | Specified
CPU/memory telemetry |  | ✓ |  |  | 05-077 | ✗ | ✗ | Specified
High-throughput benchmark harness |  | ✓ |  |  | 05-078 | ✗ | ✗ | Specified
p50/p95/p99 latency measurement |  | ✓ |  |  | 05-079 | ✗ | ✗ | Specified
Input validation and bounds checks |  | ✓ |  |  | 05-080 | ✗ | ✗ | Specified
Malformed packet rejection |  | ✓ |  |  | 05-081 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 1
Anti-amplification controls |  | ✓ |  |  | 05-082 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Replay/duplicate protection |  | ✓ |  |  | 05-083 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Crypto nonce correctness |  | ✓ |  |  | 05-084 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 1
Key material lifecycle |  | ✓ |  |  | 05-085 | ✗ | ✗ | Specified
Secret zeroization strategy |  | ✓ |  |  | 05-086 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Resource exhaustion defenses |  | ✓ |  |  | 05-087 | ✗ | ✗ | Specified
Connection/stream quotas |  | ✓ |  |  | 05-088 | ✗ | ✗ | Specified
Timeout abuse defenses |  | ✓ |  |  | 05-089 | ✗ | ✗ | Specified
Error containment |  | ✓ |  |  | 05-090 | ✗ | ✗ | Specified
PostgreSQL connection/configuration |  | ✓ | ✓ |  | 05-091 | ✗ | ✗ | Specified
Connection/session metadata schema |  | ✓ | ✓ |  | 05-092 | ✗ | ✗ | Specified
WAL/event logging |  | ✓ | ✓ |  | 05-093 | ✗ | ✗ | Specified
Partitioned telemetry tables |  | ✓ | ✓ |  | 05-094 | ✗ | ✗ | Specified
Redis caching/state layer |  | ✓ | ✓ |  | 05-095 | ✗ | ✗ | Specified
Idempotent telemetry writes |  | ✓ | ✓ |  | 05-096 | ✗ | ✗ | Specified
Schema migration/versioning |  | ✓ | ✓ |  | 05-097 | ✗ | ✗ | Specified
Retention policies |  | ✓ | ✓ |  | 05-098 | ✗ | ✗ | Specified
Telemetry aggregation jobs |  | ✓ | ✓ |  | 05-099 | ✗ | ✗ | Specified
Queryable connection history | ✓ | ✓ | ✓ |  | 05-100 | ✗ | ✗ | Specified
Packet/loss event storage |  | ✓ | ✓ |  | 05-101 | ✗ | ✗ | Specified
Next.js application shell | ✓ | ✓ |  |  | 05-102 | ✗ | ✗ | Specified
TypeScript typed API client | ✓ | ✓ |  |  | 05-103 | ✗ | ✗ | Specified
OAuth authentication flow | ✓ | ✓ |  |  | 05-104 | ✗ | ✗ | Specified
Dashboard navigation | ✓ | ✓ |  |  | 05-105 | ✗ | ✗ | Specified
Connection/session dashboard | ✓ | ✓ |  |  | 05-106 | ✗ | ✗ | Specified
Live transport metrics cards | ✓ | ✓ | ✓ |  | 05-107 | ✗ | ✗ | Specified
RTT/loss/congestion charts | ✓ | ✓ |  |  | 05-108 | ✗ | ✗ | Specified
Packet timeline viewer | ✓ | ✓ |  |  | 05-109 | ✗ | ✗ | Specified
QLOG-style packet trace visualization | ✓ | ✓ |  |  | 05-110 | ✗ | ✗ | Specified
3D network visualization with Three.js | ✓ | ✓ |  |  | 05-111 | ✗ | ✗ | Specified
GSAP/ScrollTrigger interactions | ✓ | ✓ |  |  | 05-112 | ✗ | ✗ | Specified
RL congestion-control environment |  | ✓ |  | ✓ | 05-113 | ✗ | ✗ | Specified
RL training pipeline |  | ✓ |  | ✓ | 05-114 | ✗ | ✗ | Specified
NewReno baseline evaluation |  | ✓ |  | ✓ | 05-115 | ✗ | ✗ | Specified
CUBIC baseline evaluation |  | ✓ |  | ✓ | 05-116 | ✗ | ✗ | Specified
Reward-function design |  | ✓ |  | ✓ | 05-117 | ✗ | ✗ | Specified
Simulation dataset generation |  | ✓ | ✓ | ✓ | 05-118 | ✗ | ✗ | Specified
Feature engineering from transport telemetry |  | ✓ |  | ✓ | 05-119 | ✗ | ✗ | Specified
Policy evaluation harness |  | ✓ |  | ✓ | 05-120 | ✗ | ✗ | Specified
Offline policy validation |  | ✓ |  | ✓ | 05-121 | ✗ | ✗ | Specified
Safe policy deployment gate |  | ✓ |  | ✓ | 05-122 | ✗ | ✗ | Specified
Anomaly detection model |  | ✓ |  | ✓ | 05-123 | ✗ | ✗ | Specified
QLOG trace summarizer | ✓ | ✓ |  | ✓ | 05-124 | ✗ | ✗ | Specified
Natural-language packet-loss explainer | ✓ | ✓ |  | ✓ | 05-125 | ✗ | ✗ | Specified
Schema-constrained LLM diagnostics |  | ✓ |  | ✓ | 05-126 | ✗ | ✗ | Specified
Retrieval over protocol documentation |  | ✓ |  | ✓ | 05-127 | ✗ | ✗ | Specified
Experiment-result explanation |  | ✓ | ✓ | ✓ | 05-128 | ✗ | ✗ | Specified
Benchmark anomaly explanation |  | ✓ |  | ✓ | 05-129 | ✗ | ✗ | Specified
Root-cause hypothesis generation |  | ✓ |  | ✓ | 05-130 | ✗ | ✗ | Specified
AI-assisted troubleshooting workflow | ✓ | ✓ |  | ✓ | 05-131 | ✗ | ✗ | Specified
Confidence scoring | ✓ | ✓ |  | ✓ | 05-132 | ✗ | ✗ | Specified
Hallucination/grounding checks |  | ✓ |  | ✓ | 05-133 | ✗ | ✗ | Specified
Prompt/version registry |  | ✓ | ✓ | ✓ | 05-134 | ✗ | ✗ | Specified
Unit tests for packet/frame codecs |  | ✓ |  |  | 05-135 | ✗ | ✗ | Specified
Property-based protocol tests |  | ✓ |  |  | 05-136 | ✗ | ✗ | Specified
Integration client/server tests |  | ✓ |  |  | 05-137 | ✗ | ✗ | Specified
End-to-end simulated network tests |  | ✓ |  |  | 05-138 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/simulation_tests.rs | 2
Interoperability test corpus |  | ✓ |  |  | 05-139 | ✗ | ✗ | Specified
Deterministic replay tests |  | ✓ |  |  | 05-140 | ✗ | ✗ | Specified
Fuzz corpus minimization |  | ✓ |  |  | 05-141 | ✗ | ✗ | Specified
Benchmark CI jobs |  | ✓ |  |  | 05-142 | ✗ | ✗ | Specified
Rust formatting/linting gates |  | ✓ |  |  | 05-143 | ✗ | ✗ | Specified
Dependency/security scanning |  | ✓ |  |  | 05-144 | ✗ | ✗ | Specified
Reproducible builds |  | ✓ |  |  | 05-145 | ✗ | ✗ | Specified

## Detailed Analysis
Feature | Frontend | Backend | Database | AI/ML | Priority | Area | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Implementation Notes | Feature ID | Implemented | Verified | Status | Evidence | Evidence Commit
QUIC packet header encoding/decoding |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | QUIC packet header encoding/decoding is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-001 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 2
Long-header packet support |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | Long-header packet support is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-002 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 1
Short-header packet support |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | Short-header packet support is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-003 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 2
Connection ID management |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | Connection ID management is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-004 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 3
Packet number encoding/decoding |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | Packet number encoding/decoding is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-005 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs | 1
Frame type registry |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | Frame type registry is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-006 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 1
STREAM frame encoding/decoding |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | STREAM frame encoding/decoding is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-007 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 4
ACK frame encoding/decoding |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | ACK frame encoding/decoding is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-008 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 4
CRYPTO frame handling |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | CRYPTO frame handling is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-009 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
PING/PADDING/CONNECTION_CLOSE frames |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | PING/PADDING/CONNECTION_CLOSE frames is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-010 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
MAX_DATA/MAX_STREAM_DATA frames |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | MAX_DATA/MAX_STREAM_DATA frames is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-011 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
MAX_STREAMS frames |  | ✓ |  |  | P0 | Protocol & Wire Format | Team owner | Wire specification | 22 | Critical | MAX_STREAMS frames is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-012 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs | 2
Connection state machine |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Connection state machine is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-013 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Client/server handshake flow |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Client/server handshake flow is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-014 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 4
X25519 key agreement |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | X25519 key agreement is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-015 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs | 1
ChaCha20-Poly1305 packet protection |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | ChaCha20-Poly1305 packet protection is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-016 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs | 5
Key derivation and key phase |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Key derivation and key phase is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-017 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs | 6
Initial/Handshake/Application packet spaces |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Initial/Handshake/Application packet spaces is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-018 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Handshake timeout handling |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Handshake timeout handling is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-019 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Connection close/draining states |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Connection close/draining states is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-020 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 1
Transport parameter negotiation |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Transport parameter negotiation is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-021 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
Version negotiation |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Version negotiation is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-022 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Connection establishment metrics |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Connection establishment metrics is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-023 | ✗ | ✗ | Specified
Handshake error taxonomy |  | ✓ |  |  | P0 | Connection & Handshake | Team owner | Packet codec + crypto primitives | 22 | Critical | Handshake error taxonomy is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-024 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 3
ACK range tracking |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | ACK range tracking is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-025 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Duplicate ACK handling |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | Duplicate ACK handling is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-026 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Packet loss detection |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | Packet loss detection is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-027 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Packet-threshold loss detection |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | Packet-threshold loss detection is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-028 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Time-threshold loss detection |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | Time-threshold loss detection is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-029 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Probe Timeout (PTO) calculation |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | Probe Timeout (PTO) calculation is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-030 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
PTO probe transmission |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | PTO probe transmission is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-031 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Retransmission bookkeeping |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | Retransmission bookkeeping is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-032 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
RTT sampling |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | RTT sampling is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-033 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
Smoothed RTT estimation |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | Smoothed RTT estimation is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-034 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
RTT variance estimation |  | ✓ |  |  | P0 | Reliability & Loss Recovery | Team owner | Packet numbers + ACK state | 22 | Critical | RTT variance estimation is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-035 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
NewReno congestion control |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | NewReno congestion control is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-036 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 2
CUBIC congestion control |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | CUBIC congestion control is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-037 | ✗ | ✗ | Specified
Congestion window tracking |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Congestion window tracking is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-038 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 3
Slow start |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Slow start is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-039 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Congestion avoidance |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Congestion avoidance is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-040 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Fast recovery |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Fast recovery is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-041 | ✗ | ✗ | Specified
ECN-ready congestion signals |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | ECN-ready congestion signals is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-042 | ✗ | ✗ | Specified
Packet pacing |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Packet pacing is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-043 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs | 1
Pacing timer scheduling |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Pacing timer scheduling is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-044 | ✗ | ✗ | Specified
Bandwidth-delay product estimation |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Bandwidth-delay product estimation is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-045 | ✗ | ✗ | Specified
Congestion controller interface |  | ✓ |  |  | P0 | Congestion Control & Pacing | Team owner | RTT/loss telemetry | 22 | High | Congestion controller interface is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-046 | ✗ | ✗ | Specified
Bidirectional stream management |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Bidirectional stream management is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-047 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Unidirectional stream management |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Unidirectional stream management is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-048 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Stream ID allocation |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Stream ID allocation is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-049 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 8
Stream receive reassembly |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Stream receive reassembly is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-050 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 4
Stream send buffering |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Stream send buffering is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-051 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Stream-level flow control |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Stream-level flow control is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-052 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 2
Connection-level flow control |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Connection-level flow control is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-053 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
MAX_DATA enforcement |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | MAX_DATA enforcement is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-054 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
MAX_STREAM_DATA enforcement |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | MAX_STREAM_DATA enforcement is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-055 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
MAX_STREAMS enforcement |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | MAX_STREAMS enforcement is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-056 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 4
Stream reset handling |  | ✓ |  |  | P0 | Streams & Flow Control | Team owner | Connection state | 22 | Critical | Stream reset handling is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-057 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs | 3
Path state management |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Path state management is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-058 | ✗ | ✗ | Specified
Path validation |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Path validation is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-059 | ✗ | ✗ | Specified
Migration trigger logic |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Migration trigger logic is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-060 | ✗ | ✗ | Specified
Active path selection |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Active path selection is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-061 | ✗ | ✗ | Specified
Path failure detection |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Path failure detection is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-062 | ✗ | ✗ | Specified
NAT rebinding support |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | NAT rebinding support is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-063 | ✗ | ✗ | Specified
Deterministic network simulator |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Deterministic network simulator is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-064 | ✗ | ✗ | Specified
Configurable latency injection |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Configurable latency injection is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-065 | ✗ | ✗ | Specified
Packet loss injection |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Packet loss injection is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-066 | ✗ | ✗ | Specified
Packet duplication injection |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Packet duplication injection is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-067 | ✗ | ✗ | Specified
Packet reordering injection |  | ✓ |  |  | P1 | Connection Migration & Network Simulation | Team owner | Connection state + simulator | 28 | High | Packet reordering injection is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-068 | ✗ | ✗ | Specified
Tokio UDP socket runtime |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Tokio UDP socket runtime is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-069 | ✗ | ✗ | Specified
Zero-copy receive path |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Zero-copy receive path is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-070 | ✗ | ✗ | Specified
Buffer pooling |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Buffer pooling is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-071 | ✗ | ✗ | Specified
Packet parsing allocation budget |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Packet parsing allocation budget is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-072 | ✗ | ✗ | Specified
Lock/contention profiling |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Lock/contention profiling is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-073 | ✗ | ✗ | Specified
Async task lifecycle |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Async task lifecycle is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-074 | ✗ | ✗ | Specified
Timer-wheel or timer optimization |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Timer-wheel or timer optimization is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-075 | ✗ | ✗ | Specified
Backpressure management |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | Backpressure management is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-076 | ✗ | ✗ | Specified
CPU/memory telemetry |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | CPU/memory telemetry is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-077 | ✗ | ✗ | Specified
High-throughput benchmark harness |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | High-throughput benchmark harness is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-078 | ✗ | ✗ | Specified
p50/p95/p99 latency measurement |  | ✓ |  |  | P1 | Runtime & Performance | Team owner | Tokio runtime + core engine | 28 | High | p50/p95/p99 latency measurement is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-079 | ✗ | ✗ | Specified
Input validation and bounds checks |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Input validation and bounds checks is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-080 | ✗ | ✗ | Specified
Malformed packet rejection |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Malformed packet rejection is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-081 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 1
Anti-amplification controls |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Anti-amplification controls is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-082 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Replay/duplicate protection |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Replay/duplicate protection is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-083 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Crypto nonce correctness |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Crypto nonce correctness is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-084 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 1
Key material lifecycle |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Key material lifecycle is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-085 | ✗ | ✗ | Specified
Secret zeroization strategy |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Secret zeroization strategy is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-086 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs | 2
Resource exhaustion defenses |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Resource exhaustion defenses is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-087 | ✗ | ✗ | Specified
Connection/stream quotas |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Connection/stream quotas is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-088 | ✗ | ✗ | Specified
Timeout abuse defenses |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Timeout abuse defenses is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-089 | ✗ | ✗ | Specified
Error containment |  | ✓ |  |  | P0 | Security & Failure Handling | Team owner | Core protocol state | 22 | Critical | Error containment is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-090 | ✗ | ✗ | Specified
PostgreSQL connection/configuration |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | PostgreSQL connection/configuration is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-091 | ✗ | ✗ | Specified
Connection/session metadata schema |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Connection/session metadata schema is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-092 | ✗ | ✗ | Specified
WAL/event logging |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | WAL/event logging is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-093 | ✗ | ✗ | Specified
Partitioned telemetry tables |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Partitioned telemetry tables is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-094 | ✗ | ✗ | Specified
Redis caching/state layer |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Redis caching/state layer is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-095 | ✗ | ✗ | Specified
Idempotent telemetry writes |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Idempotent telemetry writes is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-096 | ✗ | ✗ | Specified
Schema migration/versioning |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Schema migration/versioning is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-097 | ✗ | ✗ | Specified
Retention policies |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Retention policies is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-098 | ✗ | ✗ | Specified
Telemetry aggregation jobs |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Telemetry aggregation jobs is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-099 | ✗ | ✗ | Specified
Queryable connection history | ✓ | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Queryable connection history is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-100 | ✗ | ✗ | Specified
Packet/loss event storage |  | ✓ | ✓ |  | P1 | Storage, State & Telemetry | Team owner | Runtime telemetry | 28 | High | Packet/loss event storage is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-101 | ✗ | ✗ | Specified
Next.js application shell | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | Next.js application shell is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-102 | ✗ | ✗ | Specified
TypeScript typed API client | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | TypeScript typed API client is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-103 | ✗ | ✗ | Specified
OAuth authentication flow | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | OAuth authentication flow is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-104 | ✗ | ✗ | Specified
Dashboard navigation | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | Dashboard navigation is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-105 | ✗ | ✗ | Specified
Connection/session dashboard | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | Connection/session dashboard is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-106 | ✗ | ✗ | Specified
Live transport metrics cards | ✓ | ✓ | ✓ |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | Live transport metrics cards is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-107 | ✗ | ✗ | Specified
RTT/loss/congestion charts | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | RTT/loss/congestion charts is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-108 | ✗ | ✗ | Specified
Packet timeline viewer | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | Packet timeline viewer is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-109 | ✗ | ✗ | Specified
QLOG-style packet trace visualization | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | QLOG-style packet trace visualization is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-110 | ✗ | ✗ | Specified
3D network visualization with Three.js | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | 3D network visualization with Three.js is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-111 | ✗ | ✗ | Specified
GSAP/ScrollTrigger interactions | ✓ | ✓ |  |  | P1 | Frontend & Visualization | Team owner | API + telemetry | 28 | Medium | GSAP/ScrollTrigger interactions is covered by automated tests, telemetry or validation appropriate to its interface. | Measured performance/reliability target | Status: Specified → Scaffolded → Implemented → Verified. | 05-112 | ✗ | ✗ | Specified
RL congestion-control environment |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | RL congestion-control environment is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-113 | ✗ | ✗ | Specified
RL training pipeline |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 46 | Critical | RL training pipeline is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-114 | ✗ | ✗ | Specified
NewReno baseline evaluation |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | NewReno baseline evaluation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-115 | ✗ | ✗ | Specified
CUBIC baseline evaluation |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | CUBIC baseline evaluation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-116 | ✗ | ✗ | Specified
Reward-function design |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | Reward-function design is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-117 | ✗ | ✗ | Specified
Simulation dataset generation |  | ✓ | ✓ | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | Simulation dataset generation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-118 | ✗ | ✗ | Specified
Feature engineering from transport telemetry |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | Feature engineering from transport telemetry is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-119 | ✗ | ✗ | Specified
Policy evaluation harness |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | Policy evaluation harness is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-120 | ✗ | ✗ | Specified
Offline policy validation |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | Offline policy validation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-121 | ✗ | ✗ | Specified
Safe policy deployment gate |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 36 | Critical | Safe policy deployment gate is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-122 | ✗ | ✗ | Specified
Anomaly detection model |  | ✓ |  | ✓ | P2 | AI/ML Tier A | Team owner | Simulator + telemetry dataset | 46 | Critical | Anomaly detection model is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-123 | ✗ | ✗ | Specified
QLOG trace summarizer | ✓ | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | QLOG trace summarizer is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-124 | ✗ | ✗ | Specified
Natural-language packet-loss explainer | ✓ | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Natural-language packet-loss explainer is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-125 | ✗ | ✗ | Specified
Schema-constrained LLM diagnostics |  | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Schema-constrained LLM diagnostics is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-126 | ✗ | ✗ | Specified
Retrieval over protocol documentation |  | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Retrieval over protocol documentation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-127 | ✗ | ✗ | Specified
Experiment-result explanation |  | ✓ | ✓ | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Experiment-result explanation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-128 | ✗ | ✗ | Specified
Benchmark anomaly explanation |  | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Benchmark anomaly explanation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-129 | ✗ | ✗ | Specified
Root-cause hypothesis generation |  | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Root-cause hypothesis generation is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-130 | ✗ | ✗ | Specified
AI-assisted troubleshooting workflow | ✓ | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | AI-assisted troubleshooting workflow is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-131 | ✗ | ✗ | Specified
Confidence scoring | ✓ | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Confidence scoring is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-132 | ✗ | ✗ | Specified
Hallucination/grounding checks |  | ✓ |  | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Hallucination/grounding checks is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-133 | ✗ | ✗ | Specified
Prompt/version registry |  | ✓ | ✓ | ✓ | P2 | AI/ML Tier B & Intelligence | Team owner | QLOG/telemetry + model gateway | 36 | High | Prompt/version registry is covered by automated tests, telemetry or validation appropriate to its interface. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified. | 05-134 | ✗ | ✗ | Specified
Unit tests for packet/frame codecs |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Unit tests for packet/frame codecs is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-135 | ✗ | ✗ | Specified
Property-based protocol tests |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Property-based protocol tests is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-136 | ✗ | ✗ | Specified
Integration client/server tests |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 32 | High | Integration client/server tests is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-137 | ✗ | ✗ | Specified
End-to-end simulated network tests |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | End-to-end simulated network tests is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-138 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/simulation_tests.rs | 2
Interoperability test corpus |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Interoperability test corpus is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-139 | ✗ | ✗ | Specified
Deterministic replay tests |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Deterministic replay tests is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-140 | ✗ | ✗ | Specified
Fuzz corpus minimization |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Fuzz corpus minimization is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-141 | ✗ | ✗ | Specified
Benchmark CI jobs |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Benchmark CI jobs is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-142 | ✗ | ✗ | Specified
Rust formatting/linting gates |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Rust formatting/linting gates is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-143 | ✗ | ✗ | Specified
Dependency/security scanning |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Dependency/security scanning is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-144 | ✗ | ✗ | Specified
Reproducible builds |  | ✓ |  |  | P0 | Testing, CI/CD & Deployment | Team owner | Build/test system | 22 | High | Reproducible builds is covered by automated tests, telemetry or validation appropriate to its interface. | Correctness and conformance | Status: Specified → Scaffolded → Implemented → Verified. | 05-145 | ✗ | ✗ | Specified

## Dashboard
METRIC | VALUE
Total features | 145
Estimated engineering hours | 3792
Frontend responsibilities | 16
Backend responsibilities | 145
Database responsibilities | 15
AI/ML responsibilities | 22
P0 features | 79
P1 features | 44
P2 features | 22
Protocol & Wire Format | 12
Connection & Handshake | 12
Reliability & Loss Recovery | 11
Congestion Control & Pacing | 11
Streams & Flow Control | 11
Connection Migration & Network Simulation | 11
Runtime & Performance | 11
Security & Failure Handling | 11
Storage, State & Telemetry | 11
Frontend & Visualization | 11
AI/ML Tier A | 11
AI/ML Tier B & Intelligence | 11
Testing, CI/CD & Deployment | 11

## Project Inventory
Repository area | Evidence
backend/ | 2
frontend/ | 4
database/ | 0
aiml/ | 2
docs/ | 13
benchmarks/ | 0
infra/ | 0
spreadsheets/ | 1
README.md | present
backend/Cargo.toml | present
frontend/package.json | present
aiml/MODEL_CARD.md | present

## Implementation Status
IMPLEMENTATION & VERIFICATION STATUS — PROJECT 05 (05-mini-quic)
Generated At: | 2026-10-01 21:18:35
Git Commit: | 49adde6
Source File: | 05_Mini_QUIC_ULTIMATE_145_Master.xlsx
METRIC | TOTAL | IMPLEMENTED (✓) | VERIFIED (✓) | % VERIFIED
All Features
P0 BURNDOWN LIST
Feature ID | Feature Name | Priority | Implemented | Verified | Status | Evidence Test / Artifact
05-001 | QUIC packet header encoding/decoding | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs
05-002 | Long-header packet support | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs
05-003 | Short-header packet support | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs
05-004 | Connection ID management | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs
05-005 | Packet number encoding/decoding | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/packet_codec_tests.rs
05-006 | Frame type registry | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs
05-007 | STREAM frame encoding/decoding | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs
05-008 | ACK frame encoding/decoding | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs
05-009 | CRYPTO frame handling | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs
05-010 | PING/PADDING/CONNECTION_CLOSE frames | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs
05-011 | MAX_DATA/MAX_STREAM_DATA frames | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs
05-012 | MAX_STREAMS frames | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/frame_tests.rs
05-013 | Connection state machine | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-014 | Client/server handshake flow | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-015 | X25519 key agreement | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs
05-016 | ChaCha20-Poly1305 packet protection | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs
05-017 | Key derivation and key phase | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/crypto_tests.rs
05-018 | Initial/Handshake/Application packet spaces | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-019 | Handshake timeout handling | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-020 | Connection close/draining states | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-021 | Transport parameter negotiation | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-022 | Version negotiation | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-023 | Connection establishment metrics | P0 | ✗ | ✗ | Specified
05-024 | Handshake error taxonomy | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-025 | ACK range tracking | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-026 | Duplicate ACK handling | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-027 | Packet loss detection | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-028 | Packet-threshold loss detection | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-029 | Time-threshold loss detection | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-030 | Probe Timeout (PTO) calculation | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-031 | PTO probe transmission | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-032 | Retransmission bookkeeping | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-033 | RTT sampling | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-034 | Smoothed RTT estimation | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-035 | RTT variance estimation | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-036 | NewReno congestion control | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-037 | CUBIC congestion control | P0 | ✗ | ✗ | Specified
05-038 | Congestion window tracking | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-039 | Slow start | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-040 | Congestion avoidance | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-041 | Fast recovery | P0 | ✗ | ✗ | Specified
05-042 | ECN-ready congestion signals | P0 | ✗ | ✗ | Specified
05-043 | Packet pacing | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/recovery_tests.rs
05-044 | Pacing timer scheduling | P0 | ✗ | ✗ | Specified
05-045 | Bandwidth-delay product estimation | P0 | ✗ | ✗ | Specified
05-046 | Congestion controller interface | P0 | ✗ | ✗ | Specified
05-047 | Bidirectional stream management | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-048 | Unidirectional stream management | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-049 | Stream ID allocation | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-050 | Stream receive reassembly | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-051 | Stream send buffering | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-052 | Stream-level flow control | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-053 | Connection-level flow control | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-054 | MAX_DATA enforcement | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-055 | MAX_STREAM_DATA enforcement | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-056 | MAX_STREAMS enforcement | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-057 | Stream reset handling | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/stream_flow_control_tests.rs
05-080 | Input validation and bounds checks | P0 | ✗ | ✗ | Specified
05-081 | Malformed packet rejection | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-082 | Anti-amplification controls | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-083 | Replay/duplicate protection | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-084 | Crypto nonce correctness | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-085 | Key material lifecycle | P0 | ✗ | ✗ | Specified
05-086 | Secret zeroization strategy | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/handshake_tests.rs
05-087 | Resource exhaustion defenses | P0 | ✗ | ✗ | Specified
05-088 | Connection/stream quotas | P0 | ✗ | ✗ | Specified
05-089 | Timeout abuse defenses | P0 | ✗ | ✗ | Specified
05-090 | Error containment | P0 | ✗ | ✗ | Specified
05-135 | Unit tests for packet/frame codecs | P0 | ✗ | ✗ | Specified
05-136 | Property-based protocol tests | P0 | ✗ | ✗ | Specified
05-137 | Integration client/server tests | P0 | ✗ | ✗ | Specified
05-138 | End-to-end simulated network tests | P0 | ✓ | ✓ | Verified | projects/05-mini-quic/backend/tests/simulation_tests.rs
05-139 | Interoperability test corpus | P0 | ✗ | ✗ | Specified
05-140 | Deterministic replay tests | P0 | ✗ | ✗ | Specified
05-141 | Fuzz corpus minimization | P0 | ✗ | ✗ | Specified
05-142 | Benchmark CI jobs | P0 | ✗ | ✗ | Specified
05-143 | Rust formatting/linting gates | P0 | ✗ | ✗ | Specified
05-144 | Dependency/security scanning | P0 | ✗ | ✗ | Specified
05-145 | Reproducible builds | P0 | ✗ | ✗ | Specified