## Feature Matrix
DISTRIBUTED CACHE — ULTIMATE 150 FEATURE MASTER
Feature on the left; Frontend, Backend, Database and AI/ML across the top.
Feature | Frontend | Backend | Database | AI/ML
GET cache entry |  | ✓
SET cache entry |  | ✓
DELETE cache entry |  | ✓
EXISTS lookup |  | ✓
MGET batch read |  | ✓
MSET batch write |  | ✓
TTL read |  | ✓
EXPIRE update |  | ✓
PERSIST key |  | ✓
Atomic compare-and-set |  | ✓
Key namespace support |  | ✓
Value size validation |  | ✓
Request ID propagation |  | ✓
API error model |  | ✓
Health/readiness endpoint |  | ✓
Hash-table key index |  | ✓
Segmented cache storage |  | ✓ | ✓
Entry metadata structure |  | ✓ | ✓
In-memory value storage |  | ✓ | ✓
Binary-safe values |  | ✓
LRU eviction |  | ✓
LFU eviction |  | ✓
TTL-aware eviction |  | ✓
Approximate LRU sampling |  | ✓
Hot-key tracking |  | ✓
Memory usage accounting |  | ✓
Per-key metadata overhead tracking |  | ✓ | ✓
Maximum cache size enforcement |  | ✓
Memory fragmentation metrics |  | ✓
Eviction statistics |  | ✓
Per-key TTL |  | ✓
Default TTL policy |  | ✓
TTL refresh on access |  | ✓
Lazy expiration |  | ✓
Active expiration sweeper |  | ✓
Expiration wheel/bucket |  | ✓
Expired-key cleanup |  | ✓
TTL precision policy |  | ✓
Expiration race handling |  | ✓
TTL metrics |  | ✓
Write-through mode |  | ✓
Write-back mode |  | ✓
Write coalescing |  | ✓
Dirty-entry tracking |  | ✓
Flush scheduler |  | ✓
Batch persistence |  | ✓ | ✓
Persistence retry |  | ✓ | ✓
Write failure handling |  | ✓
Crash-consistent journal |  | ✓
Recovery replay |  | ✓
Persistence lag metrics |  | ✓ | ✓
Durability configuration |  | ✓
Read-through cache |  | ✓
Negative caching |  | ✓
Read batching |  | ✓
Request coalescing |  | ✓
Hot-key fast path |  | ✓
Lock minimization |  | ✓
Shard-aware lookup |  | ✓
Read latency histogram |  | ✓
Cache-hit latency tracking |  | ✓
Cache-miss latency tracking |  | ✓
Tail-latency monitoring |  | ✓
Read-path benchmark suite |  | ✓
Cache node membership |  | ✓
Consistent-hash ring |  | ✓ | ✓
Virtual nodes |  | ✓
Key ownership mapping |  | ✓ | ✓
Replica placement |  | ✓
Primary/replica roles |  | ✓
Replication stream |  | ✓
Replica acknowledgements |  | ✓
Replica lag tracking |  | ✓
Read-from-replica policy |  | ✓
Failover handling |  | ✓
Re-replication |  | ✓
Membership convergence |  | ✓
Consistency modes |  | ✓
Split-brain protection |  | ✓
Key hashing |  | ✓
Rendezvous hashing |  | ✓
Consistent hashing |  | ✓
Shard map |  | ✓ | ✓
Shard rebalancing |  | ✓
Shard migration |  | ✓
Hot-shard detection |  | ✓
Request routing |  | ✓
Locality-aware routing |  | ✓
Cross-shard operation policy |  | ✓
Per-key locking |  | ✓
Shard-level locking |  | ✓
Optimistic concurrency |  | ✓
Atomic increment |  | ✓
Atomic delete |  | ✓
CAS version tokens |  | ✓
Single-flight request suppression |  | ✓
Deadlock avoidance |  | ✓
Race detection |  | ✓
Concurrent workload tests |  | ✓
Explicit invalidation |  | ✓
Pattern invalidation |  | ✓
Namespace invalidation |  | ✓
Event-driven invalidation |  | ✓
Dependency-aware invalidation |  | ✓
Invalidation queue |  | ✓ | ✓
Invalidation retries |  | ✓
Invalidation ordering |  | ✓ | ✓
Stale-read detection |  | ✓
Coherence metrics |  | ✓
PostgreSQL cache metadata |  | ✓ | ✓
PostgreSQL node metadata |  | ✓ | ✓
PostgreSQL policy metadata |  | ✓ | ✓
Redis hot metadata |  | ✓ | ✓
Key statistics storage |  | ✓ | ✓
Eviction history | ✓ | ✓ | ✓
Hit/miss history | ✓ | ✓ | ✓
Latency history | ✓ | ✓ | ✓
Replication history | ✓ | ✓ | ✓
Capacity history | ✓ | ✓ | ✓
Telemetry aggregation |  | ✓ | ✓
Retention policies |  | ✓ | ✓
Next.js application shell | ✓ | ✓
Authentication UI | ✓ | ✓
Cache overview dashboard | ✓ | ✓ | ✓
Key lookup console | ✓ | ✓
Set/delete playground | ✓ | ✓
Hit/miss charts | ✓ | ✓
Memory utilization dashboard | ✓ | ✓ | ✓
Eviction dashboard | ✓ | ✓ | ✓
TTL explorer | ✓ | ✓
Replication topology view | ✓ | ✓ | ✓
Shard distribution view | ✓ | ✓
Node health dashboard | ✓ | ✓ | ✓
Live telemetry refresh | ✓ | ✓ | ✓
Alert/incident panel | ✓ | ✓
Configuration console | ✓ | ✓
Input validation |  | ✓
Payload size limits |  | ✓
Authentication hooks |  | ✓
Authorization hooks |  | ✓
Tenant isolation |  | ✓
Rate limiting |  | ✓
TLS support |  | ✓
Audit logging |  | ✓
Secret/config protection |  | ✓
Abuse protection |  | ✓
Fault isolation |  | ✓
Graceful node shutdown |  | ✓
Crash recovery |  | ✓
Protocol fuzzing |  | ✓

## Detailed Analysis
Feature | Frontend | Backend | Database | AI/ML | Priority | Area | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Implementation Notes
GET cache entry |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement GET cache entry with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
SET cache entry |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement SET cache entry with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
DELETE cache entry |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement DELETE cache entry with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
EXISTS lookup |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement EXISTS lookup with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
MGET batch read |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement MGET batch read with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
MSET batch write |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement MSET batch write with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
TTL read |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement TTL read with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
EXPIRE update |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement EXPIRE update with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
PERSIST key |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement PERSIST key with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Atomic compare-and-set |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement Atomic compare-and-set with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Key namespace support |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement Key namespace support with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Value size validation |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement Value size validation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Request ID propagation |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement Request ID propagation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
API error model |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement API error model with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Health/readiness endpoint |  | ✓ |  |  | P0 | Core Cache API | Team owner | Cache engine + request lifecycle | 18 | Critical | Implement Health/readiness endpoint with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Hash-table key index |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Hash-table key index with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segmented cache storage |  | ✓ | ✓ |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Segmented cache storage with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Entry metadata structure |  | ✓ | ✓ |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Entry metadata structure with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
In-memory value storage |  | ✓ | ✓ |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement In-memory value storage with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Binary-safe values |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Binary-safe values with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
LRU eviction |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement LRU eviction with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
LFU eviction |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement LFU eviction with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
TTL-aware eviction |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement TTL-aware eviction with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Approximate LRU sampling |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Approximate LRU sampling with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Hot-key tracking |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Hot-key tracking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Memory usage accounting |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Memory usage accounting with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Per-key metadata overhead tracking |  | ✓ | ✓ |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Per-key metadata overhead tracking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Maximum cache size enforcement |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Maximum cache size enforcement with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Memory fragmentation metrics |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Memory fragmentation metrics with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Eviction statistics |  | ✓ |  |  | P0 | Cache Data Structures & Memory | Team owner | Key index + memory manager | 18 | Critical | Implement Eviction statistics with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Per-key TTL |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement Per-key TTL with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Default TTL policy |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement Default TTL policy with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
TTL refresh on access |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement TTL refresh on access with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Lazy expiration |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement Lazy expiration with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Active expiration sweeper |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement Active expiration sweeper with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Expiration wheel/bucket |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement Expiration wheel/bucket with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Expired-key cleanup |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement Expired-key cleanup with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
TTL precision policy |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement TTL precision policy with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Expiration race handling |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement Expiration race handling with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
TTL metrics |  | ✓ |  |  | P0 | TTL & Expiration | Team owner | Entry metadata + scheduler | 18 | Critical | Implement TTL metrics with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Write-through mode |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Write-through mode with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Write-back mode |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Write-back mode with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Write coalescing |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Write coalescing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Dirty-entry tracking |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Dirty-entry tracking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Flush scheduler |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Flush scheduler with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Batch persistence |  | ✓ | ✓ |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Batch persistence with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Persistence retry |  | ✓ | ✓ |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Persistence retry with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Write failure handling |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Write failure handling with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Crash-consistent journal |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Crash-consistent journal with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Recovery replay |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 28 | Critical | Implement Recovery replay with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Persistence lag metrics |  | ✓ | ✓ |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Persistence lag metrics with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Durability configuration |  | ✓ |  |  | P0 | Write Path & Persistence | Team owner | Write path + persistence layer | 18 | Critical | Implement Durability configuration with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Read-through cache |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Read-through cache with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Negative caching |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Negative caching with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Read batching |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Read batching with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Request coalescing |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Request coalescing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Hot-key fast path |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Hot-key fast path with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Lock minimization |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Lock minimization with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Shard-aware lookup |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Shard-aware lookup with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Read latency histogram |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Read latency histogram with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Cache-hit latency tracking |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Cache-hit latency tracking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Cache-miss latency tracking |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Cache-miss latency tracking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Tail-latency monitoring |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 18 | Critical | Implement Tail-latency monitoring with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Read-path benchmark suite |  | ✓ |  |  | P0 | Read Path & Performance | Team owner | Lookup path + metrics | 28 | Critical | Implement Read-path benchmark suite with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Cache node membership |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Cache node membership with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consistent-hash ring |  | ✓ | ✓ |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Consistent-hash ring with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Virtual nodes |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Virtual nodes with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Key ownership mapping |  | ✓ | ✓ |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Key ownership mapping with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replica placement |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Replica placement with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Primary/replica roles |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Primary/replica roles with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replication stream |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 28 | Critical | Implement Replication stream with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replica acknowledgements |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Replica acknowledgements with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replica lag tracking |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Replica lag tracking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Read-from-replica policy |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Read-from-replica policy with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Failover handling |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Failover handling with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Re-replication |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 28 | Critical | Implement Re-replication with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Membership convergence |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Membership convergence with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consistency modes |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Consistency modes with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Split-brain protection |  | ✓ |  |  | P0 | Distributed Consistency & Replication | Team owner | Node membership + routing | 18 | Critical | Implement Split-brain protection with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Key hashing |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Key hashing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Rendezvous hashing |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Rendezvous hashing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consistent hashing |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Consistent hashing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Shard map |  | ✓ | ✓ |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Shard map with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Shard rebalancing |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 28 | Critical | Implement Shard rebalancing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Shard migration |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Shard migration with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Hot-shard detection |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Hot-shard detection with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Request routing |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Request routing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Locality-aware routing |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Locality-aware routing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Cross-shard operation policy |  | ✓ |  |  | P0 | Sharding & Routing | Team owner | Hash/routing map | 18 | Critical | Implement Cross-shard operation policy with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Per-key locking |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Per-key locking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Shard-level locking |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Shard-level locking with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Optimistic concurrency |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Optimistic concurrency with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Atomic increment |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Atomic increment with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Atomic delete |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Atomic delete with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
CAS version tokens |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement CAS version tokens with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Single-flight request suppression |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Single-flight request suppression with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Deadlock avoidance |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Deadlock avoidance with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Race detection |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Race detection with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Concurrent workload tests |  | ✓ |  |  | P0 | Concurrency & Coordination | Team owner | Shared cache state | 18 | Critical | Implement Concurrent workload tests with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Explicit invalidation |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Explicit invalidation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Pattern invalidation |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Pattern invalidation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Namespace invalidation |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Namespace invalidation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Event-driven invalidation |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Event-driven invalidation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Dependency-aware invalidation |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Dependency-aware invalidation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Invalidation queue |  | ✓ | ✓ |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Invalidation queue with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Invalidation retries |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Invalidation retries with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Invalidation ordering |  | ✓ | ✓ |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Invalidation ordering with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Stale-read detection |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Stale-read detection with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Coherence metrics |  | ✓ |  |  | P1 | Cache Invalidation & Coherence | Team owner | Key metadata + invalidation stream | 26 | High | Implement Coherence metrics with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
PostgreSQL cache metadata |  | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement PostgreSQL cache metadata with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
PostgreSQL node metadata |  | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement PostgreSQL node metadata with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
PostgreSQL policy metadata |  | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement PostgreSQL policy metadata with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Redis hot metadata |  | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Redis hot metadata with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Key statistics storage |  | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Key statistics storage with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Eviction history | ✓ | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Eviction history with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Hit/miss history | ✓ | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Hit/miss history with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Latency history | ✓ | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Latency history with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Replication history | ✓ | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 36 | High | Implement Replication history with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Capacity history | ✓ | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Capacity history with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Telemetry aggregation |  | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Telemetry aggregation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Retention policies |  | ✓ | ✓ |  | P1 | Storage, Metadata & Telemetry | Team owner | Runtime telemetry | 26 | High | Implement Retention policies with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Next.js application shell | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Next.js application shell with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Authentication UI | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Authentication UI with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Cache overview dashboard | ✓ | ✓ | ✓ |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Cache overview dashboard with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Key lookup console | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Key lookup console with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Set/delete playground | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Set/delete playground with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Hit/miss charts | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Hit/miss charts with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Memory utilization dashboard | ✓ | ✓ | ✓ |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Memory utilization dashboard with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Eviction dashboard | ✓ | ✓ | ✓ |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Eviction dashboard with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
TTL explorer | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement TTL explorer with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Replication topology view | ✓ | ✓ | ✓ |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 36 | High | Implement Replication topology view with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Shard distribution view | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Shard distribution view with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Node health dashboard | ✓ | ✓ | ✓ |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Node health dashboard with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Live telemetry refresh | ✓ | ✓ | ✓ |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Live telemetry refresh with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Alert/incident panel | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Alert/incident panel with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Configuration console | ✓ | ✓ |  |  | P1 | Frontend Dashboard & UX | Team owner | Backend APIs + telemetry | 26 | High | Implement Configuration console with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Measured latency/throughput/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Input validation |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Input validation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Payload size limits |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Payload size limits with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Authentication hooks |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Authentication hooks with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Authorization hooks |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Authorization hooks with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Tenant isolation |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Tenant isolation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Rate limiting |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Rate limiting with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
TLS support |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement TLS support with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Audit logging |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Audit logging with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Secret/config protection |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Secret/config protection with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Abuse protection |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Abuse protection with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Fault isolation |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Fault isolation with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Graceful node shutdown |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Graceful node shutdown with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Crash recovery |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 28 | Critical | Implement Crash recovery with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Protocol fuzzing |  | ✓ |  |  | P0 | Security & Reliability | Team owner | All externally reachable surfaces | 18 | Critical | Implement Protocol fuzzing with typed interfaces, deterministic tests, metrics and failure handling appropriate to the component. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.

## Dashboard
METRIC | VALUE
Total features | 150
Estimated engineering hours | 3076
Frontend responsibilities | 20
Backend responsibilities | 150
Database responsibilities | 30
AI/ML responsibilities | 0
P0 features | 113
P1 features | 37
P2 features | 0
Core Cache API | 15
Cache Data Structures & Memory | 15
TTL & Expiration | 10
Write Path & Persistence | 12
Read Path & Performance | 12
Distributed Consistency & Replication | 15
Sharding & Routing | 10
Concurrency & Coordination | 10
Cache Invalidation & Coherence | 10
Storage, Metadata & Telemetry | 12
Frontend Dashboard & UX | 15
Security & Reliability | 14
Testing, Benchmarking & Deployment | 0
AI/ML & Intelligent Cache | 0

## Project Inventory
Repository Area | Files / Evidence
backend/ | 2
frontend/ | 4
aiml/ | 2
docs/ | 13
spreadsheets/ | 1
README.md | present
backend/go.mod | present
frontend/package.json | present
aiml/MODEL_CARD.md | present
spreadsheets/distributed-cache-spec.xlsx | present