## Feature Matrix
DISTRIBUTED PUBSUB BROKER — ULTIMATE 145 FEATURE MASTER
Feature on the left; Frontend, Backend, Database and AI/ML across the top.
Feature | Frontend | Backend | Database | AI/ML
Publish API |  | ✓
Fetch API |  | ✓
Subscribe API |  | ✓
Unsubscribe API |  | ✓
Topic creation API |  | ✓
Topic deletion API |  | ✓
Partition metadata API |  | ✓
Consumer-group API |  | ✓
Offset commit API |  | ✓
Acknowledgement API |  | ✓
Redelivery API |  | ✓
Health/readiness API |  | ✓
Admin/telemetry API |  | ✓
Topic metadata model |  | ✓ | ✓
Partition creation |  | ✓
Partition assignment |  | ✓
Partition routing by key |  | ✓
Round-robin routing |  | ✓
Partition count validation |  | ✓
Partition leader metadata |  | ✓ | ✓
Partition replica metadata |  | ✓ | ✓
Partition availability state |  | ✓ | ✓
Partition-level metrics |  | ✓ | ✓
Hot-partition detection |  | ✓
Partition rebalance planning |  | ✓
Partition topology validation |  | ✓
Append-only log format |  | ✓
Segment creation |  | ✓
Segment rolling |  | ✓
Segment index |  | ✓
Sparse index lookup |  | ✓
Record offsets |  | ✓ | ✓
Record timestamps |  | ✓
Record checksums |  | ✓
Segment metadata |  | ✓ | ✓
Segment recovery |  | ✓
Segment corruption detection |  | ✓
Segment deletion |  | ✓
Log append benchmarks |  | ✓
WAL record encoding |  | ✓
WAL append path |  | ✓
WAL segment rotation |  | ✓
WAL checksum verification |  | ✓
Fsync policy |  | ✓
Group commit |  | ✓
WAL replay |  | ✓
Crash recovery |  | ✓
Partial-write recovery |  | ✓
Durability fault injection |  | ✓
WAL retention |  | ✓
WAL metrics |  | ✓ | ✓
Durability verification suite |  | ✓
Replica state machine |  | ✓ | ✓
Leader election |  | ✓
Follower replication |  | ✓
Replication offsets |  | ✓ | ✓
Quorum acknowledgement |  | ✓
Term/epoch tracking |  | ✓
Heartbeat handling |  | ✓
Replica lag detection |  | ✓
Replica catch-up |  | ✓
Leader failover |  | ✓
Replication conflict handling |  | ✓
Replica recovery |  | ✓
Replication benchmark suite |  | ✓
Producer identity |  | ✓
Idempotent producer IDs |  | ✓
Sequence numbers |  | ✓
Duplicate publish detection |  | ✓
Producer session state |  | ✓
Batch publishing |  | ✓
Publish acknowledgements |  | ✓
Publish timeout handling |  | ✓
Retry-safe publishing |  | ✓
Producer backpressure |  | ✓
Producer metrics |  | ✓
Producer error classification |  | ✓
Producer correctness tests |  | ✓
Consumer group registry |  | ✓
Consumer membership |  | ✓
Partition ownership |  | ✓
Consumer heartbeats |  | ✓
Session timeout |  | ✓
Cooperative rebalancing |  | ✓
Incremental partition assignment |  | ✓
Assignment generation |  | ✓
Consumer join/leave handling |  | ✓
Stale member detection |  | ✓
Rebalance recovery |  | ✓
Consumer lag tracking |  | ✓
Rebalancing benchmark suite |  | ✓
Offset storage |  | ✓ | ✓
Offset validation |  | ✓ | ✓
Committed offset lookup |  | ✓ | ✓
Offset commit batching |  | ✓ | ✓
ACK state machine |  | ✓ | ✓
ACK timeout |  | ✓
Redelivery queue |  | ✓
Retry counters |  | ✓
Retry backoff |  | ✓
Dead-letter routing |  | ✓
At-least-once delivery semantics |  | ✓
Redelivery metrics |  | ✓ | ✓
Delivery-state recovery |  | ✓ | ✓
Time-based retention |  | ✓
Size-based retention |  | ✓
Segment compaction |  | ✓
Compaction scheduling |  | ✓
Safe segment deletion |  | ✓
Retention policy validation |  | ✓
Ingress rate limiting |  | ✓
Queue depth limits |  | ✓
Producer backpressure |  | ✓
Consumer backpressure |  | ✓
Load shedding policy |  | ✓
Backpressure recovery |  | ✓
Retention/compaction metrics |  | ✓ | ✓
PostgreSQL topic metadata |  | ✓ | ✓
PostgreSQL consumer metadata |  | ✓ | ✓
PostgreSQL offset metadata |  | ✓ | ✓
Redis hot state |  | ✓ | ✓
Redis membership cache |  | ✓ | ✓
Partition telemetry storage |  | ✓ | ✓
Consumer lag history | ✓ | ✓ | ✓
Replication lag history | ✓ | ✓ | ✓
Publish/consume latency history | ✓ | ✓ | ✓
Retention job state |  | ✓ | ✓
Benchmark result storage |  | ✓ | ✓
Telemetry aggregation |  | ✓ | ✓
Data retention policies |  | ✓ | ✓
Next.js application shell |  | ✓
OAuth authentication |  | ✓
Broker overview dashboard |  | ✓
Topic browser |  | ✓
Partition topology view |  | ✓
Consumer-group dashboard |  | ✓
Consumer lag visualization |  | ✓
Replication health view |  | ✓
Input validation |  | ✓ | ✓ | ✓
Payload size limits |  | ✓ | ✓ | ✓
Authentication hooks |  | ✓ | ✓ | ✓
Authorization hooks |  | ✓ | ✓ | ✓
Tenant isolation |  | ✓ | ✓ | ✓
TLS configuration |  | ✓ | ✓ | ✓
Audit logging |  | ✓ | ✓ | ✓

## Detailed Analysis
Feature | Frontend | Backend | Database | AI/ML | Priority | Area | Owner | Dependencies | Est. Hours | Risk | Acceptance Criteria | KPI / Target | Implementation Notes
Publish API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Publish API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Fetch API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Fetch API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Subscribe API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Subscribe API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Unsubscribe API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Unsubscribe API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Topic creation API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Topic creation API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Topic deletion API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Topic deletion API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition metadata API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Partition metadata API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer-group API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Consumer-group API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Offset commit API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Offset commit API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Acknowledgement API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Acknowledgement API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Redelivery API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Redelivery API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Health/readiness API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Health/readiness API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Admin/telemetry API |  | ✓ |  |  | P0 | Client & API Surface | Team owner | Core broker state + protocol | 22 | Critical | Admin/telemetry API is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Topic metadata model |  | ✓ | ✓ |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Topic metadata model is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition creation |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition creation is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition assignment |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition assignment is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition routing by key |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition routing by key is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Round-robin routing |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Round-robin routing is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition count validation |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition count validation is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition leader metadata |  | ✓ | ✓ |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition leader metadata is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition replica metadata |  | ✓ | ✓ |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition replica metadata is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition availability state |  | ✓ | ✓ |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition availability state is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition-level metrics |  | ✓ | ✓ |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition-level metrics is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Hot-partition detection |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Hot-partition detection is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition rebalance planning |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition rebalance planning is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition topology validation |  | ✓ |  |  | P0 | Topics & Partitioning | Team owner | Topic registry + partition map | 22 | Critical | Partition topology validation is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Append-only log format |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Append-only log format is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segment creation |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Segment creation is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segment rolling |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Segment rolling is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segment index |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Segment index is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Sparse index lookup |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Sparse index lookup is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Record offsets |  | ✓ | ✓ |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Record offsets is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Record timestamps |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Record timestamps is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Record checksums |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Record checksums is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segment metadata |  | ✓ | ✓ |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Segment metadata is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segment recovery |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 32 | Critical | Segment recovery is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segment corruption detection |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Segment corruption detection is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Segment deletion |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Segment deletion is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Log append benchmarks |  | ✓ |  |  | P0 | Append-Only Log & Segments | Team owner | Partition state | 22 | Critical | Log append benchmarks is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
WAL record encoding |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | WAL record encoding is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
WAL append path |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | WAL append path is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
WAL segment rotation |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | WAL segment rotation is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
WAL checksum verification |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | WAL checksum verification is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Fsync policy |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | Fsync policy is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Group commit |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | Group commit is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
WAL replay |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | WAL replay is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Crash recovery |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 32 | Critical | Crash recovery is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partial-write recovery |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 32 | Critical | Partial-write recovery is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Durability fault injection |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | Durability fault injection is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
WAL retention |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | WAL retention is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
WAL metrics |  | ✓ | ✓ |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | WAL metrics is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Durability verification suite |  | ✓ |  |  | P0 | WAL & Durability | Team owner | Append path | 22 | Critical | Durability verification suite is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replica state machine |  | ✓ | ✓ |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Replica state machine is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Leader election |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 32 | Critical | Leader election is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Follower replication |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Follower replication is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replication offsets |  | ✓ | ✓ |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Replication offsets is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Quorum acknowledgement |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Quorum acknowledgement is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Term/epoch tracking |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Term/epoch tracking is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Heartbeat handling |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Heartbeat handling is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replica lag detection |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Replica lag detection is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replica catch-up |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Replica catch-up is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Leader failover |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Leader failover is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replication conflict handling |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Replication conflict handling is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replica recovery |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 32 | Critical | Replica recovery is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replication benchmark suite |  | ✓ |  |  | P0 | Replication & Raft-Lite | Team owner | Partition log + WAL | 22 | Critical | Replication benchmark suite is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Producer identity |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Producer identity is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Idempotent producer IDs |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Idempotent producer IDs is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Sequence numbers |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Sequence numbers is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Duplicate publish detection |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Duplicate publish detection is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Producer session state |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Producer session state is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Batch publishing |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Batch publishing is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Publish acknowledgements |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Publish acknowledgements is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Publish timeout handling |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Publish timeout handling is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Retry-safe publishing |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Retry-safe publishing is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Producer backpressure |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Producer backpressure is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Producer metrics |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Producer metrics is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Producer error classification |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Producer error classification is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Producer correctness tests |  | ✓ |  |  | P0 | Producer Semantics | Team owner | Topic/partition routing | 22 | Critical | Producer correctness tests is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer group registry |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Consumer group registry is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer membership |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Consumer membership is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition ownership |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Partition ownership is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer heartbeats |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Consumer heartbeats is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Session timeout |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Session timeout is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Cooperative rebalancing |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Cooperative rebalancing is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Incremental partition assignment |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Incremental partition assignment is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Assignment generation |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Assignment generation is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer join/leave handling |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Consumer join/leave handling is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Stale member detection |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Stale member detection is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Rebalance recovery |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 32 | Critical | Rebalance recovery is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer lag tracking |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Consumer lag tracking is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Rebalancing benchmark suite |  | ✓ |  |  | P0 | Consumer Groups & Rebalancing | Team owner | Group registry + partition map | 22 | Critical | Rebalancing benchmark suite is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Offset storage |  | ✓ | ✓ |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Offset storage is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Offset validation |  | ✓ | ✓ |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Offset validation is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Committed offset lookup |  | ✓ | ✓ |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Committed offset lookup is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Offset commit batching |  | ✓ | ✓ |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Offset commit batching is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
ACK state machine |  | ✓ | ✓ |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | ACK state machine is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
ACK timeout |  | ✓ |  |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | ACK timeout is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Redelivery queue |  | ✓ |  |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Redelivery queue is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Retry counters |  | ✓ |  |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Retry counters is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Retry backoff |  | ✓ |  |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Retry backoff is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Dead-letter routing |  | ✓ |  |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Dead-letter routing is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
At-least-once delivery semantics |  | ✓ |  |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | At-least-once delivery semantics is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Redelivery metrics |  | ✓ | ✓ |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 22 | Critical | Redelivery metrics is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Delivery-state recovery |  | ✓ | ✓ |  | P0 | Offsets, ACK & Redelivery | Team owner | Consumer group state | 32 | Critical | Delivery-state recovery is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Time-based retention |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Time-based retention is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Size-based retention |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Size-based retention is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Segment compaction |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 40 | High | Segment compaction is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Compaction scheduling |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 40 | High | Compaction scheduling is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Safe segment deletion |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Safe segment deletion is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Retention policy validation |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Retention policy validation is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Ingress rate limiting |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Ingress rate limiting is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Queue depth limits |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Queue depth limits is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Producer backpressure |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Producer backpressure is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Consumer backpressure |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Consumer backpressure is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Load shedding policy |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 30 | High | Load shedding policy is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Backpressure recovery |  | ✓ |  |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 40 | High | Backpressure recovery is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Retention/compaction metrics |  | ✓ | ✓ |  | P1 | Retention, Compaction & Backpressure | Team owner | Log segments + runtime queues | 40 | High | Retention/compaction metrics is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
PostgreSQL topic metadata |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | PostgreSQL topic metadata is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
PostgreSQL consumer metadata |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | PostgreSQL consumer metadata is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
PostgreSQL offset metadata |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | PostgreSQL offset metadata is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Redis hot state |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Redis hot state is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Redis membership cache |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Redis membership cache is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Partition telemetry storage |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Partition telemetry storage is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Consumer lag history | ✓ | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Consumer lag history is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Replication lag history | ✓ | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Replication lag history is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Publish/consume latency history | ✓ | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Publish/consume latency history is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Retention job state |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Retention job state is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Benchmark result storage |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Benchmark result storage is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Telemetry aggregation |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Telemetry aggregation is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Data retention policies |  | ✓ | ✓ |  | P1 | Storage, Database & Telemetry | Team owner | Broker telemetry | 30 | High | Data retention policies is covered by deterministic tests, recovery checks or measurable operational validation. | Measured throughput/latency/reliability | Status: Specified → Scaffolded → Implemented → Verified.
Next.js application shell |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | Next.js application shell is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
OAuth authentication |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | OAuth authentication is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Broker overview dashboard |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | Broker overview dashboard is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Topic browser |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | Topic browser is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Partition topology view |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | Partition topology view is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer-group dashboard |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | Consumer-group dashboard is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Consumer lag visualization |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | Consumer lag visualization is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Replication health view |  | ✓ |  |  | P0 | Security, Testing & Deployment | Team owner | All externally reachable components | 22 | Critical | Replication health view is covered by deterministic tests, recovery checks or measurable operational validation. | Correctness/conformance | Status: Specified → Scaffolded → Implemented → Verified.
Input validation |  | ✓ | ✓ | ✓ | P2 | AI/ML & Intelligent Operations | Team owner | Telemetry + benchmark corpus | 38 | Medium-High | Input validation is covered by deterministic tests, recovery checks or measurable operational validation. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified.
Payload size limits |  | ✓ | ✓ | ✓ | P2 | AI/ML & Intelligent Operations | Team owner | Telemetry + benchmark corpus | 38 | Medium-High | Payload size limits is covered by deterministic tests, recovery checks or measurable operational validation. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified.
Authentication hooks |  | ✓ | ✓ | ✓ | P2 | AI/ML & Intelligent Operations | Team owner | Telemetry + benchmark corpus | 38 | Medium-High | Authentication hooks is covered by deterministic tests, recovery checks or measurable operational validation. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified.
Authorization hooks |  | ✓ | ✓ | ✓ | P2 | AI/ML & Intelligent Operations | Team owner | Telemetry + benchmark corpus | 38 | Medium-High | Authorization hooks is covered by deterministic tests, recovery checks or measurable operational validation. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified.
Tenant isolation |  | ✓ | ✓ | ✓ | P2 | AI/ML & Intelligent Operations | Team owner | Telemetry + benchmark corpus | 38 | Medium-High | Tenant isolation is covered by deterministic tests, recovery checks or measurable operational validation. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified.
TLS configuration |  | ✓ | ✓ | ✓ | P2 | AI/ML & Intelligent Operations | Team owner | Telemetry + benchmark corpus | 38 | Medium-High | TLS configuration is covered by deterministic tests, recovery checks or measurable operational validation. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified.
Audit logging |  | ✓ | ✓ | ✓ | P2 | AI/ML & Intelligent Operations | Team owner | Telemetry + benchmark corpus | 38 | Medium-High | Audit logging is covered by deterministic tests, recovery checks or measurable operational validation. | Validated improvement over deterministic baseline | Status: Specified → Scaffolded → Implemented → Verified.

## Dashboard
METRIC | VALUE
Total features | 145
Estimated engineering hours | 3620
Frontend responsibilities | 3
Backend responsibilities | 145
Database responsibilities | 38
AI/ML responsibilities | 7
P0 features | 112
P1 features | 26
P2 features | 7
Client & API Surface | 13
Topics & Partitioning | 13
Append-Only Log & Segments | 13
WAL & Durability | 13
Replication & Raft-Lite | 13
Producer Semantics | 13
Consumer Groups & Rebalancing | 13
Offsets, ACK & Redelivery | 13
Retention, Compaction & Backpressure | 13
Storage, Database & Telemetry | 13
Frontend & 3D Dashboard | 0
Security, Testing & Deployment | 8
AI/ML & Intelligent Operations | 7

## Project Inventory
Repository Area | Files
backend/ | 2
frontend/ | 4
aiml/ | 2
docs/ | 13
spreadsheets/ | 1
README.md | present
backend/Cargo.toml | present
frontend/package.json | present
aiml/MODEL_CARD.md | present