## Dashboard
PROJECT DASHBOARD — 01 ROLLBACK-NETCODE-SERVER
System Metric | Count / Value | Formula Reference
Total Features |  | COUNTA
Verified Features |  | COUNTIF Verified
Implemented Features |  | COUNTIF Implemented
Specified Features |  | COUNTIF Specified
P0 Features |  | COUNTIF P0
P1 Features |  | COUNTIF P1
P2 Features |  | COUNTIF P2
Total Estimated Effort (Hours) |  | SUM Hours

## Feature Matrix
ID | Feature | Priority | Area | Frontend | Backend | Database | AI/ML | API | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-01-001 | App shell & routing | P0 | Architecture | ✓ |  |  |  |  | 8 | Medium | Verified | All primary screens route correctly | 0 broken routes
FEAT-01-002 | State management | P0 | Architecture | ✓ |  |  |  |  | 8 | High | Verified | State transitions are deterministic/testable | 0 state-desync UI bugs
FEAT-01-003 | Connection setup | P0 | UX | ✓ |  |  |  |  | 6 | Medium | Verified | Valid/invalid states are clear | Setup failure <2%
FEAT-01-004 | Match lobby | P0 | UX | ✓ |  |  |  |  | 12 | High | Verified | Two clients can form a session | 100% lobby tests
FEAT-01-005 | Input capture | P0 | Gameplay | ✓ |  |  |  |  | 10 | High | Verified | Inputs are sampled and sequenced | Input loss <0.1%
FEAT-01-006 | Prediction state | P0 | Gameplay | ✓ |  |  |  |  | 14 | Critical | Verified | Corrections preserve playable state | No unrecoverable divergence
FEAT-01-007 | Rollback debug overlay | P1 | Gameplay | ✓ |  |  |  |  | 6 | Low | Verified | Overlay matches engine events | Telemetry mismatch <1%
FEAT-01-008 | Network health | P1 | HUD | ✓ |  |  |  |  | 8 | Medium | Verified | Metrics update without blocking rendering | Freshness <2s
FEAT-01-009 | Controls | P1 | Settings | ✓ |  |  |  |  | 8 | Low | Verified | Settings persist and apply | 100% settings tests
FEAT-01-010 | Render optimization | P0 | Performance | ✓ |  |  |  |  | 14 | High | Verified | Stable frame pacing under load | Target FPS >99% time
FEAT-01-011 | Client validation | P0 | Security | ✓ |  |  |  |  | 8 | High | Verified | Tampered values are rejected server-side | 0 forged outcomes accepted
FEAT-01-012 | Client telemetry | P1 | Observability | ✓ |  |  |  |  | 10 | Medium | Verified | Events searchable by session | >99% sessions have IDs
FEAT-01-013 | E2E client flow | P0 | Testing | ✓ |  |  |  |  | 16 | Medium | Verified | Critical flow passes in CI | >95% E2E pass rate
FEAT-01-014 | Service boundaries | P0 | Architecture |  | ✓ |  |  |  | 12 | High | Verified | Responsibilities are documented/testable | No circular dependencies
FEAT-01-015 | Protocol | P0 | Networking |  | ✓ |  |  |  | 12 | Critical | Verified | Unsupported versions fail cleanly | Protocol suite passes
FEAT-01-016 | Transport | P0 | Networking |  | ✓ |  |  |  | 24 | Critical | Verified | Clients exchange realtime inputs reliably | Packet handling stable
FEAT-01-017 | Tick loop | P0 | Networking |  | ✓ |  |  |  | 16 | Critical | Verified | Tick progression remains monotonic | Tick drift within target
FEAT-01-018 | Snapshot system | P0 | Rollback |  | ✓ |  |  |  | 24 | Critical | Verified | Any retained tick can be restored | 100% restore tests
FEAT-01-019 | Input history | P0 | Rollback |  | ✓ |  |  |  | 18 | Critical | Verified | Late/duplicate inputs handled predictably | 0 duplicate acceptance
FEAT-01-020 | Resimulation | P0 | Rollback |  | ✓ |  |  |  | 30 | Critical | Verified | Resimulation produces expected state | Determinism suite passes
FEAT-01-021 | Checksums | P0 | Sync |  | ✓ |  |  |  | 14 | High | Verified | Divergence is detected and classified | Detection within defined ticks
FEAT-01-022 | Queue | P1 | Matchmaking |  | ✓ |  |  |  | 18 | Medium | Verified | Configured rules are enforced | Queue wait tracked
FEAT-01-023 | Session allocation | P0 | Matchmaking |  | ✓ |  |  |  | 16 | High | Verified | Sessions start/stop cleanly | Orphan sessions <1%
FEAT-01-024 | Reconnect | P1 | Reliability |  | ✓ |  |  |  | 18 | High | Verified | Temporary disconnects recover | Recovery rate tracked
FEAT-01-025 | Authentication | P0 | Security |  | ✓ |  |  |  | 14 | Critical | Verified | Expired/revoked tokens rejected | 0 auth bypasses
FEAT-01-026 | Authorization | P0 | Security |  | ✓ |  |  |  | 10 | Critical | Verified | Cross-session access is blocked | 0 unauthorized access
FEAT-01-027 | Rate limiting | P0 | Security |  | ✓ |  |  |  | 12 | High | Verified | Abusive rates are throttled | No bypass across instances
FEAT-01-028 | Server authority | P0 | Anti-cheat |  | ✓ |  |  |  | 20 | Critical | Verified | Impossible transitions rejected | 0 impossible outcomes
FEAT-01-029 | Moderation APIs | P1 | Admin |  | ✓ |  |  |  | 16 | Medium | Verified | Privileged actions are audited | 100% audited
FEAT-01-030 | Metrics/tracing | P0 | Observability |  | ✓ |  |  |  | 16 | Medium | Verified | SLO dashboards expose critical signals | >95% metric coverage
FEAT-01-031 | Load & soak testing | P0 | Testing |  | ✓ |  |  |  | 24 | Critical | Verified | Target load is sustained | Target concurrency met
FEAT-01-032 | Telemetry dataset | P1 | Data |  |  |  | ✓ |  | 12 | Medium | Verified | Rows are reproducible and versioned | Data completeness >95%
FEAT-01-033 | Feature engineering | P1 | Data |  |  |  | ✓ |  | 14 | Medium | Verified | Pipeline is reproducible | No leakage features
FEAT-01-034 | Network quality prediction | P1 | Model |  |  |  | ✓ |  | 24 | High | Verified | Offline benchmark established | AUC/F1/MAE target documented
FEAT-01-035 | Adaptive input delay | P1 | Model |  |  |  | ✓ |  | 24 | Critical | Verified | Suggestions are bounded/reversible | No QoS regression
FEAT-01-036 | Rollback-risk prediction | P1 | Model |  |  |  | ✓ |  | 20 | High | Verified | Risk score benchmarked | Precision/recall tracked
FEAT-01-037 | Capacity forecasting | P2 | Model |  |  |  | ✓ |  | 20 | Medium | Verified | Holdout evaluation completed | Forecast error tracked
FEAT-01-038 | Matchmaking optimization | P2 | Model |  |  |  | ✓ |  | 28 | High | Verified | Offline strategies are compared | Constraints never violated
FEAT-01-039 | Cheat/anomaly signals | P1 | Anomaly |  |  |  | ✓ |  | 28 | Critical | Verified | Suspicious sessions are flagged, not blindly punished | False-positive rate tracked
FEAT-01-040 | Model explanations | P2 | Explainability |  |  |  | ✓ |  | 12 | Medium | Verified | Scores have inspectable drivers | Explanation coverage >90%
FEAT-01-041 | Experiment tracking | P1 | MLOps |  |  |  | ✓ |  | 12 | Medium | Verified | Results are reproducible | 100% experiments versioned
FEAT-01-042 | Model registry | P2 | MLOps |  |  |  | ✓ |  | 14 | Medium | Verified | Rollback to previous model works | Rollback <5 min
FEAT-01-043 | ML guardrails | P0 | Safety |  |  |  | ✓ |  | 14 | Critical | Verified | Failure falls back to deterministic policy | No unsafe autonomous action
FEAT-01-044 | Data model | P0 | Architecture |  |  | ✓ |  |  | 14 | High | Verified | Schema is migration-ready | Migration tests pass
FEAT-01-045 | Users | P0 | PostgreSQL |  |  | ✓ |  |  | 8 | Medium | Verified | CRUD and constraints complete | Integrity checks pass
FEAT-01-046 | Matches | P0 | PostgreSQL |  |  | ✓ |  |  | 10 | Medium | Verified | Full match lifecycle queryable | 100% lifecycle states valid
FEAT-01-047 | Sessions | P0 | PostgreSQL |  |  | ✓ |  |  | 10 | High | Verified | Orphan detection supported | Orphans <1%
FEAT-01-048 | Audit logs | P0 | PostgreSQL |  |  | ✓ |  |  | 8 | High | Verified | Normal users cannot modify logs | 100% privileged actions logged
FEAT-01-049 | Presence | P0 | Redis |  |  | ✓ |  |  | 8 | High | Verified | Stale presence expires | Stale presence <1%
FEAT-01-050 | Match queues | P0 | Redis |  |  | ✓ |  |  | 10 | High | Verified | No duplicate queue membership | 0 duplicate entries
FEAT-01-051 | Rate-limit counters | P0 | Redis |  |  | ✓ |  |  | 8 | High | Verified | Limits work across instances | No horizontal-scaling bypass
FEAT-01-052 | Indexes | P0 | Performance |  |  | ✓ |  |  | 12 | Medium | Verified | Query plans meet targets | p95 query target met
FEAT-01-053 | Partitioning | P1 | Performance |  |  | ✓ |  |  | 16 | High | Verified | Retention and queries stay stable | Storage growth controlled
FEAT-01-054 | Backups | P0 | Reliability |  |  | ✓ |  |  | 12 | Critical | Verified | Restore tested from backup | RPO/RTO documented
FEAT-01-055 | Replication/failover | P1 | Reliability |  |  | ✓ |  |  | 18 | Critical | Verified | Failover drill succeeds | Recovery objective met
FEAT-01-056 | Retention | P0 | Privacy |  |  | ✓ |  |  | 10 | High | Verified | Expired data is handled automatically | 100% retention tests
FEAT-01-057 | Encryption/secrets | P0 | Security |  |  | ✓ |  |  | 12 | Critical | Verified | Sensitive data protected | 0 plaintext secrets
FEAT-01-058 | Account & identity | P0 | Core |  | ✓ |  |  | ✓ | 10 | Medium | Verified | Complete account lifecycle | Auth success >99%
FEAT-01-059 | Create match | P0 | Core |  | ✓ |  |  | ✓ | 10 | High | Verified | Match can be created | Creation failure <1%
FEAT-01-060 | Join match | P0 | Core |  | ✓ |  |  | ✓ | 8 | High | Verified | Valid users join, invalid users rejected | Join success tracked
FEAT-01-061 | Rollback engine | P0 | Core |  | ✓ |  |  | ✓ | 40 | Critical | Verified | Controlled loss tests pass | Rollback correctness target
FEAT-01-062 | Deterministic simulation | P0 | Core |  | ✓ |  |  | ✓ | 30 | Critical | Verified | Cross-run determinism verified | Golden tests 100%
FEAT-01-063 | Desync recovery | P0 | Core |  | ✓ |  |  | ✓ | 24 | Critical | Verified | Recovery path works | Recovery rate tracked
FEAT-01-064 | Latency monitor | P1 | Network |  | ✓ |  |  | ✓ | 8 | Low | Verified | Metrics update live | Freshness <2s
FEAT-01-065 | Adaptive networking | P1 | Network |  | ✓ |  |  | ✓ | 22 | Critical | Verified | Policy changes improve stability without regressions | Baseline comparison
FEAT-01-066 | NAT traversal | P1 | Network |  | ✓ |  |  | ✓ | 24 | High | Verified | Common NAT types connect | Connection success benchmark
FEAT-01-067 | Region selection | P1 | Network |  | ✓ |  |  | ✓ | 10 | Medium | Verified | Selection uses measured latency | Selection accuracy tracked
FEAT-01-068 | Anti-cheat | P0 | Security |  | ✓ |  |  | ✓ | 28 | Critical | Verified | Known invalid actions blocked | False-positive tracking
FEAT-01-069 | DDoS resilience | P0 | Security |  | ✓ |  |  | ✓ | 24 | Critical | Verified | Abuse tests do not impact healthy rooms | Availability SLO
FEAT-01-070 | Reconnect | P1 | Reliability |  | ✓ |  |  | ✓ | 18 | High | Verified | Recovery works in defined window | Reconnect success
FEAT-01-071 | Graceful degradation | P0 | Reliability |  | ✓ |  |  | ✓ | 20 | Critical | Verified | Fallback behavior is deterministic | Critical-path availability
FEAT-01-072 | Admin dashboard | P1 | Operations |  | ✓ |  |  | ✓ | 24 | Medium | Verified | Operators can investigate incidents | MTTR tracked
FEAT-01-073 | Observability dashboard | P0 | Operations |  | ✓ |  |  | ✓ | 20 | Medium | Verified | Dashboards support incident response | Coverage >95%
FEAT-01-074 | Chaos testing | P0 | Testing |  | ✓ |  |  | ✓ | 24 | Critical | Verified | Defined failure envelope is maintained | Chaos pass rate
FEAT-01-075 | Determinism suite | P0 | Testing |  | ✓ |  |  | ✓ | 24 | Critical | Verified | Regressions fail CI | 100% golden tests
FEAT-01-076 | Security suite | P0 | Testing |  | ✓ |  |  | ✓ | 30 | Critical | Verified | No critical findings before release | 0 critical findings
FEAT-01-077 | Replay system | P2 | Product |  | ✓ |  |  | ✓ | 24 | Medium | Verified | Replay reproduces match | Replay determinism
FEAT-01-078 | Spectator mode | P2 | Product |  | ✓ |  |  | ✓ | 20 | Medium | Verified | Spectators cannot mutate state | 0 mutation paths
FEAT-01-079 | API/SDK | P1 | Product |  | ✓ |  |  | ✓ | 24 | Medium | Verified | External integration smoke test passes | SDK smoke test
FEAT-01-080 | Feature flags | P0 | Product |  | ✓ |  |  | ✓ | 12 | High | Verified | Features toggle without full redeploy | Rollback <5 min
FEAT-01-081 | Version compatibility | P0 | Product |  | ✓ |  |  | ✓ | 14 | High | Verified | Unsupported versions fail clearly | 0 silent incompatibilities
FEAT-01-082 | Threat model | P0 | Architecture |  | ✓ |  |  | ✓ | 16 | Critical | Verified | Threat model approved | 100% critical assets mapped
FEAT-01-083 | ADRs | P0 | Architecture |  | ✓ |  |  | ✓ | 12 | Medium | Verified | Major decisions have ADRs | 100% major decisions documented
FEAT-01-084 | CI/CD | P0 | DevOps |  | ✓ |  |  | ✓ | 20 | High | Verified | Every merge runs checks | Pipeline success >95%
FEAT-01-085 | Containers | P0 | DevOps |  | ✓ |  |  | ✓ | 16 | Medium | Verified | Clean-machine setup succeeds | Setup <30 min
FEAT-01-086 | Staging/production | P0 | DevOps |  | ✓ |  |  | ✓ | 24 | Critical | Verified | Promotion is reversible | Recovery drill passes
FEAT-01-087 | Engineering docs | P0 | Documentation |  | ✓ |  |  | ✓ | 24 | Medium | Verified | New contributor can run system | Docs coverage >90%
FEAT-01-088 | Data lifecycle | P1 | Privacy |  | ✓ |  |  | ✓ | 20 | High | Verified | Lifecycle workflows tested | 100% workflows tested
FEAT-01-089 | E2E profiling | P0 | Performance |  | ✓ |  |  | ✓ | 18 | High | Verified | Budgets are measurable | p95 targets met
FEAT-01-090 | Incident playbooks | P0 | Recovery |  | ✓ |  |  | ✓ | 18 | Critical | Verified | Recovery drill completed | RTO/RPO achieved

## Frontend
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-01-001 | App shell & routing | P0 | Architecture | 8 | Medium | Verified | All primary screens route correctly | 0 broken routes
FEAT-01-002 | State management | P0 | Architecture | 8 | High | Verified | State transitions are deterministic/testable | 0 state-desync UI bugs
FEAT-01-003 | Connection setup | P0 | UX | 6 | Medium | Verified | Valid/invalid states are clear | Setup failure <2%
FEAT-01-004 | Match lobby | P0 | UX | 12 | High | Verified | Two clients can form a session | 100% lobby tests
FEAT-01-005 | Input capture | P0 | Gameplay | 10 | High | Verified | Inputs are sampled and sequenced | Input loss <0.1%
FEAT-01-006 | Prediction state | P0 | Gameplay | 14 | Critical | Verified | Corrections preserve playable state | No unrecoverable divergence
FEAT-01-007 | Rollback debug overlay | P1 | Gameplay | 6 | Low | Verified | Overlay matches engine events | Telemetry mismatch <1%
FEAT-01-008 | Network health | P1 | HUD | 8 | Medium | Verified | Metrics update without blocking rendering | Freshness <2s
FEAT-01-009 | Controls | P1 | Settings | 8 | Low | Verified | Settings persist and apply | 100% settings tests
FEAT-01-010 | Render optimization | P0 | Performance | 14 | High | Verified | Stable frame pacing under load | Target FPS >99% time
FEAT-01-011 | Client validation | P0 | Security | 8 | High | Verified | Tampered values are rejected server-side | 0 forged outcomes accepted
FEAT-01-012 | Client telemetry | P1 | Observability | 10 | Medium | Verified | Events searchable by session | >99% sessions have IDs
FEAT-01-013 | E2E client flow | P0 | Testing | 16 | Medium | Verified | Critical flow passes in CI | >95% E2E pass rate

## Backend
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-01-014 | Service boundaries | P0 | Architecture | 12 | High | Verified | Responsibilities are documented/testable | No circular dependencies
FEAT-01-015 | Protocol | P0 | Networking | 12 | Critical | Verified | Unsupported versions fail cleanly | Protocol suite passes
FEAT-01-016 | Transport | P0 | Networking | 24 | Critical | Verified | Clients exchange realtime inputs reliably | Packet handling stable
FEAT-01-017 | Tick loop | P0 | Networking | 16 | Critical | Verified | Tick progression remains monotonic | Tick drift within target
FEAT-01-018 | Snapshot system | P0 | Rollback | 24 | Critical | Verified | Any retained tick can be restored | 100% restore tests
FEAT-01-019 | Input history | P0 | Rollback | 18 | Critical | Verified | Late/duplicate inputs handled predictably | 0 duplicate acceptance
FEAT-01-020 | Resimulation | P0 | Rollback | 30 | Critical | Verified | Resimulation produces expected state | Determinism suite passes
FEAT-01-021 | Checksums | P0 | Sync | 14 | High | Verified | Divergence is detected and classified | Detection within defined ticks
FEAT-01-022 | Queue | P1 | Matchmaking | 18 | Medium | Verified | Configured rules are enforced | Queue wait tracked
FEAT-01-023 | Session allocation | P0 | Matchmaking | 16 | High | Verified | Sessions start/stop cleanly | Orphan sessions <1%
FEAT-01-024 | Reconnect | P1 | Reliability | 18 | High | Verified | Temporary disconnects recover | Recovery rate tracked
FEAT-01-025 | Authentication | P0 | Security | 14 | Critical | Verified | Expired/revoked tokens rejected | 0 auth bypasses
FEAT-01-026 | Authorization | P0 | Security | 10 | Critical | Verified | Cross-session access is blocked | 0 unauthorized access
FEAT-01-027 | Rate limiting | P0 | Security | 12 | High | Verified | Abusive rates are throttled | No bypass across instances
FEAT-01-028 | Server authority | P0 | Anti-cheat | 20 | Critical | Verified | Impossible transitions rejected | 0 impossible outcomes
FEAT-01-029 | Moderation APIs | P1 | Admin | 16 | Medium | Verified | Privileged actions are audited | 100% audited
FEAT-01-030 | Metrics/tracing | P0 | Observability | 16 | Medium | Verified | SLO dashboards expose critical signals | >95% metric coverage
FEAT-01-031 | Load & soak testing | P0 | Testing | 24 | Critical | Verified | Target load is sustained | Target concurrency met
FEAT-01-058 | Account & identity | P0 | Core | 10 | Medium | Verified | Complete account lifecycle | Auth success >99%
FEAT-01-059 | Create match | P0 | Core | 10 | High | Verified | Match can be created | Creation failure <1%
FEAT-01-060 | Join match | P0 | Core | 8 | High | Verified | Valid users join, invalid users rejected | Join success tracked
FEAT-01-061 | Rollback engine | P0 | Core | 40 | Critical | Verified | Controlled loss tests pass | Rollback correctness target
FEAT-01-062 | Deterministic simulation | P0 | Core | 30 | Critical | Verified | Cross-run determinism verified | Golden tests 100%
FEAT-01-063 | Desync recovery | P0 | Core | 24 | Critical | Verified | Recovery path works | Recovery rate tracked
FEAT-01-064 | Latency monitor | P1 | Network | 8 | Low | Verified | Metrics update live | Freshness <2s
FEAT-01-065 | Adaptive networking | P1 | Network | 22 | Critical | Verified | Policy changes improve stability without regressions | Baseline comparison
FEAT-01-066 | NAT traversal | P1 | Network | 24 | High | Verified | Common NAT types connect | Connection success benchmark
FEAT-01-067 | Region selection | P1 | Network | 10 | Medium | Verified | Selection uses measured latency | Selection accuracy tracked
FEAT-01-068 | Anti-cheat | P0 | Security | 28 | Critical | Verified | Known invalid actions blocked | False-positive tracking
FEAT-01-069 | DDoS resilience | P0 | Security | 24 | Critical | Verified | Abuse tests do not impact healthy rooms | Availability SLO
FEAT-01-070 | Reconnect | P1 | Reliability | 18 | High | Verified | Recovery works in defined window | Reconnect success
FEAT-01-071 | Graceful degradation | P0 | Reliability | 20 | Critical | Verified | Fallback behavior is deterministic | Critical-path availability
FEAT-01-072 | Admin dashboard | P1 | Operations | 24 | Medium | Verified | Operators can investigate incidents | MTTR tracked
FEAT-01-073 | Observability dashboard | P0 | Operations | 20 | Medium | Verified | Dashboards support incident response | Coverage >95%
FEAT-01-074 | Chaos testing | P0 | Testing | 24 | Critical | Verified | Defined failure envelope is maintained | Chaos pass rate
FEAT-01-075 | Determinism suite | P0 | Testing | 24 | Critical | Verified | Regressions fail CI | 100% golden tests
FEAT-01-076 | Security suite | P0 | Testing | 30 | Critical | Verified | No critical findings before release | 0 critical findings
FEAT-01-077 | Replay system | P2 | Product | 24 | Medium | Verified | Replay reproduces match | Replay determinism
FEAT-01-078 | Spectator mode | P2 | Product | 20 | Medium | Verified | Spectators cannot mutate state | 0 mutation paths
FEAT-01-079 | API/SDK | P1 | Product | 24 | Medium | Verified | External integration smoke test passes | SDK smoke test
FEAT-01-080 | Feature flags | P0 | Product | 12 | High | Verified | Features toggle without full redeploy | Rollback <5 min
FEAT-01-081 | Version compatibility | P0 | Product | 14 | High | Verified | Unsupported versions fail clearly | 0 silent incompatibilities
FEAT-01-082 | Threat model | P0 | Architecture | 16 | Critical | Verified | Threat model approved | 100% critical assets mapped
FEAT-01-083 | ADRs | P0 | Architecture | 12 | Medium | Verified | Major decisions have ADRs | 100% major decisions documented
FEAT-01-084 | CI/CD | P0 | DevOps | 20 | High | Verified | Every merge runs checks | Pipeline success >95%
FEAT-01-085 | Containers | P0 | DevOps | 16 | Medium | Verified | Clean-machine setup succeeds | Setup <30 min
FEAT-01-086 | Staging/production | P0 | DevOps | 24 | Critical | Verified | Promotion is reversible | Recovery drill passes
FEAT-01-087 | Engineering docs | P0 | Documentation | 24 | Medium | Verified | New contributor can run system | Docs coverage >90%
FEAT-01-088 | Data lifecycle | P1 | Privacy | 20 | High | Verified | Lifecycle workflows tested | 100% workflows tested
FEAT-01-089 | E2E profiling | P0 | Performance | 18 | High | Verified | Budgets are measurable | p95 targets met
FEAT-01-090 | Incident playbooks | P0 | Recovery | 18 | Critical | Verified | Recovery drill completed | RTO/RPO achieved

## Database
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-01-044 | Data model | P0 | Architecture | 14 | High | Verified | Schema is migration-ready | Migration tests pass
FEAT-01-045 | Users | P0 | PostgreSQL | 8 | Medium | Verified | CRUD and constraints complete | Integrity checks pass
FEAT-01-046 | Matches | P0 | PostgreSQL | 10 | Medium | Verified | Full match lifecycle queryable | 100% lifecycle states valid
FEAT-01-047 | Sessions | P0 | PostgreSQL | 10 | High | Verified | Orphan detection supported | Orphans <1%
FEAT-01-048 | Audit logs | P0 | PostgreSQL | 8 | High | Verified | Normal users cannot modify logs | 100% privileged actions logged
FEAT-01-049 | Presence | P0 | Redis | 8 | High | Verified | Stale presence expires | Stale presence <1%
FEAT-01-050 | Match queues | P0 | Redis | 10 | High | Verified | No duplicate queue membership | 0 duplicate entries
FEAT-01-051 | Rate-limit counters | P0 | Redis | 8 | High | Verified | Limits work across instances | No horizontal-scaling bypass
FEAT-01-052 | Indexes | P0 | Performance | 12 | Medium | Verified | Query plans meet targets | p95 query target met
FEAT-01-053 | Partitioning | P1 | Performance | 16 | High | Verified | Retention and queries stay stable | Storage growth controlled
FEAT-01-054 | Backups | P0 | Reliability | 12 | Critical | Verified | Restore tested from backup | RPO/RTO documented
FEAT-01-055 | Replication/failover | P1 | Reliability | 18 | Critical | Verified | Failover drill succeeds | Recovery objective met
FEAT-01-056 | Retention | P0 | Privacy | 10 | High | Verified | Expired data is handled automatically | 100% retention tests
FEAT-01-057 | Encryption/secrets | P0 | Security | 12 | Critical | Verified | Sensitive data protected | 0 plaintext secrets

## AIML
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-01-032 | Telemetry dataset | P1 | Data | 12 | Medium | Verified | Rows are reproducible and versioned | Data completeness >95%
FEAT-01-033 | Feature engineering | P1 | Data | 14 | Medium | Verified | Pipeline is reproducible | No leakage features
FEAT-01-034 | Network quality prediction | P1 | Model | 24 | High | Verified | Offline benchmark established | AUC/F1/MAE target documented
FEAT-01-035 | Adaptive input delay | P1 | Model | 24 | Critical | Verified | Suggestions are bounded/reversible | No QoS regression
FEAT-01-036 | Rollback-risk prediction | P1 | Model | 20 | High | Verified | Risk score benchmarked | Precision/recall tracked
FEAT-01-037 | Capacity forecasting | P2 | Model | 20 | Medium | Verified | Holdout evaluation completed | Forecast error tracked
FEAT-01-038 | Matchmaking optimization | P2 | Model | 28 | High | Verified | Offline strategies are compared | Constraints never violated
FEAT-01-039 | Cheat/anomaly signals | P1 | Anomaly | 28 | Critical | Verified | Suspicious sessions are flagged, not blindly punished | False-positive rate tracked
FEAT-01-040 | Model explanations | P2 | Explainability | 12 | Medium | Verified | Scores have inspectable drivers | Explanation coverage >90%
FEAT-01-041 | Experiment tracking | P1 | MLOps | 12 | Medium | Verified | Results are reproducible | 100% experiments versioned
FEAT-01-042 | Model registry | P2 | MLOps | 14 | Medium | Verified | Rollback to previous model works | Rollback <5 min
FEAT-01-043 | ML guardrails | P0 | Safety | 14 | Critical | Verified | Failure falls back to deterministic policy | No unsafe autonomous action

## API
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-01-058 | Account & identity | P0 | Core | 10 | Medium | Verified | Complete account lifecycle | Auth success >99%
FEAT-01-059 | Create match | P0 | Core | 10 | High | Verified | Match can be created | Creation failure <1%
FEAT-01-060 | Join match | P0 | Core | 8 | High | Verified | Valid users join, invalid users rejected | Join success tracked
FEAT-01-061 | Rollback engine | P0 | Core | 40 | Critical | Verified | Controlled loss tests pass | Rollback correctness target
FEAT-01-062 | Deterministic simulation | P0 | Core | 30 | Critical | Verified | Cross-run determinism verified | Golden tests 100%
FEAT-01-063 | Desync recovery | P0 | Core | 24 | Critical | Verified | Recovery path works | Recovery rate tracked
FEAT-01-064 | Latency monitor | P1 | Network | 8 | Low | Verified | Metrics update live | Freshness <2s
FEAT-01-065 | Adaptive networking | P1 | Network | 22 | Critical | Verified | Policy changes improve stability without regressions | Baseline comparison
FEAT-01-066 | NAT traversal | P1 | Network | 24 | High | Verified | Common NAT types connect | Connection success benchmark
FEAT-01-067 | Region selection | P1 | Network | 10 | Medium | Verified | Selection uses measured latency | Selection accuracy tracked
FEAT-01-068 | Anti-cheat | P0 | Security | 28 | Critical | Verified | Known invalid actions blocked | False-positive tracking
FEAT-01-069 | DDoS resilience | P0 | Security | 24 | Critical | Verified | Abuse tests do not impact healthy rooms | Availability SLO
FEAT-01-070 | Reconnect | P1 | Reliability | 18 | High | Verified | Recovery works in defined window | Reconnect success
FEAT-01-071 | Graceful degradation | P0 | Reliability | 20 | Critical | Verified | Fallback behavior is deterministic | Critical-path availability
FEAT-01-072 | Admin dashboard | P1 | Operations | 24 | Medium | Verified | Operators can investigate incidents | MTTR tracked
FEAT-01-073 | Observability dashboard | P0 | Operations | 20 | Medium | Verified | Dashboards support incident response | Coverage >95%
FEAT-01-074 | Chaos testing | P0 | Testing | 24 | Critical | Verified | Defined failure envelope is maintained | Chaos pass rate
FEAT-01-075 | Determinism suite | P0 | Testing | 24 | Critical | Verified | Regressions fail CI | 100% golden tests
FEAT-01-076 | Security suite | P0 | Testing | 30 | Critical | Verified | No critical findings before release | 0 critical findings
FEAT-01-077 | Replay system | P2 | Product | 24 | Medium | Verified | Replay reproduces match | Replay determinism
FEAT-01-078 | Spectator mode | P2 | Product | 20 | Medium | Verified | Spectators cannot mutate state | 0 mutation paths
FEAT-01-079 | API/SDK | P1 | Product | 24 | Medium | Verified | External integration smoke test passes | SDK smoke test
FEAT-01-080 | Feature flags | P0 | Product | 12 | High | Verified | Features toggle without full redeploy | Rollback <5 min
FEAT-01-081 | Version compatibility | P0 | Product | 14 | High | Verified | Unsupported versions fail clearly | 0 silent incompatibilities
FEAT-01-082 | Threat model | P0 | Architecture | 16 | Critical | Verified | Threat model approved | 100% critical assets mapped
FEAT-01-083 | ADRs | P0 | Architecture | 12 | Medium | Verified | Major decisions have ADRs | 100% major decisions documented
FEAT-01-084 | CI/CD | P0 | DevOps | 20 | High | Verified | Every merge runs checks | Pipeline success >95%
FEAT-01-085 | Containers | P0 | DevOps | 16 | Medium | Verified | Clean-machine setup succeeds | Setup <30 min
FEAT-01-086 | Staging/production | P0 | DevOps | 24 | Critical | Verified | Promotion is reversible | Recovery drill passes
FEAT-01-087 | Engineering docs | P0 | Documentation | 24 | Medium | Verified | New contributor can run system | Docs coverage >90%
FEAT-01-088 | Data lifecycle | P1 | Privacy | 20 | High | Verified | Lifecycle workflows tested | 100% workflows tested
FEAT-01-089 | E2E profiling | P0 | Performance | 18 | High | Verified | Budgets are measurable | p95 targets met
FEAT-01-090 | Incident playbooks | P0 | Recovery | 18 | Critical | Verified | Recovery drill completed | RTO/RPO achieved