## Dashboard
PROJECT DASHBOARD — 03 BYTECODE-VM-GC
System Metric | Count / Value | Formula Reference
Total Features |  | COUNTA
Verified Features |  | COUNTIF Verified
Implemented Features |  | COUNTIF Implemented
Specified Features |  | COUNTIF Specified
P0 Features |  | COUNTIF P0
P1 Features |  | COUNTIF P1
P2 Features |  | COUNTIF P2
Total Estimated Effort (Hours) |  | SUM Hours

## Feature Matrix
ID | Feature | Priority | Area | Frontend | Backend | Database | AI/ML | API | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-03-001 | Bytecode format & versioning | P0 | VM Lead | ✓ | ✓ | ✓ |  |  | 20 | Critical | Specified | Stable encoding/decoding and explicit version compatibility | 100% test pass
FEAT-03-002 | Opcode set | P0 | VM Lead | ✓ | ✓ |  |  |  | 24 | Critical | Specified | Every opcode has defined semantics and tests | 100% test pass
FEAT-03-003 | Bytecode verifier | P0 | VM/Security | ✓ | ✓ |  |  |  | 30 | Critical | Specified | Malformed bytecode rejected before execution | 100% test pass
FEAT-03-004 | Constant pool | P0 | VM Lead | ✓ | ✓ | ✓ |  |  | 20 | High | Specified | Constants load safely | 100% test pass
FEAT-03-005 | Instruction decoder | P0 | VM Lead | ✓ | ✓ |  |  |  | 18 | High | Specified | Valid/invalid streams handled deterministically | 100% test pass
FEAT-03-006 | Stack machine | P0 | VM Lead | ✓ | ✓ |  |  |  | 32 | Critical | Specified | Stack effects match instruction semantics | 100% test pass
FEAT-03-007 | Call frames | P0 | VM Lead | ✓ | ✓ |  |  |  | 30 | Critical | Specified | Nested calls preserve state | 100% test pass
FEAT-03-008 | Closures/upvalues | P1 | VM Lead | ✓ | ✓ | ✓ |  |  | 34 | High | Specified | Captured variables remain valid | 100% test pass
FEAT-03-009 | Exception handling | P1 | Runtime Lead | ✓ | ✓ |  |  |  | 30 | High | Specified | Exceptions unwind correctly | 100% test pass
FEAT-03-010 | Stack traces | P1 | Runtime Lead | ✓ | ✓ |  |  |  | 18 | Medium | Specified | Errors expose stable frames | 100% test pass
FEAT-03-011 | Interpreter dispatch | P0 | VM Lead | ✓ | ✓ |  |  |  | 28 | High | Specified | Dispatch is correct and benchmarkable | 100% test pass
FEAT-03-012 | Dispatch profiling | P1 | VM Lead | ✓ | ✓ |  |  |  | 18 | Medium | Specified | Hot opcodes are measurable | 100% test pass
FEAT-03-013 | Native/FFI boundary | P1 | Runtime Lead | ✓ | ✓ |  |  |  | 30 | Critical | Specified | Native calls cannot corrupt VM state | 100% test pass
FEAT-03-014 | Sandbox/capability model | P0 | Security Lead | ✓ | ✓ |  |  |  | 30 | Critical | Specified | Untrusted bytecode cannot exceed capabilities | 100% test pass
FEAT-03-015 | VM resource limits | P0 | Runtime Lead | ✓ | ✓ |  |  |  | 22 | Critical | Specified | Instruction/time/stack/memory budgets enforced | 100% test pass
FEAT-03-016 | Heap object model | P0 | GC Lead | ✓ | ✓ | ✓ |  |  | 36 | Critical | Specified | Objects allocate/traverse consistently | 100% test pass
FEAT-03-017 | Allocator | P0 | GC Lead | ✓ | ✓ | ✓ |  |  | 30 | Critical | Specified | Allocations are aligned and reusable | 100% test pass
FEAT-03-018 | Root set | P0 | GC Lead | ✓ | ✓ | ✓ |  |  | 28 | Critical | Specified | All live roots are enumerated | 100% test pass
FEAT-03-019 | Mark phase | P0 | GC Lead | ✓ | ✓ |  |  |  | 34 | Critical | Specified | Reachable objects marked correctly | 100% test pass
FEAT-03-020 | Sweep phase | P0 | GC Lead | ✓ | ✓ | ✓ |  |  | 30 | Critical | Specified | Unreachable objects reclaimed safely | 100% test pass
FEAT-03-021 | Tri-color invariants | P1 | GC Lead | ✓ | ✓ |  |  |  | 24 | High | Specified | Collector invariants preserved | 100% test pass
FEAT-03-022 | Write barriers | P1 | GC Lead | ✓ | ✓ |  |  |  | 26 | Critical | Specified | Mutator writes preserve GC invariants | 100% test pass
FEAT-03-023 | Stop-the-world GC | P0 | GC Lead | ✓ | ✓ |  |  |  | 24 | High | Specified | Mutator pauses/resumes safely | 100% test pass
FEAT-03-024 | Incremental GC | P2 | GC Lead | ✓ | ✓ |  |  |  | 38 | Critical | Specified | GC work interleaves safely | 100% test pass
FEAT-03-025 | Generational GC | P1 | GC Lead | ✓ | ✓ | ✓ |  |  | 44 | Critical | Specified | Young/old invariants hold | 100% test pass
FEAT-03-026 | Compacting GC | P2 | GC Lead | ✓ | ✓ |  |  |  | 44 | Critical | Specified | References survive relocation | 100% test pass
FEAT-03-027 | Handle table | P1 | Runtime Lead | ✓ | ✓ | ✓ |  |  | 24 | High | Specified | Native refs survive GC | 100% test pass
FEAT-03-028 | Weak references | P2 | GC Lead | ✓ | ✓ | ✓ |  |  | 24 | High | Specified | Weak refs do not retain objects | 100% test pass
FEAT-03-029 | Finalizers | P2 | GC Lead | ✓ | ✓ | ✓ |  |  | 26 | Critical | Specified | Finalization semantics are explicit | 100% test pass
FEAT-03-030 | GC telemetry | P0 | Runtime/SRE | ✓ | ✓ | ✓ |  |  | 20 | Medium | Specified | Allocation/pause/heap metrics exposed | 100% test pass
FEAT-03-031 | Heap snapshots | P1 | Tooling Lead | ✓ | ✓ | ✓ |  |  | 26 | High | Specified | Heap state can be analyzed | 100% test pass
FEAT-03-032 | Memory leak detector | P1 | Tooling Lead | ✓ | ✓ | ✓ | ✓ |  | 30 | High | Specified | Retained-object paths discoverable | 100% test pass
FEAT-03-033 | Source maps | P1 | Tooling Lead | ✓ | ✓ |  |  |  | 24 | Medium | Specified | Bytecode maps to source | 100% test pass
FEAT-03-034 | Debugger | P1 | Tooling Lead | ✓ | ✓ |  |  |  | 38 | High | Specified | Pause/step/inspect works | 100% test pass
FEAT-03-035 | Profiler | P1 | Performance Lead | ✓ | ✓ |  | ✓ |  | 34 | Medium | Specified | CPU/alloc/GC hotspots measurable | 100% test pass
FEAT-03-036 | Execution tracer | P2 | VM Lead | ✓ | ✓ |  |  |  | 24 | Medium | Specified | Bounded traces exportable | 100% test pass
FEAT-03-037 | REPL/console | P1 | Tooling Lead | ✓ | ✓ |  |  |  | 24 | Low | Specified | Interactive evaluation works safely | 100% test pass
FEAT-03-038 | Bytecode disassembler | P0 | Tooling Lead | ✓ | ✓ |  |  |  | 18 | Low | Specified | All bytecode inspectable | 100% test pass
FEAT-03-039 | Compiler frontend | P1 | Compiler Lead | ✓ | ✓ |  |  |  | 42 | High | Specified | Source compiles to valid bytecode | 100% test pass
FEAT-03-040 | Optimizer passes | P2 | Compiler Lead |  | ✓ |  | ✓ |  | 44 | High | Specified | Optimizations preserve semantics | 100% test pass
FEAT-03-041 | JIT baseline compiler | P2 | Compiler Lead |  | ✓ |  | ✓ |  | 60 | Critical | Specified | Hot functions execute natively correctly | 100% test pass
FEAT-03-042 | JIT profiling | P2 | Compiler Lead |  | ✓ |  | ✓ |  | 34 | High | Specified | Hotness identifies candidates | 100% test pass
FEAT-03-043 | Deoptimization | P2 | Compiler Lead |  | ✓ |  | ✓ |  | 46 | Critical | Specified | Optimized code returns safely to interpreter | 100% test pass
FEAT-03-044 | Inline caching | P2 | VM/Compiler |  | ✓ |  | ✓ |  | 36 | High | Specified | Dynamic operations accelerated safely | 100% test pass
FEAT-03-045 | Concurrency model | P2 | Runtime Lead | ✓ | ✓ |  |  |  | 38 | Critical | Specified | Defined thread/task/isolate semantics | 100% test pass
FEAT-03-046 | Async/event loop | P2 | Runtime Lead | ✓ | ✓ |  |  |  | 34 | High | Specified | Async tasks resume correctly | 100% test pass
FEAT-03-047 | Scheduler | P2 | Runtime Lead |  | ✓ |  |  |  | 30 | High | Specified | Fairness/resource limits enforced | 100% test pass
FEAT-03-048 | Deterministic execution | P1 | VM/QA | ✓ | ✓ |  |  |  | 26 | High | Specified | Same input reproduces execution | 100% test pass
FEAT-03-049 | Serialization | P1 | Runtime Lead | ✓ | ✓ | ✓ |  |  | 28 | High | Specified | Values round-trip safely | 100% test pass
FEAT-03-050 | VM snapshot/restore | P1 | Runtime Lead |  | ✓ | ✓ |  |  | 34 | Critical | Specified | VM state restores/resumes correctly | 100% test pass
FEAT-03-051 | Persistent cache | P2 | Runtime/DBA |  | ✓ | ✓ |  |  | 26 | Medium | Specified | Cache invalidates safely | 100% test pass
FEAT-03-052 | Runtime configuration | P0 | Runtime Lead | ✓ | ✓ | ✓ |  |  | 18 | Low | Specified | Limits/features validate correctly | 100% test pass
FEAT-03-053 | Compatibility matrix | P0 | Release Lead | ✓ | ✓ | ✓ |  |  | 20 | High | Specified | Supported combinations tested | 100% test pass
FEAT-03-054 | Crash handling | P0 | Runtime Lead | ✓ | ✓ |  |  |  | 24 | Critical | Specified | Crashes produce actionable diagnostics | 100% test pass
FEAT-03-055 | Panic/exception boundary | P0 | Runtime Lead | ✓ | ✓ |  |  |  | 20 | Critical | Specified | Host protected from VM failures | 100% test pass
FEAT-03-056 | Fuzz bytecode verifier | P0 | Security/QA |  | ✓ |  | ✓ |  | 28 | Critical | Specified | No crashes/bypasses found | 100% test pass
FEAT-03-057 | GC stress/fuzz | P0 | GC/QA |  | ✓ | ✓ | ✓ |  | 34 | Critical | Specified | Random allocation/GC preserves invariants | 100% test pass
FEAT-03-058 | Differential VM testing | P1 | QA/VM |  | ✓ |  | ✓ |  | 30 | High | Specified | Optimized/reference paths agree | 100% test pass
FEAT-03-059 | Property-based tests | P1 | QA |  | ✓ |  | ✓ |  | 28 | High | Specified | Generated programs preserve invariants | 100% test pass
FEAT-03-060 | Benchmark suite | P0 | Performance Lead |  | ✓ |  | ✓ |  | 28 | Medium | Specified | Standard workloads track regressions | 100% test pass
FEAT-03-061 | GC pause benchmark | P0 | GC Lead |  | ✓ | ✓ | ✓ |  | 22 | High | Specified | Pause distributions measurable | 100% test pass
FEAT-03-062 | Memory footprint benchmark | P0 | Performance Lead |  | ✓ | ✓ |  |  | 22 | High | Specified | RSS/heap overhead tracked | 100% test pass
FEAT-03-063 | Security threat model | P0 | Security Lead | ✓ | ✓ | ✓ | ✓ |  | 24 | Critical | Specified | Threats/mitigations documented | 100% test pass
FEAT-03-064 | Capability audit | P0 | Security Lead |  | ✓ | ✓ |  |  | 20 | Critical | Specified | Host capabilities least-privilege | 100% test pass
FEAT-03-065 | Dependency/SBOM | P1 | DevSecOps |  | ✓ | ✓ |  |  | 14 | Medium | Specified | Dependencies/licenses tracked | 100% test pass
FEAT-03-066 | CI/CD | P0 | DevOps |  | ✓ | ✓ | ✓ |  | 22 | High | Specified | Build/test/fuzz/bench gates automatic | 100% test pass
FEAT-03-067 | Cross-platform builds | P1 | DevOps | ✓ | ✓ |  |  |  | 24 | Medium | Specified | Supported platforms build/test | 100% test pass
FEAT-03-068 | Packaging/distribution | P1 | Release Lead | ✓ | ✓ |  |  |  | 20 | Medium | Specified | Versioned packages reproducible | 100% test pass
FEAT-03-069 | Release signing | P1 | Release/Security |  | ✓ | ✓ |  |  | 14 | High | Specified | Artifacts signed/verifiable | 100% test pass
FEAT-03-070 | Documentation portal | P1 | Tech Writer | ✓ | ✓ |  |  |  | 22 | Low | Specified | API/VM/GC docs discoverable | 100% test pass
FEAT-03-071 | Architecture decision records | P1 | Tech Lead | ✓ | ✓ | ✓ | ✓ |  | 16 | Low | Specified | Major decisions recorded | 100% test pass
FEAT-03-072 | Operational runbook | P0 | SRE |  | ✓ | ✓ |  |  | 18 | High | Specified | Operators can diagnose/recover | 100% test pass
FEAT-03-073 | Disaster recovery | P1 | SRE |  | ✓ | ✓ |  |  | 24 | Critical | Specified | State restores within RPO/RTO | 100% test pass
FEAT-03-074 | Metrics/alerts | P0 | SRE | ✓ | ✓ | ✓ | ✓ |  | 18 | High | Specified | Critical failures alert with context | 100% test pass
FEAT-03-075 | Experiment tracking | P1 | ML/Research |  | ✓ |  | ✓ |  | 16 | Medium | Specified | Optimization experiments reproducible | 100% test pass
FEAT-03-076 | ML anomaly detection | P2 | ML/SRE |  | ✓ | ✓ | ✓ |  | 34 | High | Specified | Abnormal GC/VM behavior flagged | 100% test pass
FEAT-03-077 | GC policy recommendation | P2 | ML/Performance |  | ✓ | ✓ | ✓ |  | 36 | High | Specified | Safe GC parameters recommended | 100% test pass
FEAT-03-078 | Workload classification | P2 | ML/Performance |  | ✓ |  | ✓ |  | 30 | Medium | Specified | Workloads classified accurately | 100% test pass
FEAT-03-079 | Adaptive runtime tuning | P2 | ML/Performance |  | ✓ |  | ✓ |  | 40 | Critical | Specified | Tuning improves benchmarks without correctness loss | 100% test pass
FEAT-03-080 | ML fallback/kill switch | P0 | ML/Runtime |  | ✓ |  | ✓ |  | 12 | Critical | Specified | ML can be disabled with no correctness loss | 100% test pass
FEAT-03-081 | Lexer/tokenizer | P1 | Compiler Lead | ✓ | ✓ |  |  |  | 24 | Medium | Specified | Deterministic tokens and diagnostics | 100% test pass
FEAT-03-082 | AST representation | P1 | Compiler Lead | ✓ | ✓ | ✓ |  |  | 24 | Medium | Specified | Stable AST for tooling | 100% test pass
FEAT-03-083 | Type system | P2 | Compiler Lead | ✓ | ✓ |  | ✓ |  | 44 | High | Specified | Deterministic type checking | 100% test pass
FEAT-03-084 | Semantic analysis | P1 | Compiler Lead | ✓ | ✓ |  |  |  | 34 | High | Specified | Invalid programs rejected before codegen | 100% test pass
FEAT-03-085 | Compiler diagnostics | P1 | Compiler Lead | ✓ | ✓ |  |  |  | 22 | Low | Specified | Actionable source diagnostics | 100% test pass
FEAT-03-086 | Module/import system | P1 | Runtime Lead | ✓ | ✓ | ✓ |  |  | 34 | High | Specified | Modules resolve and load safely | 100% test pass
FEAT-03-087 | Package/dependency manager | P2 | Release Lead | ✓ | ✓ | ✓ |  |  | 38 | High | Specified | Reproducible dependency resolution | 100% test pass
FEAT-03-088 | IDE/LSP integration | P2 | Tooling Lead | ✓ | ✓ |  |  |  | 42 | Medium | Specified | Editor navigation and diagnostics | 100% test pass
FEAT-03-089 | Intermediate representation | P2 | Compiler Lead |  | ✓ |  | ✓ |  | 42 | High | Specified | IR supports optimization | 100% test pass
FEAT-03-090 | Control-flow graph | P2 | Compiler Lead |  | ✓ |  |  |  | 26 | Medium | Specified | CFG models all branches | 100% test pass
FEAT-03-091 | Register-based VM option | P3 | VM Lead |  | ✓ |  |  |  | 42 | High | Specified | Alternative backend matches reference semantics | 100% test pass
FEAT-03-092 | SIMD/vector operations | P3 | Performance Lead |  | ✓ |  | ✓ |  | 34 | High | Specified | Vector ops have safe fallback | 100% test pass
FEAT-03-093 | WebAssembly interoperability | P3 | Runtime Lead |  | ✓ |  |  |  | 42 | High | Specified | Interop preserves safety | 100% test pass
FEAT-03-094 | Native extension SDK | P2 | Runtime Lead |  | ✓ | ✓ |  |  | 38 | Critical | Specified | Stable documented native ABI | 100% test pass
FEAT-03-095 | Plugin system | P2 | Runtime Lead | ✓ | ✓ | ✓ |  |  | 40 | Critical | Specified | Plugins are isolated | 100% test pass
FEAT-03-096 | Multi-tenant isolation | P1 | Security Lead | ✓ | ✓ | ✓ |  |  | 38 | Critical | Specified | Tenants cannot access each other | 100% test pass
FEAT-03-097 | CPU quota accounting | P1 | Runtime/SRE |  | ✓ | ✓ |  |  | 22 | High | Specified | CPU usage measured per workload | 100% test pass
FEAT-03-098 | Memory quota accounting | P1 | Runtime/SRE |  | ✓ | ✓ |  |  | 22 | High | Specified | Memory usage enforced | 100% test pass
FEAT-03-099 | IO/network quota | P2 | Security Lead |  | ✓ | ✓ |  |  | 24 | High | Specified | External IO respects quotas | 100% test pass
FEAT-03-100 | Audit log | P1 | Security Lead | ✓ | ✓ | ✓ |  |  | 20 | High | Specified | Security actions traceable | 100% test pass
FEAT-03-101 | Secrets management | P1 | DevSecOps |  | ✓ | ✓ |  |  | 18 | Critical | Specified | Secrets absent from artifacts/logs | 100% test pass
FEAT-03-102 | Memory corruption detection | P0 | VM/QA |  | ✓ | ✓ | ✓ |  | 34 | Critical | Specified | Corruption detected in test builds | 100% test pass
FEAT-03-103 | Sanitizer builds | P1 | DevOps |  | ✓ |  |  |  | 20 | High | Specified | Memory/UB/concurrency sanitizer coverage | 100% test pass
FEAT-03-104 | Mutation testing | P2 | QA |  | ✓ |  |  |  | 24 | Medium | Specified | Tests kill meaningful mutations | 100% test pass
FEAT-03-105 | Golden bytecode corpus | P0 | QA |  | ✓ | ✓ |  |  | 18 | High | Specified | Known programs remain compatible | 100% test pass
FEAT-03-106 | Backward compatibility tests | P0 | Release Lead |  | ✓ | ✓ |  |  | 24 | High | Specified | Supported old artifacts execute | 100% test pass
FEAT-03-107 | Upgrade/downgrade tests | P1 | Release Lead |  | ✓ | ✓ |  |  | 26 | Critical | Specified | Runtime upgrades preserve state | 100% test pass
FEAT-03-108 | Long-duration soak test | P1 | SRE/QA |  | ✓ | ✓ |  |  | 30 | High | Specified | No drift or leak over long runs | 100% test pass
FEAT-03-109 | Fault injection | P1 | SRE/QA |  | ✓ | ✓ | ✓ |  | 32 | Critical | Specified | Injected failures recover or fail safely | 100% test pass
FEAT-03-110 | Chaos testing | P2 | SRE |  | ✓ | ✓ |  |  | 34 | High | Specified | Dependencies tolerate faults | 100% test pass
FEAT-03-111 | Performance regression gate | P0 | Performance Lead |  | ✓ |  | ✓ |  | 20 | High | Specified | CI blocks regressions | 100% test pass
FEAT-03-112 | Binary size optimization | P2 | Release Lead |  | ✓ |  |  |  | 18 | Low | Specified | Runtime stays within size budget | 100% test pass
FEAT-03-113 | Startup snapshot | P3 | Runtime Lead |  | ✓ | ✓ |  |  | 36 | High | Specified | Preinitialized runtime starts faster | 100% test pass
FEAT-03-114 | Profile-guided optimization | P3 | Compiler Lead |  | ✓ |  | ✓ |  | 40 | High | Specified | Profiles improve optimization | 100% test pass
FEAT-03-115 | Tiered JIT | P3 | Compiler Lead |  | ✓ |  | ✓ |  | 52 | Critical | Specified | Execution tiers transition safely | 100% test pass
FEAT-03-116 | OSR on-stack replacement | P3 | Compiler Lead |  | ✓ |  | ✓ |  | 44 | Critical | Specified | Hot loops transition safely | 100% test pass
FEAT-03-117 | Code cache management | P3 | Compiler Lead |  | ✓ | ✓ |  |  | 28 | High | Specified | Compiled code invalidates safely | 100% test pass
FEAT-03-118 | Deopt reason analytics | P3 | Compiler Lead |  | ✓ |  | ✓ |  | 20 | Medium | Specified | Deopt causes measurable | 100% test pass
FEAT-03-119 | Escape analysis | P3 | Compiler Lead |  | ✓ |  | ✓ |  | 42 | High | Specified | Nonescaping allocations optimized | 100% test pass
FEAT-03-120 | Allocation-site profiling | P2 | Performance Lead |  | ✓ | ✓ | ✓ |  | 26 | Medium | Specified | Hot allocation sites identified | 100% test pass
FEAT-03-121 | Heap graph analytics | P2 | Tooling Lead |  | ✓ | ✓ | ✓ |  | 34 | Medium | Specified | Retention paths queryable | 100% test pass
FEAT-03-122 | GC policy simulator | P2 | GC Lead |  | ✓ | ✓ | ✓ |  | 36 | Medium | Specified | Policies compared offline | 100% test pass
FEAT-03-123 | Allocation trace replay | P2 | GC Lead |  | ✓ | ✓ |  |  | 28 | Medium | Specified | Workloads replay deterministically | 100% test pass
FEAT-03-124 | Runtime experiment framework | P2 | Research Lead | ✓ | ✓ | ✓ | ✓ |  | 30 | Medium | Specified | A/B configurations reproducible | 100% test pass
FEAT-03-125 | Automated benchmark report | P1 | Performance Lead | ✓ | ✓ | ✓ | ✓ |  | 22 | Low | Specified | Comparable benchmark reports | 100% test pass
FEAT-03-126 | Capacity planning model | P2 | SRE |  | ✓ | ✓ | ✓ |  | 28 | Medium | Specified | Resource needs projected | 100% test pass
FEAT-03-127 | Cost/performance optimizer | P3 | Performance/SRE |  | ✓ | ✓ | ✓ |  | 34 | Medium | Specified | Bounded cost/latency optimization | 100% test pass
FEAT-03-128 | Remote debugging | P3 | Tooling Lead | ✓ | ✓ |  |  |  | 38 | High | Specified | Authenticated remote sessions | 100% test pass
FEAT-03-129 | Telemetry privacy controls | P1 | Security Lead | ✓ | ✓ | ✓ |  |  | 20 | High | Specified | Sensitive telemetry minimized | 100% test pass
FEAT-03-130 | Data retention policy | P1 | SRE/Security | ✓ | ✓ | ✓ |  |  | 18 | Medium | Specified | Retention enforced | 100% test pass
FEAT-03-131 | Offline/air-gapped mode | P2 | DevOps |  | ✓ | ✓ |  |  | 30 | Medium | Specified | Runtime works without external services | 100% test pass
FEAT-03-132 | Embedded/device profile | P3 | Runtime Lead |  | ✓ |  |  |  | 34 | High | Specified | Runtime fits constrained targets | 100% test pass
FEAT-03-133 | Server profile | P2 | Runtime/SRE |  | ✓ | ✓ | ✓ |  | 26 | Medium | Specified | Long-lived services optimized | 100% test pass
FEAT-03-134 | Edge profile | P3 | Runtime Lead |  | ✓ | ✓ | ✓ |  | 30 | High | Specified | Intermittent connectivity supported | 100% test pass
FEAT-03-135 | Distributed execution research | P4 | Research Lead |  | ✓ | ✓ | ✓ |  | 60 | Critical | Specified | Prototype semantics and failure model | 100% test pass
FEAT-03-136 | GPU acceleration research | P4 | Performance Lead |  | ✓ |  | ✓ |  | 54 | Critical | Specified | Experimental path has fallback | 100% test pass
FEAT-03-137 | Formal invariant specification | P2 | VM/GC Lead |  | ✓ |  |  |  | 36 | High | Specified | Core invariants mechanically reviewed | 100% test pass
FEAT-03-138 | Model-based VM testing | P2 | QA/Research |  | ✓ |  | ✓ |  | 32 | High | Specified | State-model tests catch sequencing bugs | 100% test pass
FEAT-03-139 | Security fuzz corpus | P1 | Security/QA |  | ✓ | ✓ | ✓ |  | 26 | High | Specified | Fuzz corpus minimized/versioned | 100% test pass
FEAT-03-140 | Supply-chain provenance | P1 | DevSecOps |  | ✓ | ✓ |  |  | 20 | High | Specified | Build provenance verifiable | 100% test pass
FEAT-03-141 | Artifact reproducibility | P1 | DevOps |  | ✓ | ✓ |  |  | 22 | High | Specified | Equivalent artifacts reproduced | 100% test pass

## Frontend
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-03-001 | Bytecode format & versioning | P0 | VM Lead | 20 | Critical | Specified | Stable encoding/decoding and explicit version compatibility | 100% test pass
FEAT-03-002 | Opcode set | P0 | VM Lead | 24 | Critical | Specified | Every opcode has defined semantics and tests | 100% test pass
FEAT-03-003 | Bytecode verifier | P0 | VM/Security | 30 | Critical | Specified | Malformed bytecode rejected before execution | 100% test pass
FEAT-03-004 | Constant pool | P0 | VM Lead | 20 | High | Specified | Constants load safely | 100% test pass
FEAT-03-005 | Instruction decoder | P0 | VM Lead | 18 | High | Specified | Valid/invalid streams handled deterministically | 100% test pass
FEAT-03-006 | Stack machine | P0 | VM Lead | 32 | Critical | Specified | Stack effects match instruction semantics | 100% test pass
FEAT-03-007 | Call frames | P0 | VM Lead | 30 | Critical | Specified | Nested calls preserve state | 100% test pass
FEAT-03-008 | Closures/upvalues | P1 | VM Lead | 34 | High | Specified | Captured variables remain valid | 100% test pass
FEAT-03-009 | Exception handling | P1 | Runtime Lead | 30 | High | Specified | Exceptions unwind correctly | 100% test pass
FEAT-03-010 | Stack traces | P1 | Runtime Lead | 18 | Medium | Specified | Errors expose stable frames | 100% test pass
FEAT-03-011 | Interpreter dispatch | P0 | VM Lead | 28 | High | Specified | Dispatch is correct and benchmarkable | 100% test pass
FEAT-03-012 | Dispatch profiling | P1 | VM Lead | 18 | Medium | Specified | Hot opcodes are measurable | 100% test pass
FEAT-03-013 | Native/FFI boundary | P1 | Runtime Lead | 30 | Critical | Specified | Native calls cannot corrupt VM state | 100% test pass
FEAT-03-014 | Sandbox/capability model | P0 | Security Lead | 30 | Critical | Specified | Untrusted bytecode cannot exceed capabilities | 100% test pass
FEAT-03-015 | VM resource limits | P0 | Runtime Lead | 22 | Critical | Specified | Instruction/time/stack/memory budgets enforced | 100% test pass
FEAT-03-016 | Heap object model | P0 | GC Lead | 36 | Critical | Specified | Objects allocate/traverse consistently | 100% test pass
FEAT-03-017 | Allocator | P0 | GC Lead | 30 | Critical | Specified | Allocations are aligned and reusable | 100% test pass
FEAT-03-018 | Root set | P0 | GC Lead | 28 | Critical | Specified | All live roots are enumerated | 100% test pass
FEAT-03-019 | Mark phase | P0 | GC Lead | 34 | Critical | Specified | Reachable objects marked correctly | 100% test pass
FEAT-03-020 | Sweep phase | P0 | GC Lead | 30 | Critical | Specified | Unreachable objects reclaimed safely | 100% test pass
FEAT-03-021 | Tri-color invariants | P1 | GC Lead | 24 | High | Specified | Collector invariants preserved | 100% test pass
FEAT-03-022 | Write barriers | P1 | GC Lead | 26 | Critical | Specified | Mutator writes preserve GC invariants | 100% test pass
FEAT-03-023 | Stop-the-world GC | P0 | GC Lead | 24 | High | Specified | Mutator pauses/resumes safely | 100% test pass
FEAT-03-024 | Incremental GC | P2 | GC Lead | 38 | Critical | Specified | GC work interleaves safely | 100% test pass
FEAT-03-025 | Generational GC | P1 | GC Lead | 44 | Critical | Specified | Young/old invariants hold | 100% test pass
FEAT-03-026 | Compacting GC | P2 | GC Lead | 44 | Critical | Specified | References survive relocation | 100% test pass
FEAT-03-027 | Handle table | P1 | Runtime Lead | 24 | High | Specified | Native refs survive GC | 100% test pass
FEAT-03-028 | Weak references | P2 | GC Lead | 24 | High | Specified | Weak refs do not retain objects | 100% test pass
FEAT-03-029 | Finalizers | P2 | GC Lead | 26 | Critical | Specified | Finalization semantics are explicit | 100% test pass
FEAT-03-030 | GC telemetry | P0 | Runtime/SRE | 20 | Medium | Specified | Allocation/pause/heap metrics exposed | 100% test pass
FEAT-03-031 | Heap snapshots | P1 | Tooling Lead | 26 | High | Specified | Heap state can be analyzed | 100% test pass
FEAT-03-032 | Memory leak detector | P1 | Tooling Lead | 30 | High | Specified | Retained-object paths discoverable | 100% test pass
FEAT-03-033 | Source maps | P1 | Tooling Lead | 24 | Medium | Specified | Bytecode maps to source | 100% test pass
FEAT-03-034 | Debugger | P1 | Tooling Lead | 38 | High | Specified | Pause/step/inspect works | 100% test pass
FEAT-03-035 | Profiler | P1 | Performance Lead | 34 | Medium | Specified | CPU/alloc/GC hotspots measurable | 100% test pass
FEAT-03-036 | Execution tracer | P2 | VM Lead | 24 | Medium | Specified | Bounded traces exportable | 100% test pass
FEAT-03-037 | REPL/console | P1 | Tooling Lead | 24 | Low | Specified | Interactive evaluation works safely | 100% test pass
FEAT-03-038 | Bytecode disassembler | P0 | Tooling Lead | 18 | Low | Specified | All bytecode inspectable | 100% test pass
FEAT-03-039 | Compiler frontend | P1 | Compiler Lead | 42 | High | Specified | Source compiles to valid bytecode | 100% test pass
FEAT-03-045 | Concurrency model | P2 | Runtime Lead | 38 | Critical | Specified | Defined thread/task/isolate semantics | 100% test pass
FEAT-03-046 | Async/event loop | P2 | Runtime Lead | 34 | High | Specified | Async tasks resume correctly | 100% test pass
FEAT-03-048 | Deterministic execution | P1 | VM/QA | 26 | High | Specified | Same input reproduces execution | 100% test pass
FEAT-03-049 | Serialization | P1 | Runtime Lead | 28 | High | Specified | Values round-trip safely | 100% test pass
FEAT-03-052 | Runtime configuration | P0 | Runtime Lead | 18 | Low | Specified | Limits/features validate correctly | 100% test pass
FEAT-03-053 | Compatibility matrix | P0 | Release Lead | 20 | High | Specified | Supported combinations tested | 100% test pass
FEAT-03-054 | Crash handling | P0 | Runtime Lead | 24 | Critical | Specified | Crashes produce actionable diagnostics | 100% test pass
FEAT-03-055 | Panic/exception boundary | P0 | Runtime Lead | 20 | Critical | Specified | Host protected from VM failures | 100% test pass
FEAT-03-063 | Security threat model | P0 | Security Lead | 24 | Critical | Specified | Threats/mitigations documented | 100% test pass
FEAT-03-067 | Cross-platform builds | P1 | DevOps | 24 | Medium | Specified | Supported platforms build/test | 100% test pass
FEAT-03-068 | Packaging/distribution | P1 | Release Lead | 20 | Medium | Specified | Versioned packages reproducible | 100% test pass
FEAT-03-070 | Documentation portal | P1 | Tech Writer | 22 | Low | Specified | API/VM/GC docs discoverable | 100% test pass
FEAT-03-071 | Architecture decision records | P1 | Tech Lead | 16 | Low | Specified | Major decisions recorded | 100% test pass
FEAT-03-074 | Metrics/alerts | P0 | SRE | 18 | High | Specified | Critical failures alert with context | 100% test pass
FEAT-03-081 | Lexer/tokenizer | P1 | Compiler Lead | 24 | Medium | Specified | Deterministic tokens and diagnostics | 100% test pass
FEAT-03-082 | AST representation | P1 | Compiler Lead | 24 | Medium | Specified | Stable AST for tooling | 100% test pass
FEAT-03-083 | Type system | P2 | Compiler Lead | 44 | High | Specified | Deterministic type checking | 100% test pass
FEAT-03-084 | Semantic analysis | P1 | Compiler Lead | 34 | High | Specified | Invalid programs rejected before codegen | 100% test pass
FEAT-03-085 | Compiler diagnostics | P1 | Compiler Lead | 22 | Low | Specified | Actionable source diagnostics | 100% test pass
FEAT-03-086 | Module/import system | P1 | Runtime Lead | 34 | High | Specified | Modules resolve and load safely | 100% test pass
FEAT-03-087 | Package/dependency manager | P2 | Release Lead | 38 | High | Specified | Reproducible dependency resolution | 100% test pass
FEAT-03-088 | IDE/LSP integration | P2 | Tooling Lead | 42 | Medium | Specified | Editor navigation and diagnostics | 100% test pass
FEAT-03-095 | Plugin system | P2 | Runtime Lead | 40 | Critical | Specified | Plugins are isolated | 100% test pass
FEAT-03-096 | Multi-tenant isolation | P1 | Security Lead | 38 | Critical | Specified | Tenants cannot access each other | 100% test pass
FEAT-03-100 | Audit log | P1 | Security Lead | 20 | High | Specified | Security actions traceable | 100% test pass
FEAT-03-124 | Runtime experiment framework | P2 | Research Lead | 30 | Medium | Specified | A/B configurations reproducible | 100% test pass
FEAT-03-125 | Automated benchmark report | P1 | Performance Lead | 22 | Low | Specified | Comparable benchmark reports | 100% test pass
FEAT-03-128 | Remote debugging | P3 | Tooling Lead | 38 | High | Specified | Authenticated remote sessions | 100% test pass
FEAT-03-129 | Telemetry privacy controls | P1 | Security Lead | 20 | High | Specified | Sensitive telemetry minimized | 100% test pass
FEAT-03-130 | Data retention policy | P1 | SRE/Security | 18 | Medium | Specified | Retention enforced | 100% test pass

## Backend
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-03-001 | Bytecode format & versioning | P0 | VM Lead | 20 | Critical | Specified | Stable encoding/decoding and explicit version compatibility | 100% test pass
FEAT-03-002 | Opcode set | P0 | VM Lead | 24 | Critical | Specified | Every opcode has defined semantics and tests | 100% test pass
FEAT-03-003 | Bytecode verifier | P0 | VM/Security | 30 | Critical | Specified | Malformed bytecode rejected before execution | 100% test pass
FEAT-03-004 | Constant pool | P0 | VM Lead | 20 | High | Specified | Constants load safely | 100% test pass
FEAT-03-005 | Instruction decoder | P0 | VM Lead | 18 | High | Specified | Valid/invalid streams handled deterministically | 100% test pass
FEAT-03-006 | Stack machine | P0 | VM Lead | 32 | Critical | Specified | Stack effects match instruction semantics | 100% test pass
FEAT-03-007 | Call frames | P0 | VM Lead | 30 | Critical | Specified | Nested calls preserve state | 100% test pass
FEAT-03-008 | Closures/upvalues | P1 | VM Lead | 34 | High | Specified | Captured variables remain valid | 100% test pass
FEAT-03-009 | Exception handling | P1 | Runtime Lead | 30 | High | Specified | Exceptions unwind correctly | 100% test pass
FEAT-03-010 | Stack traces | P1 | Runtime Lead | 18 | Medium | Specified | Errors expose stable frames | 100% test pass
FEAT-03-011 | Interpreter dispatch | P0 | VM Lead | 28 | High | Specified | Dispatch is correct and benchmarkable | 100% test pass
FEAT-03-012 | Dispatch profiling | P1 | VM Lead | 18 | Medium | Specified | Hot opcodes are measurable | 100% test pass
FEAT-03-013 | Native/FFI boundary | P1 | Runtime Lead | 30 | Critical | Specified | Native calls cannot corrupt VM state | 100% test pass
FEAT-03-014 | Sandbox/capability model | P0 | Security Lead | 30 | Critical | Specified | Untrusted bytecode cannot exceed capabilities | 100% test pass
FEAT-03-015 | VM resource limits | P0 | Runtime Lead | 22 | Critical | Specified | Instruction/time/stack/memory budgets enforced | 100% test pass
FEAT-03-016 | Heap object model | P0 | GC Lead | 36 | Critical | Specified | Objects allocate/traverse consistently | 100% test pass
FEAT-03-017 | Allocator | P0 | GC Lead | 30 | Critical | Specified | Allocations are aligned and reusable | 100% test pass
FEAT-03-018 | Root set | P0 | GC Lead | 28 | Critical | Specified | All live roots are enumerated | 100% test pass
FEAT-03-019 | Mark phase | P0 | GC Lead | 34 | Critical | Specified | Reachable objects marked correctly | 100% test pass
FEAT-03-020 | Sweep phase | P0 | GC Lead | 30 | Critical | Specified | Unreachable objects reclaimed safely | 100% test pass
FEAT-03-021 | Tri-color invariants | P1 | GC Lead | 24 | High | Specified | Collector invariants preserved | 100% test pass
FEAT-03-022 | Write barriers | P1 | GC Lead | 26 | Critical | Specified | Mutator writes preserve GC invariants | 100% test pass
FEAT-03-023 | Stop-the-world GC | P0 | GC Lead | 24 | High | Specified | Mutator pauses/resumes safely | 100% test pass
FEAT-03-024 | Incremental GC | P2 | GC Lead | 38 | Critical | Specified | GC work interleaves safely | 100% test pass
FEAT-03-025 | Generational GC | P1 | GC Lead | 44 | Critical | Specified | Young/old invariants hold | 100% test pass
FEAT-03-026 | Compacting GC | P2 | GC Lead | 44 | Critical | Specified | References survive relocation | 100% test pass
FEAT-03-027 | Handle table | P1 | Runtime Lead | 24 | High | Specified | Native refs survive GC | 100% test pass
FEAT-03-028 | Weak references | P2 | GC Lead | 24 | High | Specified | Weak refs do not retain objects | 100% test pass
FEAT-03-029 | Finalizers | P2 | GC Lead | 26 | Critical | Specified | Finalization semantics are explicit | 100% test pass
FEAT-03-030 | GC telemetry | P0 | Runtime/SRE | 20 | Medium | Specified | Allocation/pause/heap metrics exposed | 100% test pass
FEAT-03-031 | Heap snapshots | P1 | Tooling Lead | 26 | High | Specified | Heap state can be analyzed | 100% test pass
FEAT-03-032 | Memory leak detector | P1 | Tooling Lead | 30 | High | Specified | Retained-object paths discoverable | 100% test pass
FEAT-03-033 | Source maps | P1 | Tooling Lead | 24 | Medium | Specified | Bytecode maps to source | 100% test pass
FEAT-03-034 | Debugger | P1 | Tooling Lead | 38 | High | Specified | Pause/step/inspect works | 100% test pass
FEAT-03-035 | Profiler | P1 | Performance Lead | 34 | Medium | Specified | CPU/alloc/GC hotspots measurable | 100% test pass
FEAT-03-036 | Execution tracer | P2 | VM Lead | 24 | Medium | Specified | Bounded traces exportable | 100% test pass
FEAT-03-037 | REPL/console | P1 | Tooling Lead | 24 | Low | Specified | Interactive evaluation works safely | 100% test pass
FEAT-03-038 | Bytecode disassembler | P0 | Tooling Lead | 18 | Low | Specified | All bytecode inspectable | 100% test pass
FEAT-03-039 | Compiler frontend | P1 | Compiler Lead | 42 | High | Specified | Source compiles to valid bytecode | 100% test pass
FEAT-03-040 | Optimizer passes | P2 | Compiler Lead | 44 | High | Specified | Optimizations preserve semantics | 100% test pass
FEAT-03-041 | JIT baseline compiler | P2 | Compiler Lead | 60 | Critical | Specified | Hot functions execute natively correctly | 100% test pass
FEAT-03-042 | JIT profiling | P2 | Compiler Lead | 34 | High | Specified | Hotness identifies candidates | 100% test pass
FEAT-03-043 | Deoptimization | P2 | Compiler Lead | 46 | Critical | Specified | Optimized code returns safely to interpreter | 100% test pass
FEAT-03-044 | Inline caching | P2 | VM/Compiler | 36 | High | Specified | Dynamic operations accelerated safely | 100% test pass
FEAT-03-045 | Concurrency model | P2 | Runtime Lead | 38 | Critical | Specified | Defined thread/task/isolate semantics | 100% test pass
FEAT-03-046 | Async/event loop | P2 | Runtime Lead | 34 | High | Specified | Async tasks resume correctly | 100% test pass
FEAT-03-047 | Scheduler | P2 | Runtime Lead | 30 | High | Specified | Fairness/resource limits enforced | 100% test pass
FEAT-03-048 | Deterministic execution | P1 | VM/QA | 26 | High | Specified | Same input reproduces execution | 100% test pass
FEAT-03-049 | Serialization | P1 | Runtime Lead | 28 | High | Specified | Values round-trip safely | 100% test pass
FEAT-03-050 | VM snapshot/restore | P1 | Runtime Lead | 34 | Critical | Specified | VM state restores/resumes correctly | 100% test pass
FEAT-03-051 | Persistent cache | P2 | Runtime/DBA | 26 | Medium | Specified | Cache invalidates safely | 100% test pass
FEAT-03-052 | Runtime configuration | P0 | Runtime Lead | 18 | Low | Specified | Limits/features validate correctly | 100% test pass
FEAT-03-053 | Compatibility matrix | P0 | Release Lead | 20 | High | Specified | Supported combinations tested | 100% test pass
FEAT-03-054 | Crash handling | P0 | Runtime Lead | 24 | Critical | Specified | Crashes produce actionable diagnostics | 100% test pass
FEAT-03-055 | Panic/exception boundary | P0 | Runtime Lead | 20 | Critical | Specified | Host protected from VM failures | 100% test pass
FEAT-03-056 | Fuzz bytecode verifier | P0 | Security/QA | 28 | Critical | Specified | No crashes/bypasses found | 100% test pass
FEAT-03-057 | GC stress/fuzz | P0 | GC/QA | 34 | Critical | Specified | Random allocation/GC preserves invariants | 100% test pass
FEAT-03-058 | Differential VM testing | P1 | QA/VM | 30 | High | Specified | Optimized/reference paths agree | 100% test pass
FEAT-03-059 | Property-based tests | P1 | QA | 28 | High | Specified | Generated programs preserve invariants | 100% test pass
FEAT-03-060 | Benchmark suite | P0 | Performance Lead | 28 | Medium | Specified | Standard workloads track regressions | 100% test pass
FEAT-03-061 | GC pause benchmark | P0 | GC Lead | 22 | High | Specified | Pause distributions measurable | 100% test pass
FEAT-03-062 | Memory footprint benchmark | P0 | Performance Lead | 22 | High | Specified | RSS/heap overhead tracked | 100% test pass
FEAT-03-063 | Security threat model | P0 | Security Lead | 24 | Critical | Specified | Threats/mitigations documented | 100% test pass
FEAT-03-064 | Capability audit | P0 | Security Lead | 20 | Critical | Specified | Host capabilities least-privilege | 100% test pass
FEAT-03-065 | Dependency/SBOM | P1 | DevSecOps | 14 | Medium | Specified | Dependencies/licenses tracked | 100% test pass
FEAT-03-066 | CI/CD | P0 | DevOps | 22 | High | Specified | Build/test/fuzz/bench gates automatic | 100% test pass
FEAT-03-067 | Cross-platform builds | P1 | DevOps | 24 | Medium | Specified | Supported platforms build/test | 100% test pass
FEAT-03-068 | Packaging/distribution | P1 | Release Lead | 20 | Medium | Specified | Versioned packages reproducible | 100% test pass
FEAT-03-069 | Release signing | P1 | Release/Security | 14 | High | Specified | Artifacts signed/verifiable | 100% test pass
FEAT-03-070 | Documentation portal | P1 | Tech Writer | 22 | Low | Specified | API/VM/GC docs discoverable | 100% test pass
FEAT-03-071 | Architecture decision records | P1 | Tech Lead | 16 | Low | Specified | Major decisions recorded | 100% test pass
FEAT-03-072 | Operational runbook | P0 | SRE | 18 | High | Specified | Operators can diagnose/recover | 100% test pass
FEAT-03-073 | Disaster recovery | P1 | SRE | 24 | Critical | Specified | State restores within RPO/RTO | 100% test pass
FEAT-03-074 | Metrics/alerts | P0 | SRE | 18 | High | Specified | Critical failures alert with context | 100% test pass
FEAT-03-075 | Experiment tracking | P1 | ML/Research | 16 | Medium | Specified | Optimization experiments reproducible | 100% test pass
FEAT-03-076 | ML anomaly detection | P2 | ML/SRE | 34 | High | Specified | Abnormal GC/VM behavior flagged | 100% test pass
FEAT-03-077 | GC policy recommendation | P2 | ML/Performance | 36 | High | Specified | Safe GC parameters recommended | 100% test pass
FEAT-03-078 | Workload classification | P2 | ML/Performance | 30 | Medium | Specified | Workloads classified accurately | 100% test pass
FEAT-03-079 | Adaptive runtime tuning | P2 | ML/Performance | 40 | Critical | Specified | Tuning improves benchmarks without correctness loss | 100% test pass
FEAT-03-080 | ML fallback/kill switch | P0 | ML/Runtime | 12 | Critical | Specified | ML can be disabled with no correctness loss | 100% test pass
FEAT-03-081 | Lexer/tokenizer | P1 | Compiler Lead | 24 | Medium | Specified | Deterministic tokens and diagnostics | 100% test pass
FEAT-03-082 | AST representation | P1 | Compiler Lead | 24 | Medium | Specified | Stable AST for tooling | 100% test pass
FEAT-03-083 | Type system | P2 | Compiler Lead | 44 | High | Specified | Deterministic type checking | 100% test pass
FEAT-03-084 | Semantic analysis | P1 | Compiler Lead | 34 | High | Specified | Invalid programs rejected before codegen | 100% test pass
FEAT-03-085 | Compiler diagnostics | P1 | Compiler Lead | 22 | Low | Specified | Actionable source diagnostics | 100% test pass
FEAT-03-086 | Module/import system | P1 | Runtime Lead | 34 | High | Specified | Modules resolve and load safely | 100% test pass
FEAT-03-087 | Package/dependency manager | P2 | Release Lead | 38 | High | Specified | Reproducible dependency resolution | 100% test pass
FEAT-03-088 | IDE/LSP integration | P2 | Tooling Lead | 42 | Medium | Specified | Editor navigation and diagnostics | 100% test pass
FEAT-03-089 | Intermediate representation | P2 | Compiler Lead | 42 | High | Specified | IR supports optimization | 100% test pass
FEAT-03-090 | Control-flow graph | P2 | Compiler Lead | 26 | Medium | Specified | CFG models all branches | 100% test pass
FEAT-03-091 | Register-based VM option | P3 | VM Lead | 42 | High | Specified | Alternative backend matches reference semantics | 100% test pass
FEAT-03-092 | SIMD/vector operations | P3 | Performance Lead | 34 | High | Specified | Vector ops have safe fallback | 100% test pass
FEAT-03-093 | WebAssembly interoperability | P3 | Runtime Lead | 42 | High | Specified | Interop preserves safety | 100% test pass
FEAT-03-094 | Native extension SDK | P2 | Runtime Lead | 38 | Critical | Specified | Stable documented native ABI | 100% test pass
FEAT-03-095 | Plugin system | P2 | Runtime Lead | 40 | Critical | Specified | Plugins are isolated | 100% test pass
FEAT-03-096 | Multi-tenant isolation | P1 | Security Lead | 38 | Critical | Specified | Tenants cannot access each other | 100% test pass
FEAT-03-097 | CPU quota accounting | P1 | Runtime/SRE | 22 | High | Specified | CPU usage measured per workload | 100% test pass
FEAT-03-098 | Memory quota accounting | P1 | Runtime/SRE | 22 | High | Specified | Memory usage enforced | 100% test pass
FEAT-03-099 | IO/network quota | P2 | Security Lead | 24 | High | Specified | External IO respects quotas | 100% test pass
FEAT-03-100 | Audit log | P1 | Security Lead | 20 | High | Specified | Security actions traceable | 100% test pass
FEAT-03-101 | Secrets management | P1 | DevSecOps | 18 | Critical | Specified | Secrets absent from artifacts/logs | 100% test pass
FEAT-03-102 | Memory corruption detection | P0 | VM/QA | 34 | Critical | Specified | Corruption detected in test builds | 100% test pass
FEAT-03-103 | Sanitizer builds | P1 | DevOps | 20 | High | Specified | Memory/UB/concurrency sanitizer coverage | 100% test pass
FEAT-03-104 | Mutation testing | P2 | QA | 24 | Medium | Specified | Tests kill meaningful mutations | 100% test pass
FEAT-03-105 | Golden bytecode corpus | P0 | QA | 18 | High | Specified | Known programs remain compatible | 100% test pass
FEAT-03-106 | Backward compatibility tests | P0 | Release Lead | 24 | High | Specified | Supported old artifacts execute | 100% test pass
FEAT-03-107 | Upgrade/downgrade tests | P1 | Release Lead | 26 | Critical | Specified | Runtime upgrades preserve state | 100% test pass
FEAT-03-108 | Long-duration soak test | P1 | SRE/QA | 30 | High | Specified | No drift or leak over long runs | 100% test pass
FEAT-03-109 | Fault injection | P1 | SRE/QA | 32 | Critical | Specified | Injected failures recover or fail safely | 100% test pass
FEAT-03-110 | Chaos testing | P2 | SRE | 34 | High | Specified | Dependencies tolerate faults | 100% test pass
FEAT-03-111 | Performance regression gate | P0 | Performance Lead | 20 | High | Specified | CI blocks regressions | 100% test pass
FEAT-03-112 | Binary size optimization | P2 | Release Lead | 18 | Low | Specified | Runtime stays within size budget | 100% test pass
FEAT-03-113 | Startup snapshot | P3 | Runtime Lead | 36 | High | Specified | Preinitialized runtime starts faster | 100% test pass
FEAT-03-114 | Profile-guided optimization | P3 | Compiler Lead | 40 | High | Specified | Profiles improve optimization | 100% test pass
FEAT-03-115 | Tiered JIT | P3 | Compiler Lead | 52 | Critical | Specified | Execution tiers transition safely | 100% test pass
FEAT-03-116 | OSR on-stack replacement | P3 | Compiler Lead | 44 | Critical | Specified | Hot loops transition safely | 100% test pass
FEAT-03-117 | Code cache management | P3 | Compiler Lead | 28 | High | Specified | Compiled code invalidates safely | 100% test pass
FEAT-03-118 | Deopt reason analytics | P3 | Compiler Lead | 20 | Medium | Specified | Deopt causes measurable | 100% test pass
FEAT-03-119 | Escape analysis | P3 | Compiler Lead | 42 | High | Specified | Nonescaping allocations optimized | 100% test pass
FEAT-03-120 | Allocation-site profiling | P2 | Performance Lead | 26 | Medium | Specified | Hot allocation sites identified | 100% test pass
FEAT-03-121 | Heap graph analytics | P2 | Tooling Lead | 34 | Medium | Specified | Retention paths queryable | 100% test pass
FEAT-03-122 | GC policy simulator | P2 | GC Lead | 36 | Medium | Specified | Policies compared offline | 100% test pass
FEAT-03-123 | Allocation trace replay | P2 | GC Lead | 28 | Medium | Specified | Workloads replay deterministically | 100% test pass
FEAT-03-124 | Runtime experiment framework | P2 | Research Lead | 30 | Medium | Specified | A/B configurations reproducible | 100% test pass
FEAT-03-125 | Automated benchmark report | P1 | Performance Lead | 22 | Low | Specified | Comparable benchmark reports | 100% test pass
FEAT-03-126 | Capacity planning model | P2 | SRE | 28 | Medium | Specified | Resource needs projected | 100% test pass
FEAT-03-127 | Cost/performance optimizer | P3 | Performance/SRE | 34 | Medium | Specified | Bounded cost/latency optimization | 100% test pass
FEAT-03-128 | Remote debugging | P3 | Tooling Lead | 38 | High | Specified | Authenticated remote sessions | 100% test pass
FEAT-03-129 | Telemetry privacy controls | P1 | Security Lead | 20 | High | Specified | Sensitive telemetry minimized | 100% test pass
FEAT-03-130 | Data retention policy | P1 | SRE/Security | 18 | Medium | Specified | Retention enforced | 100% test pass
FEAT-03-131 | Offline/air-gapped mode | P2 | DevOps | 30 | Medium | Specified | Runtime works without external services | 100% test pass
FEAT-03-132 | Embedded/device profile | P3 | Runtime Lead | 34 | High | Specified | Runtime fits constrained targets | 100% test pass
FEAT-03-133 | Server profile | P2 | Runtime/SRE | 26 | Medium | Specified | Long-lived services optimized | 100% test pass
FEAT-03-134 | Edge profile | P3 | Runtime Lead | 30 | High | Specified | Intermittent connectivity supported | 100% test pass
FEAT-03-135 | Distributed execution research | P4 | Research Lead | 60 | Critical | Specified | Prototype semantics and failure model | 100% test pass
FEAT-03-136 | GPU acceleration research | P4 | Performance Lead | 54 | Critical | Specified | Experimental path has fallback | 100% test pass
FEAT-03-137 | Formal invariant specification | P2 | VM/GC Lead | 36 | High | Specified | Core invariants mechanically reviewed | 100% test pass
FEAT-03-138 | Model-based VM testing | P2 | QA/Research | 32 | High | Specified | State-model tests catch sequencing bugs | 100% test pass
FEAT-03-139 | Security fuzz corpus | P1 | Security/QA | 26 | High | Specified | Fuzz corpus minimized/versioned | 100% test pass
FEAT-03-140 | Supply-chain provenance | P1 | DevSecOps | 20 | High | Specified | Build provenance verifiable | 100% test pass
FEAT-03-141 | Artifact reproducibility | P1 | DevOps | 22 | High | Specified | Equivalent artifacts reproduced | 100% test pass

## Database
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-03-001 | Bytecode format & versioning | P0 | VM Lead | 20 | Critical | Specified | Stable encoding/decoding and explicit version compatibility | 100% test pass
FEAT-03-004 | Constant pool | P0 | VM Lead | 20 | High | Specified | Constants load safely | 100% test pass
FEAT-03-008 | Closures/upvalues | P1 | VM Lead | 34 | High | Specified | Captured variables remain valid | 100% test pass
FEAT-03-016 | Heap object model | P0 | GC Lead | 36 | Critical | Specified | Objects allocate/traverse consistently | 100% test pass
FEAT-03-017 | Allocator | P0 | GC Lead | 30 | Critical | Specified | Allocations are aligned and reusable | 100% test pass
FEAT-03-018 | Root set | P0 | GC Lead | 28 | Critical | Specified | All live roots are enumerated | 100% test pass
FEAT-03-020 | Sweep phase | P0 | GC Lead | 30 | Critical | Specified | Unreachable objects reclaimed safely | 100% test pass
FEAT-03-025 | Generational GC | P1 | GC Lead | 44 | Critical | Specified | Young/old invariants hold | 100% test pass
FEAT-03-027 | Handle table | P1 | Runtime Lead | 24 | High | Specified | Native refs survive GC | 100% test pass
FEAT-03-028 | Weak references | P2 | GC Lead | 24 | High | Specified | Weak refs do not retain objects | 100% test pass
FEAT-03-029 | Finalizers | P2 | GC Lead | 26 | Critical | Specified | Finalization semantics are explicit | 100% test pass
FEAT-03-030 | GC telemetry | P0 | Runtime/SRE | 20 | Medium | Specified | Allocation/pause/heap metrics exposed | 100% test pass
FEAT-03-031 | Heap snapshots | P1 | Tooling Lead | 26 | High | Specified | Heap state can be analyzed | 100% test pass
FEAT-03-032 | Memory leak detector | P1 | Tooling Lead | 30 | High | Specified | Retained-object paths discoverable | 100% test pass
FEAT-03-049 | Serialization | P1 | Runtime Lead | 28 | High | Specified | Values round-trip safely | 100% test pass
FEAT-03-050 | VM snapshot/restore | P1 | Runtime Lead | 34 | Critical | Specified | VM state restores/resumes correctly | 100% test pass
FEAT-03-051 | Persistent cache | P2 | Runtime/DBA | 26 | Medium | Specified | Cache invalidates safely | 100% test pass
FEAT-03-052 | Runtime configuration | P0 | Runtime Lead | 18 | Low | Specified | Limits/features validate correctly | 100% test pass
FEAT-03-053 | Compatibility matrix | P0 | Release Lead | 20 | High | Specified | Supported combinations tested | 100% test pass
FEAT-03-057 | GC stress/fuzz | P0 | GC/QA | 34 | Critical | Specified | Random allocation/GC preserves invariants | 100% test pass
FEAT-03-061 | GC pause benchmark | P0 | GC Lead | 22 | High | Specified | Pause distributions measurable | 100% test pass
FEAT-03-062 | Memory footprint benchmark | P0 | Performance Lead | 22 | High | Specified | RSS/heap overhead tracked | 100% test pass
FEAT-03-063 | Security threat model | P0 | Security Lead | 24 | Critical | Specified | Threats/mitigations documented | 100% test pass
FEAT-03-064 | Capability audit | P0 | Security Lead | 20 | Critical | Specified | Host capabilities least-privilege | 100% test pass
FEAT-03-065 | Dependency/SBOM | P1 | DevSecOps | 14 | Medium | Specified | Dependencies/licenses tracked | 100% test pass
FEAT-03-066 | CI/CD | P0 | DevOps | 22 | High | Specified | Build/test/fuzz/bench gates automatic | 100% test pass
FEAT-03-069 | Release signing | P1 | Release/Security | 14 | High | Specified | Artifacts signed/verifiable | 100% test pass
FEAT-03-071 | Architecture decision records | P1 | Tech Lead | 16 | Low | Specified | Major decisions recorded | 100% test pass
FEAT-03-072 | Operational runbook | P0 | SRE | 18 | High | Specified | Operators can diagnose/recover | 100% test pass
FEAT-03-073 | Disaster recovery | P1 | SRE | 24 | Critical | Specified | State restores within RPO/RTO | 100% test pass
FEAT-03-074 | Metrics/alerts | P0 | SRE | 18 | High | Specified | Critical failures alert with context | 100% test pass
FEAT-03-076 | ML anomaly detection | P2 | ML/SRE | 34 | High | Specified | Abnormal GC/VM behavior flagged | 100% test pass
FEAT-03-077 | GC policy recommendation | P2 | ML/Performance | 36 | High | Specified | Safe GC parameters recommended | 100% test pass
FEAT-03-082 | AST representation | P1 | Compiler Lead | 24 | Medium | Specified | Stable AST for tooling | 100% test pass
FEAT-03-086 | Module/import system | P1 | Runtime Lead | 34 | High | Specified | Modules resolve and load safely | 100% test pass
FEAT-03-087 | Package/dependency manager | P2 | Release Lead | 38 | High | Specified | Reproducible dependency resolution | 100% test pass
FEAT-03-094 | Native extension SDK | P2 | Runtime Lead | 38 | Critical | Specified | Stable documented native ABI | 100% test pass
FEAT-03-095 | Plugin system | P2 | Runtime Lead | 40 | Critical | Specified | Plugins are isolated | 100% test pass
FEAT-03-096 | Multi-tenant isolation | P1 | Security Lead | 38 | Critical | Specified | Tenants cannot access each other | 100% test pass
FEAT-03-097 | CPU quota accounting | P1 | Runtime/SRE | 22 | High | Specified | CPU usage measured per workload | 100% test pass
FEAT-03-098 | Memory quota accounting | P1 | Runtime/SRE | 22 | High | Specified | Memory usage enforced | 100% test pass
FEAT-03-099 | IO/network quota | P2 | Security Lead | 24 | High | Specified | External IO respects quotas | 100% test pass
FEAT-03-100 | Audit log | P1 | Security Lead | 20 | High | Specified | Security actions traceable | 100% test pass
FEAT-03-101 | Secrets management | P1 | DevSecOps | 18 | Critical | Specified | Secrets absent from artifacts/logs | 100% test pass
FEAT-03-102 | Memory corruption detection | P0 | VM/QA | 34 | Critical | Specified | Corruption detected in test builds | 100% test pass
FEAT-03-105 | Golden bytecode corpus | P0 | QA | 18 | High | Specified | Known programs remain compatible | 100% test pass
FEAT-03-106 | Backward compatibility tests | P0 | Release Lead | 24 | High | Specified | Supported old artifacts execute | 100% test pass
FEAT-03-107 | Upgrade/downgrade tests | P1 | Release Lead | 26 | Critical | Specified | Runtime upgrades preserve state | 100% test pass
FEAT-03-108 | Long-duration soak test | P1 | SRE/QA | 30 | High | Specified | No drift or leak over long runs | 100% test pass
FEAT-03-109 | Fault injection | P1 | SRE/QA | 32 | Critical | Specified | Injected failures recover or fail safely | 100% test pass
FEAT-03-110 | Chaos testing | P2 | SRE | 34 | High | Specified | Dependencies tolerate faults | 100% test pass
FEAT-03-113 | Startup snapshot | P3 | Runtime Lead | 36 | High | Specified | Preinitialized runtime starts faster | 100% test pass
FEAT-03-117 | Code cache management | P3 | Compiler Lead | 28 | High | Specified | Compiled code invalidates safely | 100% test pass
FEAT-03-120 | Allocation-site profiling | P2 | Performance Lead | 26 | Medium | Specified | Hot allocation sites identified | 100% test pass
FEAT-03-121 | Heap graph analytics | P2 | Tooling Lead | 34 | Medium | Specified | Retention paths queryable | 100% test pass
FEAT-03-122 | GC policy simulator | P2 | GC Lead | 36 | Medium | Specified | Policies compared offline | 100% test pass
FEAT-03-123 | Allocation trace replay | P2 | GC Lead | 28 | Medium | Specified | Workloads replay deterministically | 100% test pass
FEAT-03-124 | Runtime experiment framework | P2 | Research Lead | 30 | Medium | Specified | A/B configurations reproducible | 100% test pass
FEAT-03-125 | Automated benchmark report | P1 | Performance Lead | 22 | Low | Specified | Comparable benchmark reports | 100% test pass
FEAT-03-126 | Capacity planning model | P2 | SRE | 28 | Medium | Specified | Resource needs projected | 100% test pass
FEAT-03-127 | Cost/performance optimizer | P3 | Performance/SRE | 34 | Medium | Specified | Bounded cost/latency optimization | 100% test pass
FEAT-03-129 | Telemetry privacy controls | P1 | Security Lead | 20 | High | Specified | Sensitive telemetry minimized | 100% test pass
FEAT-03-130 | Data retention policy | P1 | SRE/Security | 18 | Medium | Specified | Retention enforced | 100% test pass
FEAT-03-131 | Offline/air-gapped mode | P2 | DevOps | 30 | Medium | Specified | Runtime works without external services | 100% test pass
FEAT-03-133 | Server profile | P2 | Runtime/SRE | 26 | Medium | Specified | Long-lived services optimized | 100% test pass
FEAT-03-134 | Edge profile | P3 | Runtime Lead | 30 | High | Specified | Intermittent connectivity supported | 100% test pass
FEAT-03-135 | Distributed execution research | P4 | Research Lead | 60 | Critical | Specified | Prototype semantics and failure model | 100% test pass
FEAT-03-139 | Security fuzz corpus | P1 | Security/QA | 26 | High | Specified | Fuzz corpus minimized/versioned | 100% test pass
FEAT-03-140 | Supply-chain provenance | P1 | DevSecOps | 20 | High | Specified | Build provenance verifiable | 100% test pass
FEAT-03-141 | Artifact reproducibility | P1 | DevOps | 22 | High | Specified | Equivalent artifacts reproduced | 100% test pass

## AIML
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target
FEAT-03-032 | Memory leak detector | P1 | Tooling Lead | 30 | High | Specified | Retained-object paths discoverable | 100% test pass
FEAT-03-035 | Profiler | P1 | Performance Lead | 34 | Medium | Specified | CPU/alloc/GC hotspots measurable | 100% test pass
FEAT-03-040 | Optimizer passes | P2 | Compiler Lead | 44 | High | Specified | Optimizations preserve semantics | 100% test pass
FEAT-03-041 | JIT baseline compiler | P2 | Compiler Lead | 60 | Critical | Specified | Hot functions execute natively correctly | 100% test pass
FEAT-03-042 | JIT profiling | P2 | Compiler Lead | 34 | High | Specified | Hotness identifies candidates | 100% test pass
FEAT-03-043 | Deoptimization | P2 | Compiler Lead | 46 | Critical | Specified | Optimized code returns safely to interpreter | 100% test pass
FEAT-03-044 | Inline caching | P2 | VM/Compiler | 36 | High | Specified | Dynamic operations accelerated safely | 100% test pass
FEAT-03-056 | Fuzz bytecode verifier | P0 | Security/QA | 28 | Critical | Specified | No crashes/bypasses found | 100% test pass
FEAT-03-057 | GC stress/fuzz | P0 | GC/QA | 34 | Critical | Specified | Random allocation/GC preserves invariants | 100% test pass
FEAT-03-058 | Differential VM testing | P1 | QA/VM | 30 | High | Specified | Optimized/reference paths agree | 100% test pass
FEAT-03-059 | Property-based tests | P1 | QA | 28 | High | Specified | Generated programs preserve invariants | 100% test pass
FEAT-03-060 | Benchmark suite | P0 | Performance Lead | 28 | Medium | Specified | Standard workloads track regressions | 100% test pass
FEAT-03-061 | GC pause benchmark | P0 | GC Lead | 22 | High | Specified | Pause distributions measurable | 100% test pass
FEAT-03-063 | Security threat model | P0 | Security Lead | 24 | Critical | Specified | Threats/mitigations documented | 100% test pass
FEAT-03-066 | CI/CD | P0 | DevOps | 22 | High | Specified | Build/test/fuzz/bench gates automatic | 100% test pass
FEAT-03-071 | Architecture decision records | P1 | Tech Lead | 16 | Low | Specified | Major decisions recorded | 100% test pass
FEAT-03-074 | Metrics/alerts | P0 | SRE | 18 | High | Specified | Critical failures alert with context | 100% test pass
FEAT-03-075 | Experiment tracking | P1 | ML/Research | 16 | Medium | Specified | Optimization experiments reproducible | 100% test pass
FEAT-03-076 | ML anomaly detection | P2 | ML/SRE | 34 | High | Specified | Abnormal GC/VM behavior flagged | 100% test pass
FEAT-03-077 | GC policy recommendation | P2 | ML/Performance | 36 | High | Specified | Safe GC parameters recommended | 100% test pass
FEAT-03-078 | Workload classification | P2 | ML/Performance | 30 | Medium | Specified | Workloads classified accurately | 100% test pass
FEAT-03-079 | Adaptive runtime tuning | P2 | ML/Performance | 40 | Critical | Specified | Tuning improves benchmarks without correctness loss | 100% test pass
FEAT-03-080 | ML fallback/kill switch | P0 | ML/Runtime | 12 | Critical | Specified | ML can be disabled with no correctness loss | 100% test pass
FEAT-03-083 | Type system | P2 | Compiler Lead | 44 | High | Specified | Deterministic type checking | 100% test pass
FEAT-03-089 | Intermediate representation | P2 | Compiler Lead | 42 | High | Specified | IR supports optimization | 100% test pass
FEAT-03-092 | SIMD/vector operations | P3 | Performance Lead | 34 | High | Specified | Vector ops have safe fallback | 100% test pass
FEAT-03-102 | Memory corruption detection | P0 | VM/QA | 34 | Critical | Specified | Corruption detected in test builds | 100% test pass
FEAT-03-109 | Fault injection | P1 | SRE/QA | 32 | Critical | Specified | Injected failures recover or fail safely | 100% test pass
FEAT-03-111 | Performance regression gate | P0 | Performance Lead | 20 | High | Specified | CI blocks regressions | 100% test pass
FEAT-03-114 | Profile-guided optimization | P3 | Compiler Lead | 40 | High | Specified | Profiles improve optimization | 100% test pass
FEAT-03-115 | Tiered JIT | P3 | Compiler Lead | 52 | Critical | Specified | Execution tiers transition safely | 100% test pass
FEAT-03-116 | OSR on-stack replacement | P3 | Compiler Lead | 44 | Critical | Specified | Hot loops transition safely | 100% test pass
FEAT-03-118 | Deopt reason analytics | P3 | Compiler Lead | 20 | Medium | Specified | Deopt causes measurable | 100% test pass
FEAT-03-119 | Escape analysis | P3 | Compiler Lead | 42 | High | Specified | Nonescaping allocations optimized | 100% test pass
FEAT-03-120 | Allocation-site profiling | P2 | Performance Lead | 26 | Medium | Specified | Hot allocation sites identified | 100% test pass
FEAT-03-121 | Heap graph analytics | P2 | Tooling Lead | 34 | Medium | Specified | Retention paths queryable | 100% test pass
FEAT-03-122 | GC policy simulator | P2 | GC Lead | 36 | Medium | Specified | Policies compared offline | 100% test pass
FEAT-03-124 | Runtime experiment framework | P2 | Research Lead | 30 | Medium | Specified | A/B configurations reproducible | 100% test pass
FEAT-03-125 | Automated benchmark report | P1 | Performance Lead | 22 | Low | Specified | Comparable benchmark reports | 100% test pass
FEAT-03-126 | Capacity planning model | P2 | SRE | 28 | Medium | Specified | Resource needs projected | 100% test pass
FEAT-03-127 | Cost/performance optimizer | P3 | Performance/SRE | 34 | Medium | Specified | Bounded cost/latency optimization | 100% test pass
FEAT-03-133 | Server profile | P2 | Runtime/SRE | 26 | Medium | Specified | Long-lived services optimized | 100% test pass
FEAT-03-134 | Edge profile | P3 | Runtime Lead | 30 | High | Specified | Intermittent connectivity supported | 100% test pass
FEAT-03-135 | Distributed execution research | P4 | Research Lead | 60 | Critical | Specified | Prototype semantics and failure model | 100% test pass
FEAT-03-136 | GPU acceleration research | P4 | Performance Lead | 54 | Critical | Specified | Experimental path has fallback | 100% test pass
FEAT-03-138 | Model-based VM testing | P2 | QA/Research | 32 | High | Specified | State-model tests catch sequencing bugs | 100% test pass
FEAT-03-139 | Security fuzz corpus | P1 | Security/QA | 26 | High | Specified | Fuzz corpus minimized/versioned | 100% test pass

## API
ID | Feature | Priority | Area | Est. Hours | Risk | Status | Acceptance Criteria | KPI / Target